Easy Project

User's Manual

Easy Project Version 1.0

December 13, 1989

Published by:

William H. Roetzheim & Association

13518 Jamul Drive

Jamul, CA  92035

(619) 669-6970

Table of Contents

1.   Terms and Conditions

Shareware Concept

Other Software Available

Copyright

Limited Warranty

License Agreement

2.   Introduction

How to Use This Manual

Easy Project Overview

Hardware Requirements

Installing Easy Project

Comments, Suggestions, Bugs, Etc.

3.   Getting Started

Running Easy Project

Using the Menu

Easy Project Functional Flow

Easy Project Screen Oriented Data Entry

4.   Setup

Organization

Display

Version

Reproduce

5.   Plan/WBS

Add

Modify

Delete

Range

View

Goto

6.   Plan/Cost

Project

Standard Product

Labor Intensive

7.   Plan/Dependencies

Modify

Designate

8.   Plan/Risk

9.   Plan/Schedule

Modify

Range

Shift

View

10.  Track

Timesheets

Expenses

Report

Post

11.  File

12.  Report

Options

WBS

Cost

Dependencies

Risk

Schedule

Evaluate

13.  Reference

Terms and Conditions

Shareware Concept

Shareware is software which is distributed free (or almost free) so that

you can try it.  If the software is useful to you, you are then asked to send a

small payment directly to the author of the software.  The entire concept of

shareware software will only work if people are honest in forwarding the

payments to the individual who worked to develop the software in the first

place.

If you find this program useful, please send $25 along with your name

and address to William H. Roetzheim, 13518 Jamul Drive, Jamul, CA  92035.

Registering your copy of the software entitles you to customer support and

a free subscription to our project management newsletter.  For an additional

$10 ($35 total) you will receive these benefits plus the complete source code

to Easy Project version.

Other Products

William H. Roetzheim & Associates also offers an advanced project

management program that features:

o    Graphical, iconic user interface with mouse support

o    Up to 10,000 tasks.

o    Outline Mode

o    Full support for DOD-STD-2167A and C/SCSC cost accounting

o    LAN Support

o    Graphical reports, including histograms and PERT plots

o    Much, much more

For more information, call (619) 669-6970 for descriptive literature.

Copyright

Copyright 1988 by William H. Roetzheim and Associates.  All rights

reserved worldwide.  This document, and the program material included with

it, are the exclusive property of William H. Roetzheim and Associates.  You

are granted the right to reproduce this document and the program disk with

the following constraints:

o    No part of the program may be sold (although a nominal

duplication fee is permissible).

o    The files EASYPROJ.EXE, EASYPROJ.DOC, and XXXX0001

must be included with any copy distributed, and no changes may

be made to these files.

o    Package distributions (i.e. bundling the software with hardware

or other software) must pay a license fee of $5 per copy to

William H. Roetzheim & Associates.

Limited Warranty

This program is sold strictly "as is", with no warranties express or

implied.  We will not be liable for any damages, including consequential,

indirect, or special damages (including loss of profits or any other commercial

damage).

Introduction

How to Use This Manual

This manual assumes that you are familiar with the basics of your

computer's operating system, the keyboard layout of your computer, and basic

concepts of project management.  If necessary, begin by reviewing your

computers owner's manual for basics about your computer.  If you are not an

experienced project manager, you may want to refer to the book "Structured

Computer Project Management" (Prentice-Hall, 1988).

Easy Project makes extensive use of command line menus.  When we

are describing a specific menu option, we will describe it using the complete

path from the top level menu.  For example, if a menu is reached by selecting

Plan from the top menu followed by WBS from the next menu level, we

would show this option as Plan/WBS.

By all means, read this manual while sitting in front of your computer.

Easy project displays hundreds of different screens.  When writing this

manual, we assume that you will be following along with the text by pressing

the appropriate options on your computer.

Easy Project Overview

Easy project is a project management tool specifically designed to

assist computer professionals in the following areas:

o    Evaluating projects to determine risk, financial attractiveness,

and cash flow.

o    Planning all aspects of a project, including task decomposition

(work breakdown structure), labor and financial requirements,

task inter-relationships (dependencies), risk, and the actual

schedule.

o    Tracking expenditures, including both hours and dollars, as they

are incurred.  Predicting overruns or underruns as early as

possible.

To the greatest extent possible, we provide these capabilities in a user

friendly, flexible fashion which simplifies the process of entering and

maintaining project information.  Some of the more innovative Easy Project

features in this area are:

o    Use of a hierarchical approach to entering and viewing project

information.

o    Project windowing support.

o    Screen oriented data entry with field specific prompts displayed.

Hardware Requirements

Easy Project supports the IBM-PC and fully compatible computers

equipped with at least one disk drive and 320 Kbytes of available RAM.  The

more memory you have installed the larger your project can be.  Remember

that memory resident programs subtract from available memory and reduce

the number of tasks you can have in your project.  The exact number of tasks

you may create on your system is displayed on the Plan/WBS screen, and will

be about 1,000 for a system with 640 Kbytes of RAM.

Easy Project supports both monochrome and color displays.  Because

many users may switch between computers with monochrome and color

displays, the program senses the type of display and automatically displays

either colors or black and white as appropriate.  If you are using a

monochrome display which acts like a color display using shades of green (or

amber), you will want to use the DOS mode command to put your display in

the black and white mode (mode BW80 or mode mono) prior to running

Easy Project.

Easy project supports any printer which is capable of displaying the

IBM enhanced character set.  This includes the IBM Pro-Printer and most

Epson printers.  If your printer does not support the IBM enhanced character

set, all reports should work except Report/WBS/Hierarchy and

Report/Schedule/Gantt.  The Setup/Organization menu options lets you

designate if reports should be sent to the parallel port (default) or the serial

port.  If you are using lpt2: or com2: rather than lpt1:/com1:, you must use

the DOS mode command to redirect printer output to the appropriate

communication port prior to running Easy Project.

Installing Easy Project

Easy Project is distributed on a single disk, which is not copy

protected.  As with all software, begin by making a backup copy of the Easy

Project distribution disk and putting the original away in a save place

(diskcopy or copy *.* work fine).  If you have a hard disk, create a new

directory called \easyproj (mkdir c:\easyproj) and copy the Easy Project files

into this directory.

Comments, Suggestions, Bugs, Etc.

If you would like to see improvements, tell us your ideas.  If you wish

that Easy Project interfaced with your favorite program, let us know exactly

what type of information you would like to transfer.  Of course, we are always

grateful for any information you can provide us which will help us find any

program defects (bugs).

When writing to us, please include as much specific information as

possible.  For defects, try to isolate the program to the point where you can

consistently reproduce the symptoms.  Then give us specific instructions which

will allow us to see the problem ourselves.  You may want to send us a disk

with a sample data file on it if this is necessary to see the problem.

When writing, our address is:

William H. Roetzheim & Associates

13518 Jamul Drive, Jamul, CA  92035

(619) 669-6970

Getting Started

Running Easy Project

While it runs, Easy Project creates temporary files on the default drive.

For this reason, you should ensure that your default drive is the

drive/directory containing the Easy Project program.  On floppy disk systems,

this can be accomplished by setting the drive to the appropriate floppy

designator (i.e. A:).  On hard disk systems, you would type in C: followed by

changing directories to the Easy Project directory (i.e. cd \EASYPROJ).

Easy project uses your system date as set within DOS.  It is important

that your computer date is accurate.  If this is not automatically set for you,

use the DOS date command to set the correct date prior to running Easy

Project.

If your computer has a color display card (EGA, VGA or CGA) but

a black and white monitor, you should use the DOS mode command to set

your display to black and white mode.

To run Easy Project, type in EASYPROJ <cr>.

Using the Menu

At this point, you may want to run Easy Project and follow along on

your computer as you read the manual.

All top level choices in Easy Project are made using a command line

menu displayed at the top of your screen.  The current choice is the

highlighted item.  You may change the current choice using the arrow keys

or the space bar.  Line three on your screen displays a specific summary of

what that option is used for.  Use the arrow keys now to see how this works.

You may select a menu item by highlighting it and pressing return, or

by pressing the keyboard key matching the first letter of your choice (i.e. to

choose Plan you would press 'P').

Quit always brings you to the next higher level in the menu hierarchy.

Pressing ESC (escape) is the same as pressing quit.

Easy Project Functional Flow

The Easy Project top menu contains the following choices:

o    Plan

o    Track

o    File

o    Report

o    Setup

o    Quit

Setup is used for operations which are normally performed only rarely,

including system initialization.  We will look at the Setup option in more

depth in the following chapter as part of our Easy Project system

initialization, but Setup is not part of the normal project management

functional flow.

The normal project planning flow looks like this:

Plan - Report - Track

You plan a project, print reports based on your plan, then continuously

track the project during its life (printing periodic reports based on the

project's progress).  Obviously, you use File to save and retrieve your project

to disk during its life.

When planning a project, we have found that it is best to perform the

work in five distinct steps, as follows:

1.   Plan/WBS

2.   Plan/Costs

3.   Plan/Dependencies

4.   Plan/Risk

5.   Plan/Schedule

Plan/WBS allows you to generate a hierarchical work breakdown

structure (WBS) describing all tasks to be performed and hardware to be

delivered.  This initial thinking process should not be clouded by cost

considerations.  After a WBS is roughed out, specific costs and resource

requirements can be estimated for each task using Plan/Costs.  Dependencies

and risks are specified using Plan/Dependencies and Plan/Risk respectively.

Finally, all of this information serves as an input to preparation of a

reasonable project schedule using Plan/Schedule.

With this general view of project mangement in mind, the Easy Project

menu hierarchy shown below should make sense.  Items followed by an

asterick (*) contain menu levels not shown.

Plan

WBS (*)

Costs (*)

Dependencies (*)

Risk (*)

Schedule (*)

Track

Timesheets

Expenses

Report

Timesheets

Employee

Project

Costs

Supplier

Project

Post

File

Save

Recall

Purge

Directory

Report

WBS

Hierarchy

Detail

Cost

Dollars

Hours

Loading

Dependencies

Risk

Schedule

Task

Gantt

Evaluate

ROI/ATO

Balance Sheet

Income

Options

Print_Queue

Activate

Print

Deactivate

Destination

Screen

Printer

Disk

Setup

Organization

Display

Version

Reproduce

Easy Project Screen Oriented Data Entry

Throughout the program, Easy Project uses a screen oriented data

entry approach.  Although we won't actually setup our organizational

parameters until the next chapter, let's use this screen as a sample of Easy

Project's general approach to data entry.  From the main menu, select

Setup/Organization.  Ignore the meaning behind the displayed fields for the

moment.

A data entry screen consists of multiple data entry fields.  You can use

the up and down arrow keys on your keyboard to advance from field to field.

Try this now.  Notice that at the bottom of the screen, down arrow takes you

to the top of the screen.  Similarly, an up arrow key from the first field will

take you to the bottom of the screen.  Return (<cr>) and TAB work the

same as down arrow.  Back TAB (shifted TAB) works like an up arrow.

From all data entry screens, your keyboard's HOME key will take you

to the first valid field.  END takes you to the last valid field.  Try this.

Some data entry field access an array of information.  On the

Setup/Organization screen, this applies to the fields associated with

employees, suppliers, and lease (at the bottom).  Move your cursor down to

the employee # field at this point (it should currently have a value of zero).

Notice that if you leave the field value at zero and press down arrow, you

skip the fields for employee name and cost.  This is because employee zero

is not used.  Move back to the employee # field and change the zero to 1.

Now, pressing down arrow allows you to enter a value for the Name and Cost

of employee number 1.  Moving back to the employee # field, you can enter

the number 2 to enter data for the second employee.  By entering a number

between 1 and 249 in the employee # field you can enter data for up to 249

different employees.

Use the HOME key to move your cursor back to the first field on the

screen (Name).  Let's look at some of the editing features available to us

within a specific field:

o    For fields which may not be obvious, the upper right corner of

your screen displays a prompt window.  You may have noticed

that as you moved your cursor around the form, the prompt

displayed in this window matched the active field.

o    The field length shows you how many characters you may type.

Your cursor will not advance past the end of the data entry

field.

o    By default, data is entered in the overwrite mode.  Pressing the

INSERT key on your keyboard toggles between insert and

overwrite mode.

o    BACKSPACE deletes the character to the left of your cursor

(like a typewriter).  DEL deletes the character under your

cursor.

o    Pressing <cr>, up arrow, down arrow, TAB, or backtab accepts

the field and advances the cursor (active field).  When the field

is accepted, the system automatically checks the field for validity

and formats your entry if appropriate.

When you are done entering data into a form, you can take two

possible actions.  If you changed your mind and would like to exit without

making any of your changes permanent, you can press ESC.  If you would like

to exit and save your changes, you must press the F10 key (function key 10).

F10 is used throughout Easy Project as an 'accept screen' key.

Press ESC at this point to exit Setup/Organization without making any

changes permanent.  In the following chapter we will actually enter the

proper values.

Setup

Setup contains options which are used relatively infrequently.

Selecting Setup from the main menu displays the following sub-menu:

o    Organization

o    Display

o    Version

o    Reproduce

o    Quit

Each of these options will be discussed individually in the following

sections of this chapter.

Organization

This option allows you to set system parameters which are used by

Easy Project for all projects.  The fields have the following meanings:

o    Name/Addr:  These four free-form fields are used to enter your

company name and address.  The last line may be used for the

company phone number, if desired.  These four lines are

printed at the top of all reports output by Easy Project.

o    Optimum Constant 1 and 2:  Easy Project uses the total man-

power requirements for each task to determine an optimum task

duration in days.  For extremely small tasks, the optimum

duration is based on one person working full time on the task.

For larger tasks, the optimum duration is calculated as follows:

Optimum = constant_1 * mean ** constant_2

You can think of constant 1 as a scaling factor, and constant 2

as a number which determines what happens as tasks get bigger.

Raising or lowering constant 1 will raise or lower the optimum

duration for all tasks.  Seting constant 2 to 1.0 will result in task

durations being linearly related to manpower requirements.  A

number less than 1.0 says that bigger tasks should have more

people working on them and thus take less time per man-hour.

Our experience has shown that a value of 4.0 for constant 1 and

0.60 for constant 2 works well for most companies.

o    Penalty Constant 1 and 2:  If desired, Easy Project will predict

cost penalties associated with completing a task in less than the

optimal duration (crashing the project).  This option is discussed

fully in the chapter of this manual covering Plan/Schedule.  The

core of the calculation looks at the following ratio:

Optimum duration ** constant_1

-------------------------------

Actual duration ** constant_2

We have found that a value of 2.0 for constants 1 and 2

matches observed project performance well for most companies.

o    Discount Rate:  This number is entered to allow calculation of

discounted cash flows, discounted ROI/ROA, etc.  You may use

your estimate of the future inflation rate as an approximation.

o    System Printer:  This field should normally be left at lpt1:.  If

you use a serial printer (RS-232), set this field to com1:.  You

must use the DOS mode command to redirect output if you

wish to use lpt2: or com2:.

o    Average AP and AR Delay:  Easy Project uses these values

when preparing pro-forma financial statements and profit

analysis.  AP delay is the average number of months you delay

paying your bills for hardware (Easy Project assumes that your

employees are paid in the month they work).  AR delay is the

average number of months you expect your customer to delay

paying your invoices sent to them (this applies to hardware and

labor).  AR delay should include any acceptance periods

required by the contract.

o    Burden Rates:  When using Easy Project, you will enter direct

costs for items (actual employee salaries, your cost for

equipment, etc.)  All companies then add a burden (overhead)

charge to the direct cost to determine their burdened cost.

Most companies have more than one burden rate.  For example,

hardware might be burdened at a rate of 1.20, labor at a rate

of 2.1, maintenance activities at 1.7, and inter-company work at

1.05.  Burden category 0 (which is valid) is always 1.0, i.e no

burden applied.  On this screen, you can modify the other five

burden categories to match those in your company.  See your

accountant for the actual values to use, if necessary.

o    Markup Rates:  When using Easy Project, your price to the

customer is determined by applying a markup to your burdened

cost for an item.  As with burden rates, markup category 0 is

1.0 (i.e. no markup).  The other five markup categories can be

entered using this screen.  Once again, see your accountant for

the actual values to use.

o    Employees:  By entering various employee numbers, you can

enter up to 249 different employees (names and hourly cost).

The hourly cost is entered as dollars and cents.  We recommend

that you use the first 20 numbers for generic categories of

employees (programmer, system analyst, etc.) and the remainder

of the numbers for actual employees (Jane Doe).  In this way

you can initially plan a project in generic terms, substituting

individual names as you assign people to tasks.  Note that these

employee reference numbers will normally be different than

your company employee numbers used for accounting purposes.

o    Suppliers:  You can enter up to 99 different supplier names.

These are used when recording expenses charged to your

project.

o    Lease:  If you will never deal with sales of hardware as part of

your project, or all hardware is sold (not leased), you can skip

this area completely.  If your project may include leasing some

hardware to your customer, these fields are used to define the

lease terms.  The month you deliver the hardware is month

one.  For that month and all subsequent months of the lease,

you will need to enter the percentage of the price which you bill

as the monthly lease payment and the percentage of your cost

which you depreciate as leasehold inventory depreciation.  For

a five year lease, you do this for months 1 through 60.  Easy

Project handles leases of up to 10 years.  Note that if you make

multiple deliveries during the project, each will be analyzed for

the entire lease term starting with the delivery date.

Remember, press F10 to accept the screen and save the data, ESC to

exit without saving.

Display

Easy Project automatically senses if you are using a color or

monochrome display.  If you are using a monochrome display which displays

shades of gray, you may need to use the DOS mode command to set your

display into black and white mode for optimum clarity.

If you are using a color display, you may use this option to modify the

display colors used by Easy Project.  The colors modified apply to the

following:

o    Screen:  Normal screen display

o    Report:  Used when printing reports to the CRT

o    Input:  Used for data input windows

o    Prompt:  Used for prompt windows

o    Error:  Used for error windows

o    Level 0 - 9:  Used for WBS displays from various plan menus

(Plan/WBS, Plan/Costs, etc.)  Level 0 would be the project,

level 9 would be the most low level, detail sub-task in the

hierarchy.

The following table might be helpful when changing colors:

ForegroundBackground Color

0               0              Black

1               16             Blue

2               32             Green

3               48             Cyan

4               64             Red

5               80             Magenta

6               96             Brown

7               112            White

To use the table, simply pick a desired foreground and background

color, add the two values together, and enter this value in Easy Project.

After you change each value, the foreground and background color

selected is displayed next to your entry on the screen.

Version

This option displays your version number and an address to write with

comments, suggestions, etc.  This is also the address to use when registering

your copy of Easy Project ($25 to register, $35 to register and receive source

code).  Registration includes a free subscription to our newsletter.

Reproduce

If this is a restricted (limited capability) version, this option allows you

to make a reproduction for use by a friend.  If this is a full version of Easy

Project, this option does not do anything.

Plan/WBS

The first step in planning a project is to quantify the specific tasks to

be performed (and items to be delivered).  This is done using the Plan/WBS

menu option from the main menu.  When selecting Plan/WBS, Easy Project

checks to see if a project is already in memory (already entered or loaded

with the File/Restore option).  If not, a new project is created and you are

asked to fill in a project definition screen.

Select Plan/WBS and complete the project definition form (Name,

Short name, Manager, Priority, and Description).  Use the name "Project

Test" for the project name.  Remember to use the prompt window for

explanations of specific fields.  When you are done, press F10 to accept the

screen.

Let's take a minute and examine the Plan/WBS screen.  The top three

lines are our familiar command line menu (although the options are new).

The bottom line of the display is an informational line, and currently shows

us the maximum number of tasks we can enter (determined by our available

RAM) and the current display view (described later in this chapter).  The

center of our screen shows a WBS data entry/display area with the following

information displayed:

o    #:  Sequential task number

o    T:  Task type.  Limited to 'P' for project name, 'S' for standard

products (non-labor related deliverables), or 'L' for labor

intensive tasks.

o    Name:  Task name.  We will see that the tasks at different

levels in our project hierarchy are automatically indented

appropriately.

o    WBS Number:  Based on the WBS hierarchy, WBS numbers are

automatically assigned.  As you delete, move, add, or copy tasks

the WBS numbers are automatically kept up to date.

o    CHRG:  Automatically assigned charge number.  Unlike the

sequential number (which changes as tasks are inserted or

deleted), the task charge number will stay matched to a given

task throughout the life of the project.  When tracking expenses,

this number will be used to record dollars spent.  Note that

these Easy Project charge numbers will probably not be the

same as the charge numbers your company uses for accounting

purposes.

o    Category:  We will see that Easy Project uses a sophisticated

method of categorizing computer related tasks.  This column

shows the category designation for each task.

Notice that one task in the WBS is highlighted.  This is the current

WBS task, and we will refer to this as the WBS cursor in this document.  As

you enter tasks in your WBS, you will find the following keys useful:

o    Right arrow, left arrow, space:  Continue to move the current

command line menu choice.

o    <cr>:  Continues to accept the highlighted command line menu

choice.

o    First letter of menu choice:  Continues to accept that specific

command line menu choice.

o    Up arrow and Down Arrow:  Move the WBS cursor up or down

one task (as appropriate).

o    HOME and END:  Move the WBS cursor to the first or last

task in the hierarchy.

o    PAGE UP and PAGE DOWNP:  Display the next or previous

page of the hierarchy.

o    Control PAGE UP (^PAGE UP) and Control PAGE DOWN

(^PAGE DOWN):  Move the WBS cursor to the next or

previous task at the same level as the current task.  This option

is userful when moving down the hierarchy looking at top level

tasks only.

o    DEL and INS:  Works the same as selecting Delete and

Add/Labor-Intensive from the menu.

The command line menu for the Plan/WBS option of Easy Project

offers the following choices:

o    Add

o    Modify

o    Delete

o    Range

o    View

o    Goto

o    Quit

We will describe each of these options in detail in the sections which

follow.

Add

A project consists of two basic types of tasks.  Standard Products are

items which you company purchases for a fixed cost, marks up, and sells to

the customer.  There is no chargeable labor associated with these items.

Examples are computers, disks, some sub-contracted maintenance, off the

shelf software, etc.  Labor Intensive tasks include all tasks in which you

charge labor hours to the task/project.  Examples include installation,

software development, training, etc.

Let's begin by entering a standard task called 'Mini-computer'.  use the

Add/Standard-Product menu choice to display the data entry form.

Enter each field (Name, Short Name, Priority, Description, Milestone),

using the prompt window for assistance as needed.  Note that the category

field is automatically set to standard product, and that Easy Project attempts

to automatically come up with a reasonable abbreviation to be used in the

short name field.  When you have entered all fields, press F10.  Easy project

then assumes that we would like to enter another standard product task at

the same level.  Press ESC to terminate data entry.  Your task is now

displayed on the screen.

HINT:  The description field can be used for part numbers,

government contract CDRL numbers, or externally defined WBS or task

numbers.

Now let's try entering another standard product called 'Operating

System'.  Position the WBS cursor on 'Mini-Computer' and select

Add/Standard-Product.  The computer then asks you to show the proper level

for the new task.  The right and left arrow keys move the cursor in the small

display window.  Leaving the cursor in column 1 will place the new task at

the same level as the task 'Mini-computer'.  We want to put our new task at

the same level as 'Mini-computer', so we will leave the cursor to the left.

Press <cr> or F10 when you have selected the proper location for your new

task.  Complete the data entry form, press F10 to accept the entry, and press

ESC to terminate data entry.

Addint labor intensive tasks works exactly the same way except that

you are required to enter the task's category.  Cost reports will show the cost

(actual and percentage) for each category of work.  This information is useful

when checking the validity of cost estimates.  Labor intensive categories are

a bit tricky at first, because they must abide by the following four rules:

1.   At the top of your hierarchy, categories consist of one or more

levels of tasks falling into one of the following categories:

hardware;  software;  training;  installation;  support;

maintenance;  or other.

2.   For all categories exept software, all lower levels are

automatically set to the same category as the parent.

3.   Under a software task, lower level tasks can be any of the

following categories:  system design;  detail design;  code;  unit

testing;  integration;  system test;  or user doc.

4.   Under each of the softwrae specific categories (code, unit

testing, etc.), you may use a free-form name.  For example,

under code you may have tasks with categories of 'Report

modules', 'Data entry modules', 'Inventory modules', etc.

HINT:  The task categories have been defined as shown for a reason.

Many project managers forget to properly plan tasks in one or more of these

areas.  Use the available categories list as a checklist to be sure that you are

not forgetting something.

Enter the following short WBS into the system using Add/Standard-

Product and Add/Labor-intensive.

Project Test                   P    system

Mini-Computer                  S    Std. product

Computer                  S    Std. Product

Disk                      S    Std. Product

Terminals                 S    Std. Product

Operating System          S    Std. Product

Develop Application       L    Software

Design application   L    system design

Code application     L    code

Test application     L    system test

Develope IO card          L    Hardware

Note that, although the system will not prevent you from putting labor

intensive tasks as sub-tasks of standard products (or vice versa), this should

not be done.

HINT:  When defining your WBS, it is normally best to begin by

defining all project tasks at level one first (i.e. start by thinking of the big

picture).  When you are comfortable that all areas have been covered, then

begin adding subtasks at ever increasing levels of detail.

Modify

Selecting Modify allows you to change a task which you have already

entered.  Simply move your WBS cursor to the task you wish to modify and

select Modify from the command line menu.

Delete

You may delete tasks by pressing Delete from the command line

menu, or by pressing the DEL key on your keyboard.  The task under the

WBS cursor is deleted and the WBS is automatically renumbered.  Note that

the system does not automatically delete sub-tasks when you delete a task.

Range

The Range features of Easy Project allow you to perform various

actions on a range (contiguous set) of tasks.  Selecting Range from the

command line menu displays the following sub-menu:

o    Flag

o    Move

o    Copy

o    Delete

o    Insert

o    Extract

o    Shift

o    Unflag

These options perform the following actions:

o    Flag:  Flag is used to designate a range.  Flag is pressed once

to indicate one end point of the range (at the current WBS

cursor location), the WBS cursor is moved to the other end

point, and flag is pressed again.  Note that the current range is

shown in the 'T' column of the WBS screen.  The range remains

flagged until you press Unflag.

o    Move:  To move a range of tasks you should flag the range,

move the WBS cursor to the task directly above the desired new

location, and press Move.

o    Copy:  Copy range works exactly like move range, except the

tasks are copied to the new location.

o    Delete:  The range of tasks is deleted.

o    Insert:  You will be prompted for a file anem (optionally

including a drive and path).  The file must be a task file which

was created using the Range/Extract option (below).  The

system will then attempt to load the file into the WBS directly

under the WBS cursor.

o    Extract:  After entering a file name, the flagged range of tasks

is copied to the named file.

o    Shift:  Shift allows you to change the level of indentation in the

hierarchy for a range of tasks.

o    Unflag:  Clears all range flags.

HINT:  Range/Extract and Range/Insert can be used to move blocks

of tasks from one project to another.  These options may also be used to

build a library of project tasks which can be inserted and modified as

required.

View

Options under View control the way the project information is

displayed on your screen.  Selecting View makes the following sub-menus

available:

o    Increase

o    Decrease

o    All

o    Window

-    Split

-    Clear

-    Jump

When describing these options, the word level will be used to describe

a task's level in the hierarchy.  Tasks are at levels zero (the project top)

through nine (the lowest, most detailed sub-task).

o    Increase:  By default, Easy Project displays your entire task

hierarchy.  This is often inconvenient when attempting to get

an overview.  The current view displayed in the lower right

corner of your screen is the lowest level task which will be

displayed.  The default is 99 (i.e. display all tasks).  Increase is

used to increase the level of detail displayed (after it has been

decreased).  Use decrease to decrease the view all the way

down to 1 to see how this works.

o    Decrease:  This option decreases the level of task detail shown.

Continuing to press decrease will reduce the view to 1.

o    All:  This option sets the display view to 99 (display all).

o    Window:  The WBS screen may be split into two independent

windows.  View/Window/Split splits the screen into two

windows.  View/Window/Jump moves the WBS cursor from

one window to the other.  View/Window/Clear clears the

window and restores the screen to a single display.

HINT:  Using the window feature and move or copy range, you can

jump back and forth in your hierarchy to easily perform cut and paste

operations.

Goto

Goto is used to reposition the WBS cursor directly on a specific task.

Simply enter the sequential number of the task of interest.

Plan/Cost

After you have defined the project tasks using Plan/WBS, you need to

allocate resources (dollars and man-hours) to the project tasks.  This is

accomplished using Plan/Costs.  Select Plan/Cost at this point.

As you can see, the data entry/display screen is very similar to the

Plan/WBS screen.  The informational line on the bottom of the display no

longer displays the maximum number of tasks allowed (you can't enter new

tasks from this screen).  Instead, this line now displays the total project direct

cost, burdened cost, and price.  This is handy when estimating costs to ensure

that your total cost will make sense.

Four new columns have been added to the main display:  Cost; B; M;

and Price.  Cost is your entered direct cost for this particular task.  B is the

burden category, and M is the markup category to be applied to this task.  A

value of 0 for B or M signified no burden/markup.  A value of 1 through 5

will apply the appropriate burden/markup rate as entered in the

Setup/Organization screen.  Price is the final price to the customer after

applying the burden and markup.

The command line menu is also somewhat different, offering these

choices:

o    Modify

o    View

-    Increase

-    Decrease

-    All

-    Window

*     Split

*     Clear

*     Jump

View and Goto work exactly as described for Plan/WBS.  Modify is

used to enter resource estimates for each task in the project hierarchy.  The

specific data entered varies based on the task type ('T' column) for the

current WBS cursor position.  The three general categories are:

o    P:   Project

o    S:   Standard Product

o    L:   Labor Intensive

The following sections of this chapter address each of these three

possibilities individually.

Project

Move your WBS cursor to the top task (pressing HOME will do this)

and press Modify.

Customers typically pay for labor related work using one of the

following four methods:

1.   Payment in full on delivery of the final product.

2.   Monthly payments of cost plus profit during the project (based

on actual expenditures).

3.   Monthly payment of costs during the project, payment of profit

on delivery (common on cost plus fixed fee government

contracts).

4.   Payment of the final price in periodic installments during the

work.

This data entry screen allows you to select which of these methods is

appropriate for your project.  If you select periodic installments, this option

also allows you to enter the number of installments agreed to in the contract

(1 - 9).  This information is used when preparing pro-forma financial

statements and for modeling project financial performance.  Press ESC or

F10 to exit this screen.

Standard Product

Move your WBS cursor to a standard product WBS element and press

Modify.

Let's start by explaining the cost box displayed in the upper left corner

of your screen.

o    Line 1 tells you if the task being modified is a node or not.  A

node simply means that the task has no sub-tasks defined.

o    Line 2 tells you the cost for this task's parent in the hierarchy.

If the selected task is level 1 (i.e. the parent is the project), this

line will tell you that the task is level one.

o    Line 3 tells you the cost for siblings of this task.  This number

can be used with the displayed parent cost when performing top

down costing (or design to cost).  You basically modify the cost

estimate for all siblings until they equal the already estimated

cost for the parent.

o    Line 4 tells you the cost for this task's children.  This number

is used when performing bottom up cost estimating (you

estimate the children first, then set this task equal to the total

cost for the children).

Now let's look at the bottom half of the screen, looking at the fields

in the data entry form.  The following fields are user fields (the others are

display only):

o    Unit Cost:  This is the cost for one of the described items.

o    Quantity:  This is the quantity to be sold.  This field multiplied

by the unit cost (above) determines the net cost.  The quantity

field can only be entered for nodes.

o    B-cat and M-cat:  These fields show the burden and markup

category to be applied to this task.  These fields can be changed

only for level one tasks.  All lower level tasks automatically

have the same burden and markup category as their level one

parent.

HINT:  If you have two markup categories with different profit rates

(7.5% and 10%, for example), you can easily perform what-if planning by

varying the markup rate field for level one tasks.

o    Lease:  This field also applies only to level 1 tasks (sub-tasks

are automatically set accordingly).  An 'n' in this field implies

that the product is sold, a 'y' in this field implies that the

product is leased to the customer.  Leased items are modeled

(financially) using the lease terms defined in

Setup/Organization.

Press ESC or F10 to terminate entry for standard product cost

estimates.

Labor Intensive

Move your WBS cursor to a labor intensive task which is also a node

(no children) and press Modify.

The financial information displayed in the upper left corner of the

screen is identical, but the data entry form now includes a resource matrix.

The fields for cost, B-cat, Burdened cost, M-cat, and price are identical

to those described for a standard product.  As before, the burden and markup

category can only be entered for level one tasks.  The field labeled "P:" is the

penalty factor applied to your cost.  This penalty factor is based on inefficient

scheduling, and is described fully in the Plan/Schedule chapter of this

manual.  The field labeled Crashed Cost is the basic cost times the penalty

factor, and it is this crashed cost which is used when applying markup and

burden rates.  For now, simply note that a value of 1.0 for penalty is no

penalty, so the crashed cost should equal the base cost.

IMPORTANT NOTE:  Before going any further, we will want to have

information entered in Easy Project for at least one employee.  If you have

not completed the Setup/Organization procedure, go back now and enter

data for at least one employee.  Be sure to include the employee's hourly

wage.

The resource matrix is only available for labor intensive nodes (non-

nodes have the array automatically filled in with the sum of their children's

resource requirements).  Use the down arrow key to move your cursor to the

first field in the resource array (#:).  This is where you would enter the

employee number (or labor category number).  Enter a number for which you

have entered some employee data already (probably 1).

You are now asked to enter three manpower estimates (in hours) for

this employee (or labor category) working on this task.  The low estimate

should be a number which you are 95% sure will be the minimum hours

worked.  The expected estimate should be your most likely estimate.  The

high estimate should be a number which you are 95% sure will be the worst

case requirement.  These numbers are used to compute the mean

requirement (and also used for various probabilistic functions in other parts

of the program).

mean = [low + (4 * expect) + high] / 6

You can enter information for up to five different employees for each

task.  As you enter resource information, the field labeled "Expected

Resource Costs" displays the total dollars allocated in the resource array (for

each employee, the mean man-hour estimate times the employee's hourly

wage).  Note that if the resource number entered on the screen is a resource

which does not have a valid hourly wage entered (in Setup/Organization) the

resource cost will be zero.  If the task has a penalty factor attached, the field

for Penalized Costs is equal to the expected Resource Costs times the penalty

factor (this penalty stuff really is cleared up in Plan/Schedule, we promise!).

HINT:  When doing bottom up costing, enter the labor estimates, then

use the Expected Resource Costs to enter a valid cost in the cost field.

When doing top down costing (design to cost), adjust your resource array

until it matches the previously entered cost field.

To save some effort when entering resource estimates, you may use the

following shorthand:

2d = 2 days = 16 hours

2w = 2 weeks = 80 hours

2m = 2 months = 320 hours

In other words, enter an integer followed by the letter d, w, or m and the

system will convert the number to the appropriate number of man-hours.

IMPORTANT NOTE:  When you are done, the cost field for each

task should exactly equal the sum of the cost fields for the task's children.

You should ensure that this is true during your planning process.

Plan/Dependencies

Easy Project handles dependencies by defining predecessor tasks only

(successor links are implied by the predecessor links).  Easy Project allows

you to specify the percent which the predecessor must be complete prior to

beginning the successor.  For example, the detail design stage of software is

normally dependent on the system design state, and we would say that system

design is a predecessor of detail design.  If the system design does not need

to be 100% done before we start detail design, we might say that system

design is a predecessor of detail design, and that system design should be

50% complete prior to starting detail design.

Select the Plan/Dependencies option.  The WBS display window now

displays a new column labeled Dependencies.

For each task, this column will have an X for each predecessor link

defined.  Because you may define up to eight predecessors for each task, this

column may contain up to eight Xs.

The command line menu should look relatively familiar at this point.

The actual menu structure is as follows:

o    Modify

o    Designate

-    Select

-    Add-Link

-    Remove-Link

-    Disconnect

o    View

-    Increase

-    Decrease

-    All

-    Window

*     Split

*     Clear

*     Jump

o    Goto

Modify

Move your cursor to a task and press Modify.  From this screen you

can designate up to eight predecessors to this task using the sequential

number (not charge number) of each predecessor.  The Percent field is your

estimate of the percent the predecessor must be complete prior to this task

starting.  You can also enter the rigidity of the dependency link (1 - 9).

Designate

You may designate most dependency links using Designate, if you

desire.  Move the WBS cursor to the successor task and press Select (the 'T'

column shows the task selected).  You may now move the WBS cursor to

each predecessor and press Add-Link.  If you make a mistake, move the WBS

cursor to the improper predecessor and press Remove-Link.  Moveing the

WBS cursor to a task and pressing Disconnect removes all predecessor links

defined for that task, and searches the WBS hierarchy to remove links

defined by other tasks to the now disconnected task (i.e. disconnects all links

to/from this task).

All links defined using Add-Link assume a rigidity of 9 and a percent

complete required of 100%.  You can then use Modify to change these

numbers, if desired.

Plan/Risk

One vital area of project management which is often ignored (at your

own peril) is risk management.  Easy Project simplified the process of

estimating risk.

Select the Plan/Risk option.  All risk estimates are numbers from 1

to 99, with 1 being extremely low risk and 99 being extremely high risk.  The

columns labeled NR, TR, SR, and OR have the following meanings:

o    NR:  This number defines the network related risk for this task.

o    TR:  This number defined the technical risk for this task.

o    SR:  This number defines the schedule related risk for this task.

o    OR:  This number is the average of the other three, and gives

some indication of the task's overall risk.

Now, move your WBS cursor to any task and press Modify.  We will

describe each field individually.

o    Network LOF:  The network likelihood of failure is an

indication of the likelihood of problems caused by this task's

predecessor tasks not being completed on time.  This number

is automatically calculated based on the number of predecessor

links defined.

o    Network COF:  The network consequence of failure is an

indication of how many other tasks may be adversly affected by

slips in this task.  This number is automatically calculated based

on the number of other tasks which have this tasks as a

predecessor.

o    Network Overall:  This is the average of the Network LOF and

Network COF, and is the number displayed on the main screen

as NR.  This field is automatically calculated.

o    Tech LOF - HM:  This is a user entered field for the technical

likelihood of failure due to hardware maturity.  99 would be

appropriate for development using experimental hardware which

has not been adequately tested.  1 might be appropriate when

using well established hardware you are extremely familiar with.

o    Tech LOF - SM:  This user entered field is similar, but looks

at the likelihood of failure due to softare maturity.  99 would

be appropriate for state of the art development using innovative

techniques, while 1 might be appropriate for routine

modifications to a COBOL program.

o    Tech LOF - HC:  This user entered field measures the

likelihood of failure due to the complexity of the hardware you

must work with.  Large network type applications are probably

a 99, while simple, single user systems might be a 1.

o    Tech LOF - SC:  This user entered field measures the

likelihood of failure due to software complexity.  Large,

complex tasks would clearly be 99.  Small modules with few

outside interactions would be 1.

o    Technical LOF:  This field is automatically computed, and is

the average of the four Tech LOF factors just entered.

o    Technical COF:  This user entered field describes the technical

consequence of failure.  If this task is basically stand-alone and

of relatively low importance, the technical consequence of

failure will be quite low.  If the entire project will not work

unless this task works, the technical consequences of failure for

this module are quite high.

o    Technical Risk (Overall):  This field is automatically computed

and is the average of the Technical LOF and the Technical

COF.  This is the number for TR displayed on the main screen.

o    Cost/Schedule Risk:  This number is automatically computed

based on the duration used for the task.  Tasks which are

scheduled for their optimum duration will have a value of 50

here.  Tasks which are scheduled to take longer than their

optimum duration will have a number lower than 50.  Tasks

which are crashed (scheduled duration shorter than optimum

duration) will have a number over 50.

Plan/Schedule

From the main menu, select Plan/Schedule.  The main window now

displays a Gantt chart used for scheduling.  Let's begin by looking at the

Gantt (bar) chart in some detail.  The Gantt chart is divided into 8 columns.

Each column represents one week, month, or one quarter.  The current scale

is shown in the lower left corner of your screen.  Standard product nodes are

shown on the Gantt chart as an asterick (*) corresponding to the product's

delivery date to the customer.  Labor intensive tasks are shown as a bar.

You may notice that the Gantt bars are not all the same.  Various levels of

sub-tasks are shown by different bar types to differentiate between top level

tasks and their sub-tasks.

You might notice one slightly subtle change in the "T" column of your

WBS.  If a task is scheduled to begin before its predecessor tasks are

sufficiently complete, the L or S label is replaced by a double arrow.

In addition to your normal WBS cursor movement keys, the

Plan/Schedule option allows you to use control right arrow and control left

arrow to scroll the Gantt window in time.  Try this.  Notice that the column

labels at the top of the Gantt window show the month.

With that overview complete, let's look at the menu options available

from Plan/Schedule:

o    Modify

o    Range

o    Shift

o    View

o    Goto

Modify

Modify performs differently for:  Projects (task 0); standard products;

or labor intensive tasks.

Pressing Modify while your WBS cursor is on task 0 lets you enter the

following general schedule information:

o    Start date:  The project's calendar start date is entered here.

All other dates entered are relative to this absolute start date.

This solves the problem of planning a project based on a 1

January start date, actually starting the project on 15 February,

and needing to change the dates for every task in the project.

With Easy Project, you would simply change the project start

date and reprint all reports with the proper dates.  You can use

shift to schedule tasks for specific calendar dates, because the

shift option shows the actual dates scheduled in the upper left

corner of the screen.

o    Working hours/week:  This is obviously normally 40.  Reducing

this number might allow for projects done on a part time or at

low priority (internal projects).  All task durations will

automatically increase in direct proportion to the reduced hours

worked per week.  Increasing the number might allow for high

priority projects in which overtime has been authorized.  All

task durations will automatically decrease in direct proportion

to the reduced hours worked per week.  Changing the working

hours per week does not affect penalty, if applicable (See next

paragraph).

o    Estimate type:  There are two fundamentally different

approaches to estimating software work, and many overruns are

incurred by not recognizing which type you are using.  Fixed

price estimating (f) is simple, and is normally appropriate for

fixed price contracts, design to cost projects, and projects with

ample time for completing the work.  On a fixed price contract,

your cost and man-hour estimates for each task are fixed.

Crashing a project (scheduling the work in a non-optimal

fashion) will reduce the probability of successfully meeting the

schedule (the schedule risk), but will not affect the costs for

individual tasks.

Optimal scheduling is more complex, but also more

realistic for many projects.  This technique says that all cost and

man-hour estimates were made assuming the tasks would be

performed with adequate time.  If the tasks are crashed, the

cost for each task will increase.  Easy Project will automatically

calculate the schedule related cost penalty for crashing tasks if

the Estimate Type field is set to 'o'.  For reasonable schedule

changes, you will notice that the schedule risk does not change,

but the costs go up.  For drastic schedule changes, both the cost

and schedule risk will increase (i.e. no matter how much money

you spend, you can't develop 1 man-year of software in 1 day!)

As an example, assume you plan out a project to develop

a new accounting system.  Your plan shows that the project will

require 18 months to complete.  The customer insists that you

complete the work in 12 months.  You have three choices:

1.    Your best bet is to reduce the scope of work to

a point where 12 months is the optimal delivery

time.  This is not always possible.

2.    If the money available is fixed, you would used

fixed type estimating.  After reducing the

schedule, you could deliver the schedule to the

customer and explain that there is only a 14%

chance of meeting the deadlines.

3.    If sufficient funds are available, you would use

optimal type estimating.  After reducing the

schedule, you could deliver the schedule to the

customer and explain that the schedule changes

have increased the cost from $155,000 to $315,000.

o    Percent Complete:  This is your estimate of the project's current

percent complete.

Pressing Modify while your WBS cursor is on a standard product node

allows you to enter the delivery date in days from project start.  Pressing

Modify while your WBS cursor is on a labor intensive task allows you to enter

the following two fields:

o    Duration:  This is the task duration in calendar days.  Changing

the duration will automatically change the schedule risk.  If the

estimate type is 'o' (optimal) the penalty and net cost will also

automatically change as you modify the duration.  Notice that

setting the duration equal to the optimum duration (displayed)

sets the schedule risk to 50 and the penalty to 1.0 (no penalty).

Changing the duration of a task automatically changes the

duration of the task's children by a proportional amount.

o    Percent Complete:  This is your estimate of the percent this

task is complete.  This number is used when predicting

dollars/man-hours required to complete the work.  Setting this

field to 100 marks a task as complete.

Range

This option works similar to the Range option in Plan/WBS.  Flag is

used to mark the top and bottom of the range (the flagged range is shown in

the "T" column).  Unflag is used to clear the range markers.  Shift allows you

to shift the flagged range on the Gantt chart.  Shifting is accomplished using

the right and left arrow keys (control right and left arrow for faster

movement).  Shifting is terminated by pressing ESC, up arrow, or down

arrow.

Shift

Shift is used to shift individual tasks.  As with shift range, the right and

left arrow keys are used to shift the task (control right and left arrow for

faster movement).

As you shift a labor intensive task, all children of the task are

automatically shifted.  In the upper left corner of the screen, the task start

date, end date, schedule risk, and penalty is displayed.  In the information

line (bottom of display), the total man-power loading for the project is

displayed for each time period displayed on the Gantt chart.  Manpower

loading is shown in man-weeks/months/quarters.  In other words, this is the

total number of people you will need to have working on the project during

this period of time to meet your schedule.  As you shift tasks, dependency

links are automatically checked and a double arrow will be displayed in the

"T" column if the task is scheduled before at least one of its predecessor tasks

is sufficiently complete.

Pressing HOME while shiftint a task allows you to enter the task start

date in terms of the number of days from project start.

Because sub-tasks should be scheduled within the time period

scheduled for their parent task, tasks can not be shifted past the start/end

date of their parent task.  This restriction is also built into the use of the

HOME key (paragraph above).

Shift is terminated by pressing ESC, up arrow, or down arrow.

NOTE:  Shifting task zero shifts the Gantt window.

View

In addition to the normal options available using View, you can select

View/Format to modify the Gantt scale.  The Gantt chart can be scaled so

that each column is one week, one month, or one quarter.

HINT:  Scheduling should normally be accomplished in a top down

fashion.  Set the view to 1 and schedule all level 1 tasks (with the Gantt chart

set to an appropriate scale).  When this top level schedule looks OK, set the

view to 2 and schedule all level 2 tasks (changing the Gantt scale if

appropriate).  Repeat this process until all tasks have been scheduled.

Track

After a project has started, you need to record chanrges (labor and

materials), normally on a weekly basis.  The Track option is used for this.

The Track top level menu looks like this:

o    Timesheets

o    Expenses

o    Report

o    Post

o    Quit

Timesheets is used to enter periodic (normally weekly) employee

timesheets for all projects.  Expenses is used to enter material charges

(invoices) for all projects.  Report is used to print timesheet and expense

related reports.  Post is used to transfer charges directly to appropriate

project tasks.  We will discuss each of these options individually in the

sections that follow.

Timesheets

You will normally enter timesheets weekly (bi-weekly in some

companies).  Before beginning, you will need an appropriate timesheet filled

out for each employee.  For each project task the employee worked on during

the reporting period, the timesheet should specific the project name, the task

charge number, and the hours billed.  Optionally, you may also record the

actual hours worked if you want to track unpaid overtime, etc.

Select Track/Timesheets to display the timesheet data entry form.

This is a matrix type form, where entry number refers to the sequential

timesheet entry number (0 - 499).  If one employee charged to three different

tasks, these charges might be recorded as entry numbers 0, 1, and 2.

Starting with entry number 0, enter the employee number (1 - 249),

the project name, the charge number, the hours worked on that task

(optional), and the hours billed to that task.  The field for project name will

contain the eight character file name in which the project is stored, not the

20 character name entered when you created the project.  When you have

completed all fields on this form, move your cursor to the first field and set

the entry number to 1.  This will allow you to make the second entry.

Continue this process until you have entered all timesheet charges.

Entries can be modified by selecting the appropriate entry number and

modifying the displayed field.

When you are done entering timesheet information, press F10 to save

all entries to disk.  Pressing ESC will exit without saving any timesheet entries

made during this session.

Expenses

Select Track/Expenses to enter expense reports (material charges) into

the system.  Expenses are entered exactly like timesheets, except the entries

are limited to 0 - 99.  The field for dollars charged refers to your cost, i.e. the

amount your supplier invoiced you for the item.

Report

Reports accessed from this menu are expense and timesheet related

and may include information applicable to many projects (i.e. they would

cover all timesheet charges, not just those for a specific project).  Pressing

Timesheet/Report displays the following sub-menu:

o    Timesheets

o    Costs (expenses)

o    Employees

o    Suppliers

Timesheets prints a sorted list of all timesheet entries made since the

last posting (Timesheet/Post).  Entries may be sorted by employee or project.

Costs-(Expenses) prints a sorted list of all expense entries made since the last

posting.  Entries may be sorted by supplier or project.

HINT:  Because these reports sort the actual timesheet/expense file,

these options can be used to re-order your entered data prior to viewing it

using Track/Timesheets or Track/Expenses.

Employees prints a list of all valid employee numbers, names, and

hourly rates.  Suppliers prints a list of all valid supplier numbers and names.

All of these reports are printed to the screen by default.  To change

the print destination, you must use the Report/Options/Destination capability

from the main menu.  This option allows you to print reports to the screen,

the printer, or to a disk file.  (See the Report chapter for details of using this

capability).

Reports printed from this menu can not be queued (See the Report

chapter for an explanation of queueing reports).

HINT:  Use these reports to double check all charges prior to posting.

Post

After all expenses and timesheets have been entered, printed, and

checked for accuracy, they are posted to the appropriate project files on your

disk.  The project files should be on the default drive (and directory), and

should match the project name field in the individual timesheet/expense

entries.  Selecting Track/Post will post all entries automatically.

If any invalid entries are detected during the posting (project name

does not match a valid file or charge number does not match a valid task in

the project), the entry is left in the timesheet/expense file.  All valid entries

are cleared from the file after posting to the projects.  If invalid entries were

detected, you should print out the appropriate file, correct the problems, and

perform the posting operation again to post the remaining entries.

HINT:  Errors in timesheet or expense entries which are detected

prior to posting can be corrected by changing the appropriate entry.  After

posting, errors must be correcting by making an off-setting entry (negative

hours or dollars charged).

File

The File option is used to store/retrieve files to and from disk.  When

entering file names, it is permissible to specify a drive and/or path name if

you are not using the default drive/directory for storage.  Pressing File

displays the following sub-menu:

o    Save

o    Recall

o    Purge

o    Directory

o    Quit

Save is used to save the current project to disk.  Recall is used to

recall a project form disk.  Purge is used to delete a project from disk.

Directory is used to display a directory of available projects.

Report

The Report option prints reports relating to a specific project.

Pressing Report displays the following sub-menu:

o    WBS

o    Cost

o    Dependencies

o    Risk

o    Schedule

o    Evaluate

o    Options

o    Quit

We will begin by discussing Options because this choice affects all

reports.  We will then talk about each available report individually.

Options

Selecting Report/Options offers the following sub-menus:

o    Print-Queue

-    Activate

-    Print

-    Deactivate

o    Destination

-    Screen

-    Printer

-    Disk

Most project managers find that they need to print a long series of

reports on a regular basis.  Print-Queue is used to simplify this process.

When you select Activate, then select various reports to be printed, Easy

Project stores the list of reports requested but does not actually print any

reports.  Selecting Print causes all of the the reports in the print queue to be

output in the order you selected them.  Selecting Deactivate causes reports

to be printed immediately as they are selected.  Note that Deactivate does

not clear the print-queue (Easy Project still remembers the reports you want

to output).

HINT:  If you output the same list of reports every week (or month),

you can place these reports in the print-queue one time, then deactivate the

print-queue.  Every time you want the series of reports output, simply select

Report/Options/Print-queue/Print.

Destination is used to select the current report destination (including

those printed from the print-queue).  Reports may be directed to the screen,

the printer, or to a disk file called REPORT.ASC.  The default is the screen.

Reports sent to report.asc are appended to the end of the file.  When you

select Report/Options/Destination/Disk you will be asked if you want the

existing report.asc file cleared.

All reports will prompt you for the project name (i.e. the name of the

project you want the report for).  The project name is the name of the

project file, including the drive and path if necessary.

Note that printing reports causes the project currently in memory to

be over-written.  For all operations in which the current project will be over-

written or deleted, Easy Project determines if you have made changes since

the last save.  If so, you are asked if you would like the current project saved

prior to continuing.

WBS

Two WBS related reports are available, Hierarchy and Detail.

Hierarchy displays the task hierarchy for the designated project.  Detail

displays each task's WBS number, Name, Category, Priority, Milestone status,

and charge number.

Cost

Three cost (resource) related reports are available, Dollars, Hours, and

Loading.

o    Dollars:  This report displays detailed financial information, in

terms of dollars, for each task in the project hierarchy.  For

each task, the report displays the task name, cost, penalized

cost, burdened cost, price, WBS number, amount charged (and

posted) to date, dollars available, and predicted dollars to

complete.  Predicted dollars to complete is only displayed for

labor intensive tasks for which you have entered a percent

complete (see Plan/Schedule).

This report also includes two summary pages.  One page

displays summary information for each of the primary project

categories (hardware, installation, trainging, support,

maintenance, other, and software).  The second summary screen

displays summary information for each of the software sub-

categories (system design, detail design, code, unit testing,

integration, system test, and user documentation).  The

displayed percentages can be used to determine if your project

plan includes sufficient funds for all required project activities.

o    Hours:  This report displays detailed financial information in

terms of man-hours for all labor intensive tasks.  For each task,

the report displays the total hours planned, hours worked, hours

billed, and hours remaining.  In addition, nodes will include the

specific employee man-hour allocations.

o    Loading:  This report displays the month by month man-power

loading for each employee (or employee category) working on

the project.  Each line of output shows the project year number

followed by twelve numbers representing the monthly loading

for that year.  Numbers shown are in man-months.

Dependencies

The Dependency report shows all dependency links defined, including

the predecessor task number, the rigidity, and the percent complete required.

Risk

The Risk report shows the detail risk factors for each project task.

These factors are Network Likelihood of Failure, Network Consequence of

Failure, Overall Network Risk, Technical Likelihood of Failure, Technical

Risk, Cost/Schedule Risk, and Total Risk.

Schedule

Two Schedule reports are available, Task and Gantt.  Task shows you

the start date, end date and duration for each task in your project hierarchy.

Gantt displays the project Gantt chart in the same format used by

Plan/Schedule.  Note that the scale (weeks, months, or quarters) and the time

frame displayed in the Gantt window are set within Plan/Schedule prior to

saving the project.

Evaluate

Three Evaluate reports are available, ROI/ATO, Balance-Sheet, and

Income.  ROI/ATO calculates and displays the monthly Net Income Before

Taxes (NIBT), average assets, monthly Return on Investment (ROI), and

monthly Asset Turnover (ATO) throughout the project life.  Balance-Sheet

calculates and displays the monthly cash balance, accounts receivable balance,

inventory balance, cumulative depreciation on leasehold inventory, and

accounts payable balance.  Negative numbers for cash indicate project

financing requirements (internal or through borrowing).  Income calculates

and displays the monthly sales, cost of sales, depreciation expense, and NIBT

throughout the project life.

Reference

Activate

Report/Options/Print-Queue/Activate.  All report commands are

queued for later execution.  The user is prompted if the existing report queue

should be cleared when this option is selected.

Add

Plan/WBS/Add.  Add a new task to the project hierarchy.  Tasks can

be either standard product tasks or labor intensive tasks.

Add Link

Plan/Dependencies/Designate/Add-Link.  Add a new dependency link

from the previously selected task to the current task.  The current task

becomes a predecessor of the previously selected task.  Links are added with

a rigidity of 9 and a required percent complete of 100, although these may

be changed using modify.  The screen will display an X in the dependency

column for each link added.

Addr

Organization address field.  Accessed from Setup/Organization.  Free

form field for company address printed at the top of all reports.

All

Set current view to display all levels of hierarchy.  Shown as view of

99 on hierarchyical displays.

Arrow Keys

Right and left arrow keys select the current default menu choice from

command line menus, or move the cursor during screen oriented data entry.

Up and down arrows move your WBS cursor on WBS hierarchy displays, or

advance to the next/previous field during screen oriented data entry.  Control

right and left arrow keys scroll the Gantt window on the Plan/Schedule

screen.

Average AP Delay

Average accounts payable delay.  The average number of months you

expect to delay paying your bills after delivery of a component to you.

Average AR Delay

Average accounts receivable delay.  The average number of months

you expect your customer to delay paying your invoices after completion of

the work.  This number should include any required acceptance periods.

B-Cat

Burden category.  Burden category 0 is always 1.0 or no burden

applied.  Burden categories 1 through 5 are set by the user to yoru companies

burden rates from the Setup/Organization data entry screen.

Backspace

Works like a correcting typewriter backspace during screen oriented

data entry.  Fills the right most element of the current field with a character

which is used to show a blank location.

Back tab

Shifted TAB.  During screen oriented data entry, back tab works the

same as up arrow (goto previous field).

Balance Sheet

Report/Evaluate/Balance-Sheet.  Print pro-forma (projected) balance

sheets for the desired project from project start until project completion.

Basic Cost

Entered from Plan/Cost/Modify and displayed on several forms.  This

is your direct cost for this item prior to applying any burden or profit.

Burden Rate

Your cost for all items is increased by an overhead charge called

burden rate.  This includes all indirect costs except profit (R&D costs,

handling costs, General and Administrative, overhead, etc.)  Easy Project

allows you to set up to five different burden rates/categories in

Setup/Organization.  A burden rate of 1.0 would be no burden at all.

Burdened Cost

An item's basic cost times the appropriate burden rate.  Computed

automatically by Easy Project.

Carriage Return

Used to check and accept the current field during screen oriented data

entry, and to accept the highlighted item from the command line menu.

Category

Task category, entered from the Plan/WBS/Add or Plan/WBS/Modify

menu.  Automatically set for standard product tasks.  For labor intensive

tasks, category is used to ensure that appropriate funds are allocated to each

task required during development.

Charge Number

A unique number assigned to each project task entered into Easy

Project.  This number is used to uniquely identify tasks to Easy Project when

entering dollars and hours chargted.  This number will normally not be the

same as your company designated charge number for accounting purposes.

Children Cost

The total cost for all children of the current task in the WBS

hierarchy.

Clear

Plan/*/View/Window/Clear.  Accessed from each of the plan menus.

Closes one WBS window, leaving a single WBS on the display.

Control Page Down

From any of the Plan screens, moves the WBS cursor down to the next

task at the same level in the hierarchy (skipping lower level tasks).

Copy

Plan/WBS/Range/Copy.  After marking a range of tasks and moving

the WBS cursor to the desired location, pressing copy will copy the marked

range to the point just below the WBS cursor.

Cost

Plan/Costs.  Used to enter cost and resource data for WBS elements.

Track/Costs.  Used to enter dollars charged to a projects tasks.

Report/Cost.  Used to print dollars, hours, and loading estimates for

the project, including predicted costs to complete each task.

The cost field displayed during screen oriented data entry is the item's

basic cost times the quantity.

Crashed Cost

For labor intensive items developed faster than their optimum

development time, the crashed cost is the basic cost times the Easy Project

calculated penalty factor.  The difference between the basic cost and the

crashed cost is the efficiency penalty you incur by rushing development.  This

number will be 1.0 (no penalty) if the estimate type variable is set to "f"

(fixed).

d

When entering hour estimates on the resource matrix of

Plan/Costs/Modify, you may enter a number followed immediately by a "d"

(days).  The system will convert the number from days to hours.

Date

Easy Project uses the system date extensively, so it is important that

you set the system date prior to running Easy Project.  This can be

accomplished automatically when you boot if your have a batter powered

clock (see the instruction manual with your add-in card), or manually using

the DOS date command.

Deactivate

Report/Options/Print-Queue/Deactivate.  Turn off the print queue,

sending all reports to the printer as they are requested.  Reports currently in

the queue are retained and can be printed later using the Print option.

Decrease

Plan/*/View/Decrease.  Decrease the current view by 1, down to a

minimum of 1.  The current view is the highest level in the WBS hierarchy

which Easy Project will display.

Delete

Plan/WBS/Delete.  Delete the current WBS task.  The WBS hierarchy

is automatically renumbered.

Plan/WBS/Range/Delete.  Delete the flagged range.  You are

prompted to confirm the deletion.  The WBS hierarchy is automatically

renumbered.

Delete Key (DEL)

From the Plan/WBS display, the delete key works like the

Plan/WBS/Delete option and deletes the current task.

Delivery Date

The delivery date for a standard product component, expressed in days

from project start.  The shift option can be used to see the actual calendar

delivery date, if desired.

Dependencies

Plan/Dependencies.  Define task dependencies.

Description

Task description.  Often used to store part numbers, externally defined

WBS numbers, and government contract CDRL numbers.

Destination

Report/Options/Destination.  Used to determine if reports are output

to the screen, the printer, or to a disk file.

Detail

Report/WBS/Detail.  Print a detailed listing of all tasks in the project

plan.

Directory

File/Directory.  Print a listing of all Easy Project project files on the

designated device.

Disconnect

Plan/Dependencies/Designate/Disconnect.  Disconnects the current

WBS task from the dependency network.  All defined predecessors are

cleared, and all tasks which reference this task as a predecessor are modified

to not reference this task.

Discount Rate

Your companies discount rate.  May be used to calculate discounted

cash flow, discounted ROI, etc.  Entered from Setup/Organization.

Disk

Report/Setup/Destination/Disk.  Output all reports to the disk file

report.asc.  New reports are appended to the end of the file.  The user is

asked if the existing file should be cleared when this option is selected.

Display

Setup/Display.  Used to enter display colors used by Easy Project

when running on color systems (Easy Project always uses black and white

colors when using a monochrome text card).

Dollars

Report/WBS/Cost/Dollars.  Print a report showing costs to date and

predicted costs to completion in terms of dollars.

Dollars Charged

Entered on the Track/Expenses data entry screen.  The dollars

charged to a designated project and task.

Down Arrow

See Arrow Keys

Duration

Entered on Plan/Schedule data entry screens.  Task duration in terms

of calendar days.

Employee

Track/timesheet/Employee.  Print a summary of all timesheet entries

entered but not posted, sorted by employee.

Track/Report/Employees.  Print a list of all employees entered into

Easy Project.

Employee #:  Employee number (1 - 250) used to index into Easy

Project employee file from Setup/Organization.  Note that some employees

may actually be classes of employees (e.g. Secretary, Programmer).

Employee Cost:  Hourly cost (or average hourly cost for employee

classes).  Entered in dollars and cents from Setup/Organization.

Employee Name:  Name of employee or employee class.  Entered

from Setup/Organization.

END Key

Move cursor to last task in WBS hierarchy, or move cursor to last valid

field from a data entry screen.

End Date:

Task end date in terms of days from project start.  Will equal start

date plus task duration.

Enter Key

See Carriage Return.

Entry Number

A sequential index number used from the Track/Timesheets and

Track/Expenses screens.

ESC (Escape) Key

Used to abort a function.  Aborts a data entry screen without making

any changes permanent.  Aborts a menu level and displays the previous

command line menu (works like Quit in this respect).

Estimate Type

Entered by modifying task one (the project) from Plan/Schedule.  Can

be "f" for fixed or "o" for optimal.  If optimal, allows Easy Project to increase

task costs if development is attempted in less than the optimal time for the

estimated labor.  If fixed, cost estimates will not change but schedule risk will

increase significantly faster as a schedule is crashed.

Evaluate

Report/Evaluate.  Used to access reports which predict and evaluate

a projects financial performance.

Expected Resource Costs

Computed by Easy Project and displayed on the data entry screen for

Plan/Costs/Modify.  Equal to the sum of the mean labor estimates (hours)

times the hourly wage for the designated employee number(s).

Expenses

Track/Expenses.  Used to enter non-labor project expenses.  Entries

are entered into project files using the Post command.

Extract

Plan/WBS/Range/Extract.  Write the marked range of tasks to a disk

file.  The tasks in the file can be inserted into this project or another project

using the Plan/WBS/Range/Insert option.

F10

Special Function Key 10.  Used to accept a data entry screen.

File

File.  Used to save, retrieve, and purge projects to/from disk.

Flag

Plan/*/Range/Flag.  Used to designate a range.  Pressing flag once

marks one end of the range.  Pressing flag a second time marks the other end

of the range.  The flagged range is shown in the "T" (type) column on the

WBS display.  The range remains flagged until unflagged with the Unflag

option.

Gantt

Report/Schedule/Gantt.  Print the project's current Gantt chart.  The

scale used (weeks, months, or quarters) and the gantt window starting and

ending date are those used from Plan/Schedule.

Goto

Plan/*/Goto.  Goto a specific task number.  The display is recentered

with the designated task at the top.

Hierarchy

Report/WBS/Hierarchy.  Print a hierarchy chart for a project.

HOME Key

From a data entry screen, move the cursor to the first valid field.

From a WBS hierarchical screen, move the WBS cursor to the first task.

Hours

Report/Cost/Hours.  For a given project, print the hours expended to

date for each task.

Hours Billed

Entered from Track/Timesheets.  The number of labor hours charged

to a specific task.

Hours Worked

Entered from Track/Timesheets.  The number of labor hours worked

on a specific task.  May differ from hours billed because of unpaid overtime,

etc.

Income

Report/Evaluate/Income.  Print pro-forma (projected) income

statements for a project from start through finish.k

Increase

Plan/*/View/Increase.  Increase the view by one.  View can be 1 - 9

or 99 (all).  The current view is the maximu hierarchical level which will be

displayed.

Insert

Insert Key:  From Plan/WBS works lie Plan/WBS/Add/Labor-

Intensive.

Plan/WBS/Range/Insert.  Inserts a previously extracted disk file into

the WBS starting at the location immediately below the WBS cursor.

Installments

Entered by modifying task zero from Plan/Costs WBS hierarchy.

Applies only to payment type 4, periodic installments.  Tells Easy Project the

number of installments made for each payment.

Jump

Plan/*/View/Window/Jump.  After the WBS is split into two

windows, Jump is used to move the WBS cursor from one window to the

other.

Labor Intensive

Tasks in Easy Project are one of three types:  Project (task zero);

Standard Product;  or Labor Intensive.  Standard Product tasks are

deliverables which do not require any chargeable labor, and normally consist

of hardware, pre-packaged software, etc.  Labor intensive tasks require

chargeable labor and includes software, training, etc.

Lease

Level one standard product tasks can be sold to the customer (lease

= n) or leased to the customer (lease = y).  The entry is made for level one

standard product tasks from the Plan/Costs/Modify data entry screen.

Lease Depreciation

The monthly depreciation applied to leasehold inventory.  Entered

from the Setup/Organization data entry screen.

Lease Month

The month for which you plan to enter the leasehold depreciation or

payment.  A number from 1 through 120 (ten year lease).  Entered from

Setup/Organization.

Lease Payment

The monthly payment invoiced to the customer for standard products

leased.  Entered from the Setup/Organization data entry screen.

Left Arrow

See Arrow Keys

Level

Task hierarchical level.  Task zero (project) is level zero.  All other

tasks are levels one through nine.  Tasks at higher level numbers are subtasks

of tasks with lower level numbers (e.g. level 2 tasks are subtasks of level 1

tasks).

Loading

Report/Cost/Loading.  Print report showing resource loading during

project.

m

When entering resource estimates, user may enter a number followed

immediately by an "m" (months).  Easy Project will convert the entered

number from months to hours automatically.

M-Cat

Markup category.  Similar to B-Cat.  Designates a task's markup

category.  0 implies no markup (profit).  1 - 5 applies a markup rate as

defined in Setup/Organization.

Manager

Project manager.  Entered from Plan/WBS/Modify for task zero.

Markup Rate

Profit rate for a given markup category (1 - 5).  Entered from

Setup/Organization.  Similar to Burden Rate.

Milestone

Entered when entering or modifying  tasks from Plan/WBS.  Tells if

entered task is a milestone task in the project.

Modify

Plan/*/Modify.  Modify task, cost, risk, etc. for task highlighted in

WBS hierarchy.

Monochrome

When using Easy Project with a color display card (EGA, CGA, or

VGTA) and a monochrome monitor, you should use the DOS mode

command to set the card's mode to black and white.  Alternatively, you may

use the Easy Project Setup/Display command to modify the display colors to

colors which are easier to see on a monochrome nonitor.

Move

Plan/WBS/Range/Move.  Move the flagged range of tasks to the

location just under the WBS cursor.

Name

Name of project or task.

Network

COF (Consequences of Failure).  Impact on project from failure to

complete this task on time.  Number between 1 (minimal) and 99 (significant)

automnatically set by Easy Project based on defined dependencies.

LOF (likelihood of Failure).  Same as COF above, but deals with

probability of not completing this task on time because of network related

problems (predecessors not complete on time).

Risk.  Overall network risk.  Average of COF and LOF.

Node

Task with no children.

NR

Network Risk.

Optimum Constant

Two constants used when determining the optimum task duration

based on man-hours of labor required.  Modified from Setup/Organization.

Optimum Duration

The optimum duration, in calendar days, for a given task based on the

man-hours of labor involved.

Options

Report/Options.  Used to control the print queue and print

destinations.

OR

See Overall Risk

Organization

Setup/Organization.  Used to initialize company wide variables which

apply to all projects.

Overall Risk

Average of Network Risk, Technical Risk, and Schedule Risk.

Page Down

Move down one screen page in the WBS hierarchy.

Page Up

Move up one screen page in the WBS hierarchy.

Parent Cost

Cost for this task's parent.  Applies to tasks level 2 and below only.

Payment Type

Set by modifying task zero with Plan/Cost/Modify.  Can be one of the

following:  1.  Invoice on delivery;  2.  Invoice Monthly during work;  3.

Invoice costs monthly during work, invoice for fee (profit) on delivery;  or 4.

Periodic installments.

Penalized Costs

Costs after application of the penalty factor.  The penalty factor is

calculated by Easy Project if the estimate type is 'o', and is a penalty for

trying to perform the work in less than the optimal number of calendar days.

Penalty Constant

Used when calculating the penalty factor for tasks developed in less

than the optimal number of calendar days.  Set in Setup/Organization.

Penalty Factor

A penalty applied to task costs which are crashed.  A penalty factor

of 1.0 is no penalty.

Percent Complete

Your estimate of what percent complete this task is.  A number

between 0 and 100, with 100 signifying a completed task.  Used to mark tasks

as complete and by Easy Project to calculate estimated dollars required to

complete the work.

Plan

Plan menu option, used to define a project.

Post

Track/Post.  Used to enter timesheet and expense data into project

files.  Successful entries are deleted from the Easy Project timesheet and

expense files.  Invalid entries must be corrected and the Post operation

performed again.  Timesheet or expense errors discovered prior to executing

Post can be corrected by modifying the timesheet/expense entry.  Errors

discovered after executing Post must be corrected by entering an offsetting

entry.

Predecessor Tasks

A task which must be complete (at least partially) prior to this task

starting.  Entered from Plan/Dependencies.

Price

Your price to the customer for an item.  Equals your basic cost times

the quantity times the burden rate times the markup rate times the penalty

factor.

Print

Report/Options/Print-Queue/Print.  Tells Easy Project to print all

reports in the print queue.  The queue is not cleared by the print option, so

the same series of reports can be printed on a regular basis.

Print Queue

A list of reports ready to be printed by Easy Project.

Printer

Easy Project can print reports to the screen, the printer, or the disk

(set by Report/Options/Destination).  The printer will be the printer set in

Setup/Organization.  If you are using LPT2: or COM2: you must use the

DOS mode command to redirect output from LPT1: to the apropriate port.

The printer must support the IBM enhanced character set.

Priority

Priority for a given task.  A number from 1 to 99 with 99 being the

highest priority.  Set within Plan/WBS/Modify and Plan/WBS/Add.

Project

The project name and related information.  The project information

is stored in task zero of the WBS hierarchy.  When entering the project name

for timesheet and expense charges, the eight character (maximum) project file

name must be used.

Purge

File/Purge.  Used to delete a project form the disk.

Quantity

For standard product tasks, the quantity to be delivered.  Applies to

nodes only.  Entered from Plan/Costs/Add or Plan/Costs/Modify.

Range

Plan/*/Range.  Used to designate and manipulate a range of WBS

elements.

Recall

File/Recall.  Retrieve an Easy Project file from disk.

Remove-Link

Plan/Dependencies/Designate/Remove-Line.  Remove a dependency

link from the previously selected task to the current WBS task.

Report

Print Easy Project reports.

Reproduce

Inactive for fully functioning versions of Easy Project.

Resource

Entered from Plan/Costs data entry screen for labor intensive nodes

only.

#:  Employee number as defined in Setup/Organization.

Expected estimate:  The most likely number of man-hours required to

complete the task.

High estimate:  Your worst case estimate (95%) of the number of

man-hours required to complete the task.

Low estimate:  Your best case estimate (95%) of the number of man-

hours required to complete the task.

Return

See Carriage Return.

Right Arrow

See Arrow Keys.

Rigidity

The rigitidy of a dependency link.  A number from 1 (slight

preference) to 9 (rigid requirement).  Entered from

Plan/Dependencies/Modify.

Risk

Report/Risk.  Report showing risk factors for each task.

Also, see individual types of risk (network, technical, schedule, overall).

ROI/ATO

Return on Investment/Asset Turnover.  Report printed via

Report/Evaluate/ROI-ATO which shows the predicted return on investment

and asset turnover for the project.

Save

File/Save.  Save the current project to disk.

Scale

Displayed on the bottom of the Plan/Schedule WBS hierarchy.  Shows

the scale of the Gantt window (weeks, months, or quarters).

Schedule

Plan/Schedule.  Used to enter start and stop dates and calendar

durations for tasks.

Schedule Risk

The amount of schedule risk, with 1 being low risk (high probability

of on time completion) and 99 being high risk (low probability of on time

completion).  Automatically calculated by Easy Project based on man-power

requirements and calendar durations.

Screen

Report/Options/Destination/Screen.  Print all Easy Project reports to

the screen.

Select

Plan/Dependencies/Designate/Select.  Designate a task of interest.

Add-link is then used to define predecessor tasks.

Setup

Setup.  Setup Easy Project system wide variables.

Shift

Plan/WBS/Range/Shift.  Shift the flagged range of tasks to a different

hierarchical level.

Plan/Schedule/Shift.  Shift the highlighted task (and its children) on

the Gantt chart.

Plan/Schedule/Range/Shift.  Shift the flagged range of tasks on the

Gantt chart.

Short Name

An abbreviated name for the task.

Sibling Cost

The total cost for this task and all of its siblings (i.e. the total cost for

all children of this task's parent).

Sname

See short name.

Space Bar

On command line menu, advances choice.  From data entry screen,

enters a space character.

Split

Plan/*/View/Window/Split.  Split the WBS hierarchy into two

windows.

SR

See Schedule Risk

Standard Product

See Labor Intensive

Start Date

Project start date in MM/DD/YY form, or task start date in calendar

days after project start date.

Successor Tasks

All tasks which have this task as a predecessor.  Successor tasks are

not directly entered in Easy Project (i.e. they are implied by designating

predecessor links).

Supplier

A company which supplies items charged to a project.  Entered in

Setup/Organization.

Track/Report/Costs/Supplier.  Print all expenses entered into Easy

Project but not yet posted, sorted by supplier.

Track/Report/Suppliers.  Print a list of all suppliers entered into Easy

Project.

Supplier Name:  The name of the supplier.

Supplier Number:  A sequential number for the supplier (1 - 99).

System Printer

Easy Project printer address, set in Setup/Organization.  See also

printer.

Tab

Advances one field during screen oriented data entry.

Task

Report/Schedule/Task.  Print a detailed report showing the scheduled

start and end date for all tasks.

Task Name

Name of task in Easy Project.

Technical Risk

Technical risk for a given task.  Entered in Plan/Risk/Modify.

Timesheets

Track/Timesheets.  Enter Employee Timesheets.

TR

See Technical Risk.

Track

Track.  Project tracking features of Easy Project.

Type

WBS Task type.  Can be P (project, task zero only), L (labor intensive

task), or S (standard product task).

Unflag

Plan/*/Range/Unflag.  Unflag a range.

Unit Cost

Direct cost for one item.

Up Arrow

See Arrow Keys.

Version

Setup/Version.  Print current Easy Project version number and address

to send suggestions.

View

Plan/*/View.  Change current display view.  The view is the lowest

hierarchical level (highest level number) task which will be displayed.  Ranges

from 1 (display little detail) to 9 (display much detail) and 99 (display all

detail).

w

When entering resource man-hour estimates, user may enter a number

followed immediately by a "w" (weeks) and the system will convert the

number from weeks to hours.

WBS

Easy Project calculated hierarchical position.  May not match

externally set WBS numbers.

Window

Plan/*/View/Window.  Split WBS into two windows.

Work Hours Per Week

Number of hours worked (per employee) on this project per week.

Normally 40.  Would be higher if overtime was authorized.  Would be lower

if employees performed work part time.  When changed, automatically sets

all task durations to optimum duration for new work schedule.