MainLine

Project Management Software

Revision 2.0

By

Minuteman Systems

P.O. Box 152

Belmont MA  02178

Preface

Copyright Information

Copyright 1992, 1993, 1994 by Minuteman Systems

The software and the disks on which it is contained are

licensed to you, for your own use. This is copyrighted

software. You are not obtaining title to the software or any

copyright rights. You may not sublicense, rent, lease,

convey, modify, translate, convert to any other programming

language, decompile, or disassemble the software for any

purpose.

You may make as many copies of this software as you need for

backup purposes. You may use this software on more than one

computer, provided there is no chance it will be used

simultaneously on more than one computer.

Registration Information

This program is supplied as Shareware. This means that you

may evaluate the program for free, but are required to pay a

registration fee if you keep it and use it.

Note that any fee paid to a Shareware distribution company

or similar supplier does not replace, nor contribute

towards, the registration fee.

If you are satisfied with the program and wish to use it,

you may register it by filling out a hardcopy of the

included file ORDER.TXT. Send it with a check or money order

for $29.95 to

Minuteman Systems, PO Box 152, Belmont, Massachusetts,

02178. As a registered user, you will receive

o  A printed, bound User's Manual.

o  Free updates for one year.

o  Telephone service.

o  A personalized diskette with your name and a serial

number. Also, the registration screen usually presented

when exiting the program will be disabled.

Incentive Plan - Once you have registered, have

acquaintances list your name as a reference when they

register. You will receive a $5.00 rebate.

Notice

This software is supplied as-is. There are no warranties,

expressed or implied.

Minuteman Systems disclaims all warranties relating to this

software, whether expressed or implied, including but not

limited to any implied warranties of merchantability and

fitness for a particular purpose, and all such warranties

are expressly and specifically disclaimed. Neither Minuteman

Systems nor anyone else who has been involved in the

creation, production, or delivery of this software shall be

liable for any indirect, consequential, or incidental

damages arising out of the use or inability to use such

software even if Minuteman Systems has been advised of the

possibility of such damages or claims. In no event shall

Minuteman Systems' liability for any damage ever exceed the

price paid for the license to use the software, regardless

of the form of claim. The person using the software bears

all risk as to the quality and performance of the software.

Some states do not allow the exclusion of the limit of

liability for consequential or incidental damages, so the

above limitation may not apply to you.

This agreement shall be governed by the laws of the

Commonwealth of Massachusetts and shall inure to the benefit

of Minuteman Systems and any successors, administrators,

heirs and assigns. Any action or proceeding brought by

either party against the other shall be brought only in a

STATE or FEDERAL COURT of competent jurisdiction located in

Middlesex County, Massachusetts. The parties hereby consent

to in personam jurisdiction of said courts.

Table of Contents

Preface                                                  i

1 Introduction                                           1

1.1  How This Manual Is Organized                   1

2  Installation                                          2

2.1  System Considerations                          2

Installation Procedure                              3

3  Trial Run - 1st Pass                                  4

3.1  The Initial Screen                             4

3.2  Moving Around - Key Commands                   6

3.3  The Command Menu                               7

3.4  Quick Entry - Adding a Task                    8

3.5  Storing a Project                              10

3.6  Printing Reports                               10

3.7  Exiting                                        10

3.8  Examining The Reports                          11

4  Trial Run - 2nd Pass                                  14

4.1  Reading In A Project                           14

4.2  Editing an Existing Task                       14

4.3  Inserting, Deleting, Moving Lines              15

4.4  Deleting A Task                                18

4.5  Adding Descriptions to Groups of Tasks         19

4.6  Adding A Date and Labels to The Display        19

4.7  Multiple Editing Views                         22

4.8  Locating Tasks - The "Search" Function         22

4.9  The Wait Function                              23

4.10  Changing Program Configuration                24

5  Advanced Topics                                       28

5.1  System Capabilities                            28

5.2  Following The Critical Path                    28

5.3  The Journal File - Recovering Damaged Project

Files                                               28

5.4  Attaching Fixed Dates to Tasks or  Milestones  29

5.5  Project Rollups                                29

5.6  Renumbering Tasks and Milestones               31

5.7  Copying A Group of Projects                    31

5.8  Importing Projects                             32

6  Command Listing                                       33

6.1  Filing                                         33

6.2  Edit                                           33

6.3  Search                                         33

6.4  Display                                        34

6.5  Print                                          34

APPENDIX  A - QUICK-START INFORMATION                    1

A.1  Starting Up                                    1

A.2  Moving Around The Screen                       1

A.3  Calling Up Commands                            1

A.4  Basics of Editing and Generating Reports       2

A.5  Notes on Dates and Calculations                2

APPENDIX  B - SELECTING OUTPUT FORMATS                   1

APPENDIX  C - SERVICE                                    1

List Of Figures

Figure 1: Blank Project                             5

Figure 2: 1 Task Added                              9

Figure 3: DEMO.DAT                                  12

Figure 4: DEMO.RPT                                  13

Figure 5: Tasks Added                               16

Figure 6: Moved Lines                               17

Figure 7: Adding Comments                           20

Figure 8: Date and Label Fields                     21

Figure 9: Using The Task Wait Function              23

Figure 10: Display Options Configuration Menu       25

Figure 11: Using Rollup Tasks                       30

1

1 Introduction

The principal job of the MainLine Project Management Program

is to develop a schedule in a clear and understandable

format, for the purposes of

1. Identifying the parts of the project and their

interdependencies.

2. Allowing easy changes to the schedule for "what if"

purposes.

3. Providing compact reports suitable for presentations, and

compatible with electronic mail systems for distribution

to those working on the project.

1.1  How This Manual Is Organized

Section 2 describes the method for installing the program on

the machine. It also discusses the requirements of the

computer this program is to run on.

Section 3 and Section 4 illustrate how to use MainLine by

means of a series of examples.

Section 3 goes over the basics - turning on the program,

creating a simple project, and generating some reports.

Section 4 demonstrates with further examples how to edit a

project and manipulate the display of a project on the

screen.

Section 5 describes some advanced features.

Section 6 lists all the individual commands available and

describes each briefly.

Appendix A includes "quick-start" information if you wish to

get up-and-running prior to having read this whole manual.

Appendix B gives further information on formatting the

schedule output for printing and electronic mailing.

2

2  Installation

To install and use this program, all that is required is

familiarity with the basics of DOS operation. If you aren't

experienced with creating directories and copying files,

consult the DOS documentation with your system.

2.1  System Considerations

This program is intended to be run on IBM-style personal

computers and exact compatibles. The program has been

successfully tested and used on numerous machines.

This is a DOS program. It can also be called from Windows.

Speed of the program will vary depending on the model of PC

used. The program has been tested on 20MHz 386-SX machines

and found to have very usable speed. It has been tested on

older machines including 8 MHz "XT" machines - while the

performance is slower, it is still quite usable.

Whatever machine used should have at least 640K of RAM

memory available.

Note - The presence on a system of Terminate-And-Stay-

Resident programs (TSRs), memory managers, or Local Area

Network (LAN) software may interfere with the operation of

this program. "Interference" usually  means that the program

cannot load and execute. However, in borderline cases there

may be misoperations during the running of the program. This

includes things like running out of memory, or disturbances

of the display. If you are experiencing difficulty loading

or running this program, and any of those other types of

software are installed on your system, try removing them or

disabling them in various combinations to determine what is

causing the problem.

Video Considerations - The first time the program is used,

it will default to run in a black and white mode compatible

with most if not all video cards and display monitors

available. The program's command menu has options for

selecting the colors displayed, and for changing the

resolution of the display. (See Section 4.9.) These

selections may then be stored away as defaults for future

use.

3

Installation Procedure

Registered users receive a diskette containing the updated,

executable code and related files in non-compressed format.

They should be copied directly into the existing working

subdirectory on your hard disk.

If the program is obtained from a Bulletin-Board-System

(BBS), an electronic information system (i.e. CompuServe,

Genie, Prodigy, America On-Line,  etc. etc), or the

Internet, it will typically be presented as a single

compressed file with a name like MAINLINE.ZIP, MAINLI.ZIP,

or MNLIN2P0.ZIP. The file must be decompressed using a

current version of PKUNZIP. The decompressed file will

consist of the following files;

o  ML.EXE - The executable program file.

o  ML.ICO - An Icon file, for use under WIndows

o  SMCGA.FNT - Fonts used in high resolution black/white

display.

o  SMVGA.FNT - Fonts used in high resolution color display.

o  INSTALL.TXT - Notes about installing the program, similar

to this section.

o  ORDER.TXT - A Form for registering the program

o  README.1ST - A brief description of the program,

including installation considerations.

o  PACKING.LST - A list of the included files.

Create a subdirectory on your hard-drive such as C:\MAINLINE

and copy the above files into it.

Windows Installation: MainLine may be accessed from Windows.

Create a program item for it under a new or existing program

group. Attatch the ML.ICO icon file (f it does not happen

automatically).

The contents of diskettes obtained from Shareware vendors

may vary but will typically include the following files;

o  MAINLINE.EXE - A compressed, self-extracting file

containing the executable code, this documentation, and

several data files.

o  INSTALL.BAT - Installation Batch File

o  INSTALL.TXT - Instructions for using INSTALL.BAT to

install the program.

o  ORDER.TXT - A Form for registering the program

o  README.1ST - A brief description of the program,

including installation considerations.

o  PACKING.LST - A list of the included files.

Diskette vendors may also place other files on the diskette.

Before doing any installation, it is best to make a backup

copy of the supplied diskette. This is easily done by

copying all files on the diskette using the DOS command;

DISKCOPY b: b: (Assuming diskette drive is "b" - otherwise

substitute the proper disk drive letter.)

4

3  Trial Run - 1st Pass

This section will go through the real basics - turning the

program on, creating and saving a simple project, generating

some reports, and exiting the program.

First set the default drive to the one where you have stored

the program. Start the program by entering ML followed by

ENTER or Carriage Return (CR).

3.1  The Initial Screen

See Figure 1. After a few seconds the display will show a

Gantt/Pert chart for a minimal project. It will have only a

start milestone, a single task, and an end milestone. Here

are some important things to note about the way a schedule

is displayed.

o  The Calendar - Dates run left to right across the top of

the display. Month, date, and day-of-week (MTWTF) are

shown. Only week-workdays are used, and there are no

provisions for holidays.

o  Milestones - Each Milestone is represented by an asterisk

(*) and is shown as occurring on one day only.

o  Tasks - Tasks are represented as equal signs (=) if they

are on the critical path, or dash-lines (-) if they

aren't.

o  ID's - Each task or milestone must have a unique

identifying number which is displayed below it ("10" for

the "Start" Milestone).

o  Line Numbers - Each task or milestone is represented on a

3-row "Line". ("1" for the Start milestone, "2" for

"Task".) You can assign the Line Number for any Task or

Milestone, to format the Schedule the way you want.

o The name of the Current Project is displayed in the upper

left hand corner.

o The amount of used capacity is displayed. Since only 3 of

MainLine's 150 tasks are in use, the usage is quite small

(2%)

5

Figure 1: Blank Project

Project: MLWORK   Edit Task  :_             Usage 2%  INS    MainLine Rev 2.0

.----------------------+---------------------+------------------.

Press /,\,or   |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

ESC for       |    0    1    2    2  | 0    1    1    2    |    0    1    2   |

Command Menu  |    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|            2 | Task    .    .    .    .    .    .    .    .    .    .    .   |

|              | ===================^   .    .    .    .    .    .    .    .   |

|              |  20.    .    .    .    .    .    .    .    .    .    .    .   |

|            3 |    .    .    .    .End .    .    .    .    .    .    .    .   |

|              |    .    .    .    .*   .    .    .    .    .    .    .    .   |

|              |    .    .    .    . 30 .    .    .    .    .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|            5 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|            6 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

6

3.2  Moving Around - Key Commands

You can use keyboard keys to move around and look at other

parts of the schedule.

You can use the UP(^) and DOWN(v) arrows to scan through the

schedule one line at a time.

The "PAGE UP" and "PAGE DOWN" keys will move the display one

screen at a time.

Pressing the RIGHT and LEFT Arrow keys moves the display

horizontally.

Note - If multiple Arrow or PAGE UP/DOWN keys are entered

quickly, after a brief pause the screen will be updated only

once. This is a great timesaver. It reduces the time spent

waiting for the screen to be redrawn. To demonstrate this

feature, press RightArrow three times quickly. This only

works with multiple entries of the same key type.

These and other key selections are listed below;

Key                Function

Down Arrow         Advance Screen One Line

Up Arrow           Back Screen One Line

Right Arrow        Move Forwards in time.

Left Arrow         Move Backwards in Time

PAGE DOWN          Advance to Next Screen

PAGE UP            Go Back 1 Screen

HOME               Move to Top-most Screen and Start of

Calendar

CTRL-T             Move to Top-most Screen

CTRL-B             Move To Bottom-most Screen

CTRL-L             Move Horizontally Left To Start of Calendar

CTRL-R             Move Horizontally Right to Latest Used Date

CTRL-F             Find Task/Milestone

+                  Follow the critical path forwards in time

-                  Follow the critical path backwards in time

"|"                Go To A Specific Line Number

"\",/", or ESC     Activate Command Menu

7

3.3  The Command Menu

There are many commands for editing, filing, generating

outputs, etc. The majority are activated by use of a pull-

down menu. The menu is called up by pressing the "\", "/",

or ESC key. (Press "/" Now)

Note that the commands "File, Edit, Search ,Display,Print"

are displayed at the top of the screen, and that "Filing" is

highlighted.

The Highlight may be moved around by pressing the right- or

left- arrows. Try it, but then return to "Filing".

Pressing down-arrow cause a menu to appear below the

highlighted entry.

With "Filing" still highlighted, hit down-arrow now and note

that the menu choices New, Open, Save, Import, and Exit

appear. The first entry (New) is highlighted.

Pressing the Up- or Down Arrow key moves the highlight up

and down. Pressing the Right- and Left- Arrow keys moves to

adjacent menus.

Pressing the ENTER or RETURN key cause the highlighted

command to be executed.

While viewing the pull-down-menu, screen movement keys no

longer operate. Pressing ESCAPE at any time backs up one

level in the Menu-Command line. Pressing ESCAPE when at the

top level exits the Menu and normal screen viewing ability

returns. (Press ESCAPE twice now.)

From here on, sequences of using the pull-down-menu will be

described as follows;

"\+File+Save" means execute the series of menu choices

starting with "\" or "/", then "Filing",  and "Store".

8

3.4  Quick Entry - Adding a Task

The more frequently used functions of Edit, Add, and Delete

task may be activated directly without going through the

pull-down menu.

Note that the top-line of the screen  contains the phrase

"Edit Task:" followed by a blinking cursor. Pressing the "a"

key will cause the phrase "Add Task" to appear. Pressing "d"

similarly switches to "Delete Task:", and "e" returns to

"Edit Task:"

Press "a" to cause "Add Task" to appear. Type in "25" and

press ENTER. (All entries require termination by ENTER.)

Enter "t" or ENTER when prompted to select a Task or

Milestone.

You will be asked to specify the ID of a Task or Milestone

which the new task is to succeed - enter "20".

You will be asked to specify the ID of a Task or Milestone

which the new task is to preceed - enter "30". (You don't

have to enter anything here, you could leave it blank -

we'll just include it for this exercise.)

A Task Data Sheet for task 25 will now appear at the bottom

of the screen. You may edit any of the task's data entries

by selecting a letter/number associated with the data,

pressing ENTER, and then entering the data.

Enter "c" (with ENTER) to edit the Title. Then enter "New

Task".

"New Task" should appear in the Title field of the Task Data

Sheet.

Enter "d" to edit the Duration. Then enter "20" for 20

working days.

To leave the editing mode, enter "x" for Exit.

The full screen is displayed again. It should look like

Figure 2.

Note the following about the new task;

o  It is chronologically between the "Task" and the "End".

o  It is on line 2.

o  It is on the critical path.

Note 1 - Note that the screen-movement keys (Arrows, PG

UP/DN, etc, all function while the task editor is working.)

Note 2 - A default line number is always supplied, typically

the same line number as that of the "After Task?" entry.

When the Task Editor is active, you may change the line

number as follows;

Enter "l" to select which line the task should appear on.

Use BACKSPACE to erase the present line number, then enter

the new line number.

9

Figure 2: 1 Task Added

Project=<DEMO>      Usage = 2%             MainLine Rev 2.0

.----------------------+---------------------+------------------.

|_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|            2 | Task    .    .    . New Task.    .    .    .    .    .    .   |

|              | ===================^===================^   .    .    .    .   |

|              |  20.    .    .    .  25.    .    .    .    .    .    .    .   |

|            3 |    .    .    .    .    .    .    .    .End .    .    .    .   |

|              |    .    .    .    .    .    .    .    .*   .    .    .    .   |

|              |    .    .    .    .    .    .    .    . 30 .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|            5 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|            6 |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

|              |    .    .    .    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

10

3.5  Storing a Project

In order to store the edited project under a new name, do

the following;

Execute /+File+Save

You will be prompted for the name to store it under - a

default of "mlwork" is shown in brackets.

Type "demo" for the name and press ENTER.

The data base for this project has now been saved. The

project could be edited further (remember to store again

after additional changes), or you could exit, restart the

program, and load the stored project.

3.6  Printing Reports

Before exiting let's generate some output reports. We'll

just create the reports now, and examine them after exiting.

Create a schedule report by executing

\+Print+Partial_Schedule. Create a date report by executing

\+Print+Date_Report

Create a task-milestone report by executing

\+Print+Task_Detail

3.7  Exiting

Let's temporarily exit.

Enter the commands \+File+Exit

11

3.8  Examining The Reports

You should be back to the DOS prompt.

Enter the command

C:\MAINLINE>DIR

You will get a directory listing which should include the

following files

1. ML.EXE - The executable MainLine file

2. DEMO.PRJ - The data file for the demo project you have

created.

3. DEMO.PR1 - An auxillary data file storing text

information.

4. DEMO.TXT - The Schedule for DEMO

5. DEMO.DAT - A Date Report for DEMO

6. DEMO.RPT - A complete report with all the data of all the

tasks and milestones in DEMO.

7. MLJRNL.PRJ - A backup file to protect project data. (See

Section 5.3.)

8. MAINLINE.CFG - A configuration file storing options about

screen appearance.

DEMO.TXT is a text file containing the schedule. It will be

132 columns wide. It should look like Figure 2. (Figure 2

has been modified here to be 80 columns wide to fit better

in this manual.)

You can examine DEMO.TXT with the TYPE command or with a

text editor. You can mail it to anyone on your network. You

can send it to any ASCII printer. If you print it out in

LANDSCAPE on a laser printer, a viewgraph/transparency can

be made which is suitable for use in presentations.

DEMO.DAT lists the start- and end- dates for all the tasks

and milestones in DEMO. It is reproduced in Figure 3

DEMO.RPT lists all tasks and milestones in DEMO, with their

complete data - predecessors, titles, start and end dates,

etc. It is listed in Figure 4

Note - Any change to a .PRJ or .PR1 file could make the file

unusable. Never try to directly edit or otherwise change a

.PRJ or .PR1 file. Don't even try to view it with a word

processor or text editor.

12

Figure 3: DEMO.DAT

Report Date: 16-Mar-92

Task and Milestone Date Report        Project Name: demo

--------------------

Task# Typ Description                               Start      End

----- --- ----------------------------------------  ---------  ---------

10   S   Blank               Start                 02-Mar-92  02-Mar-92

20   T                       Task                  03-Mar-92  30-Mar-92

25   t                       New Task              31-Mar-92  27-Apr-92

30   F                       End                   27-Apr-92  27-Apr-92

13

Figure 4: DEMO.RPT

Report Date: 16-Mar-92

Task and Milestone Detail Report      Project Name: demo

--------------------

*******************************************************************************

Task #  10     Type S    Description; Blank                 Start

Start:02-Mar-92

End:02-Mar-92

Duration:  0

Wait :  0

Display Line:  1

Predecessors ;

-------------------------------------------------------------------------------

Task #  20     Type T    Description;                       Task

Start:03-Mar-92

End:30-Mar-92

Duration:  20

Wait :  0

Display Line:  2

Predecessors ;  10,

-------------------------------------------------------------------------------

Task #  30     Type F    Description;                       End

Start:27-Apr-92

End:27-Apr-92

Duration:  0

Wait :  0

Display Line:  3

Predecessors ;  25,

-------------------------------------------------------------------------------

Task #  25     Type t    Description;                       New Task

Start:31-Mar-92

End:27-Apr-92

Duration:  20

Wait :  0

Display Line:  2

Predecessors ;  20,

-------------------------------------------------------------------------------

14

4  Trial Run - 2nd Pass

In the previous chapter we demonstrated the very basics;

turning the program on, creating and storing a simple

project, generating some reports, and exiting.

This chapter will demonstrate in more detail the functions

of MainLine.

We'll start by reading back in the project that was

previously created.

4.1  Reading In A Project

Enter ML to start the program. Execute the command sequence

\+File+Open.

Select the project "demo". You may do this either of two

ways. Pressing ENTER will load the highlighted project.

(Arrow keys and PAGE UP/DOWN keys move the highlight around

the displayed list of existing project files.) Or, just type

in the project name DEMO followed by ENTER.

Note - Another way to load a project is to include the name

of the project when starting Mainline. I.E. entering ML DEMO

at the DOS prompt would have automatically loaded the DEMO

project.

4.2  Editing an Existing Task

Before demonstrating more functions, lets first update the

project to represent something a little more specific.

Call up the Task Editor for Task 20.

Select the Title by entering "c". Erase the present title

using the BACKSPACE key, and enter the new title "Define".

In a similar manner, edit the task duration (field "d") to

be 10 days.

Select task 25 for editing by entering "n" (for New task)

and the Task Data Sheet for Task 25 will appear. Using the

procedure above, change its title to "Develop".

Select "x" to end the editing session.

This has demonstrated how to make changes to an existing set

of tasks or milestones.

Note that in editing entries the cursor may be positioned

using the right- and left-arrows, and new characters may be

inserted by typing.

15

4.3  Inserting, Deleting, Moving Lines

The lines on the screen may be changed much like those in a

spreadsheet. Blank lines may be added or deleted, or blocks

of lines may be moved around.

To insert some blank lines execute \+Display+Add_lines.

When prompted, enter that you want to add lines before line

3, and that you want to add 3 lines. Note on the screen that

the END task has been "pushed down" 3 lines. (Remember - one

"line" means 3 rows on the screen.)

We don't need to demonstrate it here, but by using

\+Display+Delete_lines you can delete a group of consecutive

lines.

It is not possible to delete a line that has tasks or

milestones on it.

You are now somewhat proficient at adding and editing tasks.

Now proceed to add the following tasks to the project.

o  Task 40, line 2, duration 15, title "Manufacturing" - add

this task after task 25, and before milestone 30.

o  Task 50, line 3, duration 30, title "Programming" - add

this task after task 20, and before milestone 30.

o  Task 60, line 4, duration 33, title "Marketing" - add

this task after task 20, and before milestone 30.

o  Task 70, line 5, duration 20, title "Testing" - add this

task after task 25, and before milestone 30.

The project should appear as in Figure 5. At this point, save

the project so the work doesn't get lost.

To move lines 5 and 6 so that they are after line 2, and

ahead of the present line 3, execute \+Display+Move_lines.

When prompted respond as follows;

Move From Line = "5"

Thru Line = "6"

To Line = "3"

The whole command sequence will be repeated for

verification. Type ENTER to proceed, or "n" to abort. The

lines should now be re-ordered as in Figure 6.

16

Figure 5: Tasks Added

MainLine Rev 2.0

.----------------------+---------------------+------------------.

|_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|            2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |

|              | =========^===================^--------------^   .    .    .   |

|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |

|            3 |    .    . Programming  .    .    .    .    .    .    .    .   |

|              |    .    . -----------------------------^   .    .    .    .   |

|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |

|            4 |    .    . Marketing    .    .    .    .    .    .    .    .   |

|              |    .    . --------------------------------^.    .    .    .   |

|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |

|            5 |    .    .    .    .    .    . Testing .    .    .    .    .   |

|              |    .    .    .    .    .    . ===================^   .    .   |

|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |

|            6 |    .    .    .    .    .    .    .    .    .    .End .    .   |

|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |

|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

17

Figure 6: Moved Lines

MainLine Rev 2.0

.----------------------+---------------------+------------------.

|_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|            2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |

|              | =========^===================^--------------^   .    .    .   |

|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |

|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |

|              |    .    .    .    .    .    . ===================^   .    .   |

|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .End .    .   |

|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |

|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |

|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |

|              |    .    . -----------------------------^   .    .    .    .   |

|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |

|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |

|              |    .    . --------------------------------^.    .    .    .   |

|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

18

4.4  Deleting A Task

Deleting a task is very straightforward.

Press "d" to change the quick entry mode to "Delete Task"

and enter the ID of the task or milestone to be deleted.

(Alternatively, use the pull-down-menu to execute

\+Edit+Delete)

In some instances it may not be appropriate to delete a

task, and the DELETE will be automatically aborted. This can

occur if deleting the Task would make it impossible to

calculate the Critical Path.

How It Works

The critical path is automatically calculated between a

specified "Start" milestone and a specified "Finish"

milestone.

These two milestones are selected by the user. Call up the

task data sheet and you will notice that there is a field

called "Type". Tasks and Milestones are identified here by

"t" and "m" respectively.

The "S" (Start) milestone is fixed for any one project. Any

one milestone may be assigned as the "F" (Finish) Milestone.

The Critical path is calculated between the Start and Finish

milestones.

Requirements

The only requirement is that there be a logical "path"

between the Start and Finish milestones. An interesting

result of this is that you may have other tasks/milestones

which originate or terminate "in space" - no path leading

directly from or to the Start and Finish dates. This is

acceptable, and in many cases reflects real life. (Many

other Project Management tools require that all tasks are

connected together and that there are no "loose ends".)

Moving the End Points Around

The "Blank" project starts with exactly one Start and one

Finish Task assigned.

To "move" the Finish designation around, for What-If

purposes, you may temporarily append the Finish

characteristic to more than one milestone, then remove the

superfluous one. Any edits which even temporarily result in

having no Finish milestone will be rejected.

If at any point there is more than one Start or Finish

milestone, the critical path calculations may be wrong. This

will be corrected once there are no superfluous Starts and

Finishes.

19

4.5  Adding Descriptions to Groups of Tasks

It is helpful to add comments to groups of tasks or

milestones.

Comment fields may be added in the left hand field of the

display. There are two comment fields, called Head1 and

Head2.

Call up the DEMO project. Edit task #20 ("Define") so that

the Head1 field contains "Project 1" and the Head2 Field

contains "- Hardware". Edit Task 50 ("Programming") so that

the Head2 Field contains "- Software". Finally, edit Task 60

("Marketing") so that the Head2 field contains "- Other"

The schedule should now look like Figure 7.

When 2 or more Tasks or milestones on the same line both

have entries in their Head1 or Head2 fields, the Heads from

one task/milestone are arbitrarily selected for display.

4.6  Adding A Date and Labels to The Display

A Date field, and user-defined Labels, are displayed in the

upper left-hand corner of the display. There are 4 Labels,

each 15 characters long.

The Date field is assigned or updated whenever the project

is Stored.

The Label fields are set by the user using the commands

\+Display+Labels

A menu will be presented to enter new Labels or to change

the existing ones.

20

Figure 7: Adding Comments

MainLine Rev 2.0

.----------------------+---------------------+------------------.

|_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|Project 1   2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |

| - Hardware   | =========^===================^--------------^   .    .    .   |

|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |

|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |

|              |    .    .    .    .    .    . ===================^   .    .   |

|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .End .    .   |

|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |

|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |

|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |

| - Software   |    .    . -----------------------------^   .    .    .    .   |

|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |

|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |

| - Other      |    .    . --------------------------------^.    .    .    .   |

|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

21

Figure 8: Date and Label Fields

MainLine Rev 2.0

Label 1        .----------------------+---------------------+------------------.

Label 2        |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

Label 3        |    0    1    2    2  | 0    1    1    2    |    0    1    2   |

Label 4        |    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|Project 1   2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |

| - Hardware   | =========^===================^--------------^   .    .    .   |

|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |

|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |

|              |    .    .    .    .    .    . ===================^   .    .   |

|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .End .    .   |

|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |

|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |

|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |

| - Software   |    .    . -----------------------------^   .    .    .    .   |

|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |

|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |

| - Other      |    .    . --------------------------------^.    .    .    .   |

|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

22

4.7 Multiple Editing Views

Call up the task editor for any task. Note that, adjacent

to the 4 date fields (Begin, Finish, Duration, Wait) there

are 4 text fields labeled G, H, I, and J respectively. These

4 fields may be used for any purpose, although they would

be most convenient for providing brief notes about the 4

adjacent date fields. Example;

[B] Begin   : 22-Mar-94        [G] Started On Schedule

[F] Finish  : 29-Mar-94        [H] Projected End

[D] Duration:  5               [I] Best Estimate

[W] Wait    :  0               [J]

Note that by pressing the "v" key and ENTER/RETURN, the view

of the task editor changes. Predecessor and date information

are replaced by 4 lines of text labeled 1,2,3, and 4

respectively. Pressing the numeric key and ENTER/RETURN

allows each line to be edited.

This allows a short amount of description to be appended to

every task or milestone. The information is printed out as

part of the normal TASK DETAIL REPORT.

Selecting "v" again  changes the view one more time. The 10

predecessor are displayed. The Description field of each

predecessor is listed, as well as the predecessor's

identifying task number. This makes it somewhat easier to

edit predecessors.

Selecting "v" one more time returns the Task Editor to its

original view.

4.8  Locating Tasks - The "Search" Function

Features are included to make it easy to locate a particular

task. This becomes necessary as a project grows.

You can search through the entire project for one or more

tasks having a particular Title or Descriptive field. Enter

\+Search and menu entries  will be presented to search by

Description, Head1, or Head2. Enter a word or phrase, and

all tasks will be sequentially displayed that match the

entry. "Near misses" will be accepted - i.e. if "Des" is

entered, tasks or milestones having Titles of "Design",

"Destination",and "Oldest" would all be located. (The search

ignores the case of characters). This can be very helpful

when the exact title is not remembered. As each found task

is displayed, the option is presented of stopping and

displaying the screen holding that task, of continuing the

search, or of quitting. If you continue to search and no

further matching tasks are found, you have the option of

displaying the last found match, or of quitting.

It is also possible to locate tasks directly by ID Number

(press CTRL-F when viewing the screen) or by going to the

tasks line if it is known ( press "|" ).

23

4.9  The Wait Function

It is sometimes useful to specify that a task not actually

start  until some fixed time after its predecessors have

completed. This could be accomplished by inserting a "wait"

task. However, MainLine offers the simpler step of assigning

a "wait" period for each task.

In the Demo example, edit the [W]ait field of the task data

sheet for task 40 to have a delay of 10 days. The results

are shown below. The period of waiting is indicated by a

string of "......" characters for tasks off the critical

path, or "::::::" for tasks on the critical path.

Figure 9: Using The Task Wait Function

MainLine Rev 2.0

Label 1        .----------------------+---------------------+------------------.

Label 2        |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

Label 3        |    0    1    2    2  | 0    1    1    2    |    0    1    2   |

Label 4        |    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|Project 1   2 | Define  . Develop .    .    .    .    . Manufacturing.    .   |

| - Hardware   | =========^===================^::::::::::==============^   .   |

|              |  20.    .  25.    .    .    .    .    .  40.    .    .    .   |

|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |

|              |    .    .    .    .    .    . -------------------^   .    .   |

|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |

|            4 |    .    .    .    .    .    .    .    .    .    .    .End .   |

|              |    .    .    .    .    .    .    .    .    .    .    .*   .   |

|              |    .    .    .    .    .    .    .    .    .    .    . 30 .   |

|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |

| - Software   |    .    . -----------------------------^   .    .    .    .   |

|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |

|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |

| - Other      |    .    . --------------------------------^.    .    .    .   |

|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

24

4.10  Changing Program Configuration

MainLine has several options for changing the appearance of

the screen display or printed output, or for changing

fundamental characteristics of the present project. These

are accessed via the command \+Display+Options.

The menu shown in Figure 10 will appear. Information about

the current project will be displayed - the project's name,

and its date of most recent revision. Other information

about how MainLine is currently operating is also displayed.

Information preceded by a letter in brackets may be changed

using this menu.

To change a setting, enter the bracketed letter in front of

the setting, and then press ENTER. For some settings, a

series of choice-prompts will follow. For others, the

setting will automatically toggle to its only other value.

Example - Changing The Start Date

MainLine uses the current date as the default project start

date. To change it, enter S followed by ENTER. When prompted

for a new start date, enter 6-Jan-92.

Press X followed by ENTER to leave the Options menu. The

Calendar should be appropriately updated. When you store the

project again, the new start date will be stored with it.

The only restriction is that the selected date must be on a

week-day.

Example - Changing The Time Scale

Projects can be displayed using either days or weeks as the

basic unit of time. When the default, days, is used,

approximately 4 1\2 months of activity may be displayed on

an 80 column screen. (Wider screen styles, allowing longer

time ranges to be displayed, are described in the following

material.) When a scale of weeks is used, approx. 7 months

activity can be displayed on an 80 column screen.

On the Options menu, enter T and ENTER, and the time scale

will automatically toggle from DAYS to WEEKS.

When a project is stored, the time_scale in use is stored as

part of the project. That time scale will be used when that

project is read back in at a later time.

Note - All Task Durations must always be entered as working-

days, regardless of which time scale is used for displays,

25

Figure 10: Display Options Configuration Menu

.------------------------------------------------------------------------------.

!      Project                                Configuration                    !

!      ----------------------------           -----------------------          !

!            Name       : __________                Name  : __________         !

!            Rev Date   : __________            [F] File                       !

!        [S] Start Date : __________            [G] Get                        !

!                                                                              !

!      Screen                                 Printer                          !

!      ----------------------------           ---------------------            !

!        [W] Width      : ___                   [P] Print Width: ___           !

!        [C] Color/Fore : __________            [D] Display ID : ___           !

!                 /Back : __________                                           !

!        [T] Time Scale : __________                                           !

!        [I] ID Display : __________            [X] Exit                       !

!                                                                              !

!             Press Letter in [ ] To Change Function, [x] to Finish            !

!                                                                              !

!   MainLine Rev 2.0   Registered To : ____________________    Ser.No. _____   !

`------------------------------------------------------------------------------'

26

Screen Width and Color

Black and White display, of an 80 column-wide screen, is the

default display mechanism. However, the use of colors and

wider screen styles is also supported.

Assuming your machine's graphics adapter and monitor support

color, you may change the display colors using the Global

Colors function [C]

A wider time range may be displayed on the screen by

changing the Screen Width to 105 columns using the Width

function [W]. The 105 columns mode also provides about 50%

more rows of displayed data. If your system supports VGA

graphics, you will be prompted for a choice of Black/White

display ("CGA-style" graphics) or full color. If your system

does not support VGA graphics, only the Black/White CGA-

style is offered.

There are some tradeoffs to using the 105 columns-mode of

screen display;

o  All letters are displayed in Uppercase. (Printed outputs

continue to use Upper and Lower case).

o  Black/White CGA-mode runs somewhat slower than 80-columns

mode. 105-Columns color-mode runs slower still. This is more

noticeable on older, slower machines. On a 20 MHz 386-based

machine, all modes run quite acceptably.

27

Other Settings

Here is a brief description of other settings that may be

selected using the Options menu. See Section 6 for more

information.

o  [I] : Screen ID Display - Controls (yes/no) whether task

identifying numbers are displayed below each task. This

allows mores lines of tasks to be displayed on the screen.

o  [P] : Printer Size - Selects "A" size 80 column output,

or "B" size 132 column output.

o  [D] : Printer ID Display - Similar to Screen ID Display,

but affects printed output only.

Configuration Files

You can store the configuration so that it will be used

automatically the next time MainLine is used. (This saves

you from having to set it up every time). Pressing F and

ENTER will file the present configuration. A default

filename will be supplied (MainLine). Press ENTER to store

the configuration as MainLine. You may find that there are

different configurations you prefer to use on some

occasions. You can set a different configuration, then store

it under some other name. It can be recalled at a later time

using the "Get" command (choice G in the Options Menu). The

name of the configuration presently in use is always

displayed in the Options menu.

The configurations are stored in your directory with

extension .cfg. You do not have to specify the extension

when storing or loading a configuration file - that is done

automatically.

28

5  Advanced Topics

5.1  System Capabilities

Projects of the following sizes can be handled;

o  Up to 150 Tasks and/or Milestones.

o  Tasks/Milestones may be displayed on up to 1000 "Lines"

o  Dates must fall within the range of 1-Jan-1991 to 1-Jan-

2000.

Attempts to exceed these values will usually not be

accepted. It is possible that under some circumstances the

program may accept the value and then crash.

5.2  Following The Critical Path

On larger projects, it may be desirable to trace the tasks

and milestones along the critical path. Pressing the "+" and

"-" keys moves the display forwards or backwards in time

along the critical path.

5.3  The Journal File - Recovering Damaged Project Files

It is possible that at some time the operation will be

unwillingly terminated while there are edits that have not

been saved.

This may occur due to a system crash (possibly due to a

power outage), or due to some as-yet-unknown bug in the

program. To allow recovery from this, a "backup" or

"journal" file of editing activity is created. Every time

you leave the text editor, the Project File of the current

project, including edits, is copied to the file MLJRNL.PRJ.

To recover, copy the MLJRNL.PRJ to some random project

filename like RECOVER.PRJ. Then start MainLine again, and

read in RECOVER as a project. If it appears to be what you

want, exit the program and copy RECOVER.PRJ over your

original projects' .PRJ file.

29

5.4  Attaching Fixed Dates to Tasks or  Milestones

A task or milestone may be entered with no predecessors,

with its date manually entered. This is useful for

indicating fixed or external occurrences.

To do this, enter the task or milestone using the normal

task addition procedure. When prompted for "After Task?"

enter n for "none". Enter (or not) a "Before Task?". When

the Task Editor Screen pops up, enter a [B]egin date for the

new task or milestone.

Thereafter, that task or milestone will appear at that date,

regardless of other tasks or milestones in the project. (You

can always Edit that date.)

Note - Fixed tasks or milestones which get on the critical

path will prevent the critical path from reaching all the

way back to the project START milestone. There is nothing

wrong with this, but it may at first appear to be a

surprising result. It will be flagged as a  WARNING.

5.5  Project Rollups

It is often desirable to summarize a group of related tasks

as one larger effort. The Project Rollup task provides this

function.

A Rollup is a special type of task whose beginning and end

dates are linked to a collected group of tasks.

Figure 11 demonstrates this function. Task #100 is a rollup

task. It rolls up the results of tasks 40,70, and 90. Note

that 100's start date equals the start date of task 40

(earliest start of the 40,70,90). Task 100's end date equals

the end date of task 90 (latest end date of 40,70,90) Note

that task 70's start and end lie within the min/max ranges,

and so task 70 does not affect task 100. (Later changes in

start/ends of the project tasks could alter this.)

Entering Rollup Tasks - A Rollup task is entered using the

same process as a regular task. Enter it initially as a

regular task. It's predecessors are the tasks it is to

rollup. After entering the rollup task, use the TASK/EDIT

function to change its TYPE to "R" or "r".

Helpful Hint - On a large schedule, Rollups can be used to

provide a concise summary of the overall project. Enter the

whole schedule in the normal fashion. Create a page-worth of

blank lines at the head of the schedule. Place rollups there

which summarize the key subsections of the project.

30

Figure 11: Using Rollup Tasks

MainLine Rev 2.0

.----------------------+---------------------+------------------.

|_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |

|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |

|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |

|            2 |    . Rollup - 40/70/90 .    .    .    .    .    .    .    .   |

|              |    . -----------------------------^   .    .    .    .    .   |

|              |    .  100    .    .    .    .    .    .    .    .    .    .   |

|            3 | Task Task 40 . Task 50 .    .    .    .    .    .    .    .   |

|              | ====^=========^---------^   .    .    .    .    .    .    .   |

|              |  20.  40.    .  50.    .    .    .    .    .    .    .    .   |

|            4 |    .    .    . Task 90 .    .    .    .    .    .    .    .   |

|              |    .    .    . ===================^   .    .    .    .    .   |

|              |    .    .    .  90.    .    .    .    .    .    .    .    .   |

|            5 | Task 60 . Task 70 .    .    .    . Task 80 .    .    .    .   |

|              | ---------^-------------------^   . =========^   .    .    .   |

|              |  60.    .  70.    .    .    .    .  80.    .    .    .    .   |

|            6 |    .    .    .    .    .    .    .    .    .End .    .    .   |

|              |    .    .    .    .    .    .    .    .    .*   .    .    .   |

|              |    .    .    .    .    .    .    .    .    . 30 .    .    .   |

`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|

|MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|

|    0    1    2    2  | 0    1    1    2    |    0    1    2   |

|    6    3    0    7  | 3    0    7    4    |    8    5    2   |

|     Mar '92          |    Apr '92          |    May '92       |

`----------------------+---------------------+------------------'

31

5.6  Renumbering Tasks and Milestones

As a Project is used and modified over time, it may become

desirable to renumber tasks. Work is generally easier if

related tasks have task numbers in the same range.

The Renumber command;

\+Edit+Renumber

allows this. You may renumber an individual task, a group of

tasks, or all the tasks in the present project. You select

the task(s) to be renumbered, and specify a point to start

renumbering the tasks At. All tasks are renumbered from the

starting point forwards. The tasks will have the same

sequence as in the original range. They will be numbered in

steps of 10. To prevent overlaps, or having multiple tasks

with the same number, a few restrictions are imposed;

o  The new range cannot overlap any tasks which aren't being

renumbered.

o  The new range cannot overlap the "old range" of tasks

that are being renumbered.

Any attempted renumberings which violate the rules are

rejected.

The rules may not seem intuitively obvious. If you

experiment with a sample project, though, the principles

will soon become clear.

5.7  Copying A Group of Projects

Very often a sequence of events (a group of tasks and

milestones) will need to be entered multiple times in a

project. This is simplified by using the Copy Tasks

function. \+Tasks+Copy will lead to a menu to select a range

of tasks for copying. Since each task must have a unique ID

number, the menu will request a new starting point to re-

number the copied tasks to. A sufficient block of blank

lines is automatically inserted into the project following

the last task to be copied. The range of tasks/milestones

will then be copied into that area, with the same

relationships, durations, titles and comments. It is

advisable, but not mandatory, to modify the titles and

comments to make it easier to distinguish the new tasks from

the old ones.

32

5.8  Importing Projects

It often becomes desirable to merge together projects which

have been developed separately. This is achieved using the

Import command;

\+File+Import

Before any two projects can be merged, it is necessary to

make sure that the two projects do not repeat any task

numbers. This can be done easily using the Renumber function

described above.

It is not necessary for you to change the Line Numbers which

are used to display the tasks. The program does this for

you. It re-numbers the "Line Number" entry for each task so

that the imported project starts being displayed after the

existing project. (If you don't like this order, you can

always change it using the Move Lines command.)

The merged projects retain the name of the project that was

in memory when the import started.

If the original and imported projects have different start

dates, the earlier date is selected as the start date for

the merged projects.

There are cases where projects cannot be merged. The reason

will be displayed, along with relevant numbers. The cases

are;

o  The imported project cannot have tasks numbers which

overlap the existing project.

o  The total number of tasks in the merged project cannot

exceed the maximum number of tasks allowed per project

(150).

o  The total number of lines displayed cannot exceed the

maximum displayed for any one project (1000).

After two projects have been merged, some additional work

may be necessary. For example, if the two projects each have

their own Start and End milestones, it will be necessary to

select single Start and End milestones for the new, merged,

project.  Also, it will probably be necessary to add links

between various tasks in the two projects - that was

possibly the reason for merging the projects in the first

place.

33

6  Command Listing

This section describes briefly all functions that may be

accessed by the menu-command line.

6.1  Filing

The following functions may be accessed by this command;

1. New - Restarts with the "blank" project being displayed.

2. Open - recall an existing project file. You will be

prompted for a project name.

3. Save - Save away the project file which is being worked

on. A default is always given. If you're working on a file

which was read-in, the old name is the default. You may

store it under a new name if you wish.

4. Import - Merge another project file with the project

presently being worked on.

5. Exit - Leave Program

6.2  Edit

This is the environment for changing tasks and milestones.

1. Change - Select an existing Task or Milestone to change

its data.

2. Add Task - Add one or more new tasks.

3. Delete - Delete an existing task or milestone.

4. Find Task - Locate an existing task by its ID number.

5. Renumber - Change the Task Numbers for One, Some, or All

Tasks.

6. Copy - Duplicate a group of tasks and milestones.

6.3 Search

Search for tasks by

1. Description

2. 1st Header

3. Second Header

34

6.4  Display

1. Options - Set system options of;

Screen Width (80 or 105 column display), Color (foreground

and background colors),  Screen ID(Show or hide, to

compact data on the screen), Calendar Start Date, Time

Scale, Printer Width), Print ID (Similar to Screen ID, but

for printed output.)

2. Add Lines - Add Blank Lines into the display.

3. Delete Lines - remove unused lines from the display.

4. Move Lines - Move a block of used lines up or down.

5. Labels - Enter or change 4 label-lines on display.

6.5  Print

1. Partial Schedule - Print a schedule report covering only

the time-span presently shown on the screen. Output file =

filename.txt

2. All Schedule - Print a schedule report for the period

currently shown on the display through the end of the

project. Adjacent pages of the report will need to be

taped together to obtain a full horizontal view. Output

file = filename.txt

3. Date Report - Print a report of the start and end dates

for all tasks and milestones. Output file = filename.dat

4. Task Detail Report - List complete information on all

tasks and milestones in the project. Output file =

filename.rpt.

1

APPENDIX  A - QUICK-START INFORMATION

A.1  Starting Up

Decompress the program files and install in a directory such

as C:\MAINLINE. If the progrtam was obtained as a .ZIP file

from a BBS, it can be copied into the directory and

decompreseed using PKUNZIP.If obtained from a Shareware

supplier, use the supplied INSTALL.BAT file or other

installation tool.

The executable file is ML.EXE. To run the program, at the

DOS prompt type ML followed by ENTER.

A.2  Moving Around The Screen

After a few seconds a screen will be displayed for a blank

project.

The calendar is displayed across the top of the screen.

The duration of all tasks is identified with either "="'s

(on critical path) or with "-"'s (not on critical path.) All

milestones have a duration of 0 and are indicated with a

"*". All tasks and milestones have unique identifying TASK

ID numbers. These are displayed on the schedule below the

row of symbols (-,=, or *) indicating the duration of the

task/milestone.

The up and down arrow keys may be used to scroll the display

up and down one task-line at a time.

When examining the schedule, the following other controls

may be used;

Key                Function

Down Arrow         Advance Screen One Line

Up Arrow           Back Screen One Line

Right Arrow        Move Forwards in time.

Left Arrow         Move Backwards in Time

PAGE DOWN          Advance to Next Screen

PAGE UP            Go Back 1 Screen

HOME               Move to Top-most Screen and Start of

Calendar

CTRL-T             Move to Top-most Screen

CTRL-B             Move To Bottom-most Screen

CTRL-L             Move Horizontally Left To Start of Calendar

CTRL-R             Move Horizontally Right to Latest Used Date

CTRL-F             Find Task/Milestone

+                  Follow the critical path forwards in time

-                  Follow the critical path backwards in time

"|"                Go To A Specific Line Number

"\", "/", or ESC   Activate Pull-Down Menu

2

A.3  Calling Up Commands

Pressing "\" , "/", or ESC calls up a pull-down menu at the top

of the screen. The majority of commands are activated from this.

One entry on the command line is highlighted. The highlight

may be moved around by using the horizontal arrow keys (<-

or ->). Pressing Down-Arrow causes a menu of choices to appear.

One of them is highlighted. The Up- and Down-Arrows move the

highlight. The Right- and Left-Arrows select adjacent menus.

Pressing ENTER activates the highlighted command. Pressing

Escape backs out of the menu system.

The most frequently used functions of Editing, Adding, and

Deleting tasks may also be used without going through the

menu system. Type "e", "a", or "d" to select which function.

Enter the task number followed by return, and the function

will start.

A.4  Basics of Editing and Generating Reports

Existing Tasks and Milestones are edited by activating the

menu  and selecting "Edit" followed by "Change". A data

sheet will appear listing all current data on the task or

milestone. Individual entries are selected by pressing the

code-letter in front of the data field on the sheet - i.e.

"d" for "duration", "c" for "description, etc. Additional

data views may be obtained by entering "v". When done, enter

"x" to exit the data-editor with changes, or "q" to quit

without implementing the changes.

New Tasks and Milestones may be added by using the menu-

command to select "Edit" followed by "Add Task". You will be

prompted for basic information about the task/milestone, and

then the data sheet will appear.

Similarly, tasks may be deleted using "Edit" followed by

"Delete". Deletions which make it impossible to calculate

the critical path are not accepted.

A.5  Notes on Dates and Calculations

o  Each project must contain one milestone designated as the

"Start" of the Critical Path, and another designated as

the "Finish". These selections are made with the data-

sheet editor by entering "s" and "f" respectively in the

"Type" field for those milestones.

o  There must be a logical path of tasks and milestones

between the Start and Finish milestones. There may be

tasks and milestones which are partially or completely

disconnected ("hanging or ending in space"), but there

must be a set of tasks and milestones connecting the Start

and Finish together.

o  Only work-weekdays are used. Weekend-days, if entered,

are rejected.

1

APPENDIX  B - SELECTING OUTPUT FORMATS

A principal function of MainLine is to generate compact

schedule reports suitable for viewing on screens, mailing,

hardcopy, or making viewgraphs for use in presentations.

The schedule is a TEXT file which can be mailed, or printed

in a variety of ways. A schedule printed on 8.5"x11" paper

can be made into a viewgraph or transparency suitable for

presentations. Use the \+Display+Options command to select

whether the output is 80 or 132 columns wide. A schedule

that is 132 columns wide can be printed on 11"x14.5" paper

and reduced on a photocopier onto 8.5"x11" paper. Many

printers provide a LANDSCAPE option which allows a schedule

132 columns wide to be printed directly on 8.5"x11" paper.

1

APPENDIX  C - SERVICE

Registered users are provided service for this program.

Telephone service is provided at (617)489-5639

Limited service is also provided on the INTERNET network at

address bck@world.std.com