^T - A TASK MANAGEMENT SYSTEM

USERS GUIDE

VERSION 1.12

Copyright (C) 1989

Steve Starsinic

Hummelstown, Pennsylvania

All Rights Reserved

TABLE OF CONTENTS

Introduction.................................................. 3

Features...................................................... 5

License/Copyright/Registration Info........................... 7

Installation/Configuration.................................... 8

How To Use ^T................................................. 9

Summary.................................................. 9

Editing the Custom Calendar.............................. 9

Edit File Name........................................... 9

Add Resources............................................ 9

Adding Tasks.............................................10

Conflicts................................................12

Removing Conflicts.......................................12

Editing Tasks............................................13

Editing Resources........................................13

Adding And Using Projects................................13

Outline Maintenance......................................14

Deleting Tasks...........................................14

Deleting Projects........................................15

Saving the File..........................................15

Customizing The Outline Display..........................15

Printing Reports.........................................15

Questions And Answers.........................................16

Future Versions of ^T.........................................18

^T Registration Form..........................................19

- 2 -

INTRODUCTION

^T (pronounced "control-T"), is a Task Management System.  Its

purpose is to provide constant and accurate feedback about your

current workload.

To properly understand ^T, it is first necessary to distinguish

between "tasks" and "projects", not according to textbook or

dictionary definitions, but as they are interpreted by the

author.

A task is (1) a work assignment that is complete, in and of

itself, or (2) a single step in the development of a project.

A project is a work assignment whose completion is dependent on

the completion of a number of tasks.

^T is oriented towards managing tasks, not projects.  ^T will

allow you to set up, in outline form, the resources (usually

people) you are responsible for managing, and the tasks assigned

to each.  With regular management of your outline model, ^T will

be able to tell you (1) the size and duration of your current

workload, (2) the status of each task, (3) costs associated with

each task, (4) workload and scheduling conflicts, and (5) a

limited form of project tracking.

The design of ^T was influenced by a number of underlying

philosophies:

First, not all of us require $500 project Management packages.

The cost is too high, the systems too complicated, and the

learning curve too long.

Second, not all of us manage large scale projects.  Instead, we

manage a number of people, to whom we assign individual tasks.

In these environments, the intricacies of network diagrams and

dependencies get in the way rather than help.

Third, tasks have a relatively high turnover rate and are subject

to frequent rearrangement, requiring frequent updating of

schedules.

Fourth, the duration of a task (on the calendar) is not the same

as the number of working days the task requires.  All workers

have both "unscheduled" responsibilities as well as plain wasted

time that prevents full-time attention to scheduled tasks.

Lastly, even though people are capable of working on more than

one task at a time, managing the distribution of one worker's

- 3 -

time across several of that worker's tasks is best left to the

worker.

With these philosophies in mind, ^T is relevant, inexpensive,

easy to learn, and easy to use.  With ^T, you create a workload

outline using resources as the "parent" items, and tasks as

"child" items.  tasks are attached to resources, and can be

easily rearranged and/or reassigned.  If more than one task

(regardless of resource) is part of a project (as defined above),

a project view of the outline will show that relationship.  In

addition,  start/end dates and costs are accumulated in the

project.

There are a number of things that ^T does NOT do.

It does not attempt to represent that fact that tasks are worked

on concurrently.  tasks are arranged in an outline form, with the

start date of a given task being the end date of a previous task.

This arrangement relieves the user of having to "time-slice" a

resource (a maddening and futile chore in a high task turnover

environment), and still represents the total task load of the

resource and the status of individual tasks.  Also, by logically

gathering tasks together in the outline, using priorities, and

setting commitment dates, all within ^T, planning and control can

be done effectively.

You can NOT force start dates.  The jury is still out on this,

but for now ^T always calculates a start date.  If a start date

must in reality be delayed, lock in the committed end date

instead.  Then ^T will warn you if developments in the workload

are threatening this date.

Tasks can NOT be made dependent across resources.  In other

words, the start date of a task for Resource 'A' cannot be

calculated based on the end date of a task for Resource 'B'.

^T does NOT provide PERT style (network) diagrams or Critical

Path determination.  If those approaches to project management

are important to you, ^T is inappropriate for your needs.

^T does NOT print Gantt charts.  Some form of Gantt chart

printing may be added in the future.

- 4 -

FEATURES

Some ^T Program Features.

GENERAL

- Outline orientation

- Drop-down menus

- Pop-up data entry screens and error messages

- Help

- Modifications made in-memory.  File saves take place only

on command.  Built in warnings to prevent accidental loss

of changes.

- Easy modification of data

- File loads on demand and from command line

RESOURCES

- Handles up to 50 resources

- Hourly charge rates for each resource

- "Unscheduled Time" factors for each resource

TASKS

- Handles up to 500 tasks.

- tasks can be rearranged or reassigned

- Tracking of time spent, costs, start and end dates, etc.

- Set priorities and committed completion dates

- Age warning for inactive tasks

- On-screen warning of conflicts

PROJECTS

- Handles up to 100 projects

- project commitment date governs all linked tasks

- Accumulate dates and costs for all linked tasks

CONFIGURATION

- Customize calendar as to days per week worked, hours per

day, and holidays.

- Customize age warning period, manual recalc, printer

driver

- Modify or create new printer drivers

- Complete control over which fields for tasks, resources

and projects display in outline.

- Customized screen colors, with pre-configured color and

monochrome color sets.

- 5 -

PRINTING

- Print to screen, print file, ASCII data, printer

- Uses either serial or parallel printer

- Outline report prints entire outline

- Resource assignment report prints just the assignments for

one resource on a separate page.  Select one at a time

or print all resources consecutively.

- Project assignment report prints assignments for a

project on a separate page.  Select one at a time

or print all projects consecutively.

- In reports, only currently selected fields are printed.

- 6 -

LICENSE/COPYRIGHT/REGISTRATION INFO

License

^T is a Shareware product.  It is legal to take or to give copies

of ^T for the purpose of evaluating it.  If, after evaluating ^T

for a period of 30 days, you decide that it does not meet your

needs, you are expected to discontinue use.  If you wish to

continue to use ^T, you are expected to register your copy by

completing the registration form in the back of this manual and

sending it and $35.00 to

Steve Starsinic

7 Dorchester Road

Hummelstown, PA 17036

Registration benefits: (1) the legal right to use ^T, (2) the

current version on disk, and (3) inclusion on the ^T users

mailing list.

You may NOT (1) sell ^T, (2) bundle ^T with other goods or

services, or (3) modify ^T in any way.  Licenses are granted to

the individual registrant only.  Write to the above address to

request exceptions or to inquire about site or corporate

licenses.

^T is provided on an AS IS basis without warranty of any kind,

expressed or implied, including but not limited to the implied

warranties of merchantability and fitness for a particular

purpose.

Any comments, bug reports, or suggestions for improvement may be

mailed to the above address or sent to Steve Starsinic on

Compuserve, 71735-1660.

- 7 -

INSTALLATION/CONFIGURATION

Installing ^T

1. Make a subdirectory for the ^T files:

Type  'MD\^T'  and press enter

2. Make this directory the default directory:

Type  'CD\^T'  and press enter

3. Copy the ^T files.  In the following commands, if you are

not installing the files from drive A, substitute your

drive letter:

Type  'COPY A:^T.EXE'  and press enter

Type  'COPY A:^T.CFG'  and press enter

Type  'COPY A:*.DRV'   and press enter

4. Start the program:

Type  '^T'  and press enter

Configuration

1. ^T is pre-configured for color monitors.  If you have a

monochrome monitor, press 'CV' to select Configure-Video.

At the Mode field, type 'M' to select monochrome, and press

'F2'.

2. Type 'CD' to select Configuration-Default Calendar.

Enter all info (working days, hours per day, and holiday

dates).  Press 'F2' when finished.

4. Type 'CG' to select Configure-General Defaults.  Tab to

Printer Driver, and select one of the pre-built drivers.  If

your printer is not included in the set of printer drivers,

select GENERIC driver.  Drivers can be modified and renamed

later.  Press 'F2' when finished.

Other customizations are available, but these are all that are

necessary to get started.  Changes are automatically saved when

you press F2.

- 8 -

HOW TO USE ^T

SUMMARY

The intent of ^T is to give you constant feedback on the status

of your current workload.  It does this by telling you, at any

given time, how much work remains for each task.  In a ^T task

outline, resources are responsible for tasks.  Tasks are assigned

to resources.  Tasks are listed in outline form beneath their

assigned resources.  The Start Date of the first task is the date

that comes from the Start Date field in the resource record.  The

End Date of the first task is determined by adding the time

REMAINING in the task to the start date.  Note the emphasis on

the word "remaining".  Even though ^T stores the number of

working hours actually worked so far, the Start and End dates

shown in the outline represent how much work you have remaining.

The Start Date for the resource is important.  The normal routine

you should follow in updating your outline is to periodically

(e.g. once per week) update all the tasks currently assigned to a

given resource as to hours spent and percentage complete.  Then,

change the resource Start Date to the date you updated the

information.  In this way, ^T is able to tell you your remaining

workload AS OF THE LAST DATE YOU UPDATED THE INFORMATION.  You

continue in this way, completing and deleting tasks, adding new

ones, reassigning, and rearranging as necessary.

The following topics lead you logically through the steps

necessary to build an outline and perform periodic maintenance.

EDITING THE CUSTOM CALENDAR

The Custom Calendar establishes which days of the week are

working days, the number of hours in a working day, and scheduled

Holidays.  You access the custom calendar by selecting Edit from

the main menu and Calendar from the edit menu.  Complete the data

entry form, and press F2 to save.  All ^T data entry screens are

saved with F2 and canceled with Esc.

EDIT FILE NAME

Before an outline file can be saved it must first be given a

name.  Select Edit from the main menu and File Description from

the edit menu.  You should enter a description of the outline

file, a path, and a filename.  The description will be used as a

header for all reports, so make it formal and relevant.

ADD RESOURCES

- 9 -

Before any tasks can be added, you must add at least one

resource.  In most cases a resource is a person.  Add resources

by pressing 'AR' to bring up the Resource Details screen.

The Name is simply a long name or description of the resource.

The Label field should be a recognizable short description of the

resource.  The Label field is important in that this field is

used as an index to the resource.  An entry is required and must

be unique from every other resource label.

The Start Date of the resource becomes the Start Date of the

first task assigned to that resource.  When setting up a ^T

outline for the first time, you will normally use the current

date.  However, this date is intended to be changed regularly.

The intent of ^T is to show you the amount of work remaining in

the tasks, not the past work already done (although it stores

this information).  Because of this, every time you update task

information, the resource Start Date should be set to the date

the task info was updated.

The Number field is optional and can be used for any purpose.

The Hr. Rate is used to calculate the costs for all tasks linked

to this resource.  If you're not interested in tracking costs,

you don't have to enter a rate.

The Unscheduled task description and hours fields are critical to

accurate scheduling.  In this area, you account for the fact that

people engage in activities (both work and non-work) that cannot

practically be planned into a formal schedule.  Use as few or as

many lines as required.  On each line, enter a description of the

"activity" that contributes to the reduction of efficiency for

formally scheduled tasks.  Categories might include

"Supervisory", "Administrative", "Phone interruptions", and "Non-

Work Activities".  For each category, enter the number of hours

per week spent on that activity.  As each amount is entered,

you'll see the Total and the Scheduled Task Efficiency changing.

The Scheduled Task Efficiency is used to translate the working

hours required to perform a task into realistic calendar

durations.

You can add all resources at one time, or add them as needed.

ADDING TASKS

Access the Task Details (Add) screen by pressing 'AT' (Add-Task).

The Description is just that - a description of the task.

The Label, Number, and Classification fields are optional and may

be used for any purpose.  However, the intent was to provide a

field for a very short task description (Label), a place to store

- 10 -

a task identification number (Number), and a categorization of

the task (Classification).  The label and number fields are free

form.  The classification field is completed by selecting from a

pop-up, pre-defined table of classes (user-customized via the

Configure menu).

The Resource field is used to link the task to a resource.  It

will default to the resource that is "current" in the outline,

but the task can be assigned (at any time) to any other resource

simply by selecting the desired resource from the pop-up table.

The Project field is used to link the task to a project.  In this

discussion we haven't mentioned projects yet, but tasks can be

linked or unlinked to projects at any time.  Projects are

discussed below.

The Chargeback field is optional and can be used for any purpose.

However, it was provided because many users work in companies in

which service departments (e.g. Data Processing) charge costs

back to production departments.  This field allows you to record

a chargeback label or code.

The Priority can be set from 0 to 99.  0 is highest priority, 99

is lowest.  The priority defaults to the midpoint of 50.

Priority can be used to "break the tie" when one (or more) tasks

are more important than others and you want to be warned if,

during "what-if" rearranging, you violate that priority.

The Commit Date is the date by which the task must be completed.

Note that it is an optional field.  However, if you have a "must

complete by" date, it can be entered in this field.  If at any

time the task's calculated End Date falls after the Commit Date,

you will be warned.

The Adjust Working Hrs field defaults to YES.  For most tasks,

the default will be correct.  This means that we want ^T to

adjust the working hours for the "unscheduled tasks" performed by

this resource.  We would use "NO" for tasks like Travel and

Training where the duration and the actual working time are

equal.

The Date Entered field is normally left defaulted to today's

date.  Date Entered is used only to determine a task's age (how

long it's been on the schedule).

The final field to add a task is Estimated Working Hours to

perform this task.  Enter the expected number of working hours to

complete the task.  Enter Working hours,  not the span of time,

or duration, you expect it to take on a calendar.  It is ^T's job

to figure out the duration of the task.

As with every other data entry screen, press F2 to save it.

- 11 -

Each time you enter a task, a number of other fields are

automatically calculated, including date and cost fields.  To

immediately see these fields, simply press Enter.

CONFLICTS

As you add tasks, you may start to see the characters 'C', 'P',

or 'A' appear in the screen immediately to the left of the task

line.  The word "Conflict" will also be highlighted on the bottom

status line.  These represent Conflict warnings.  If 'C' appears,

it means that the calculated End Date for the task has exceeded

the Commit Date.  If 'P' appears, it means that this task appears

in the outline before a task with a higher priority.  If 'A'

appears, it means that the age of the task exceeds the warning

level set in the Configure-General Defaults screen.

REMOVING CONFLICTS

Commit Date Conflicts.  One approach is to move the task to a

position in the outline in which the calculated End Date no

longer exceeds the Commit Date.  You can do this by moving the

pointer to the task, and pressing 'RM' (Rearrange-Move).  You can

then use the arrow keys to move the task up or down in the

outline.  As the task moves, the dates are automatically

recalculated, and the 'C' warning will clear if the conflict

corrects itself.  Another alternative is to change the Commit

Date.  Either rearrange your business affairs so that a later

date is acceptable, or remove the date altogether if the commit

date is not really necessary.  Next, you could assign the task to

another resource whose schedule would allow the task to be

completed on time.  Lastly, you could change the resource's

unscheduled time to allow for more task time.  However, this can

be dangerous.  If you change the person's unscheduled time, you

must make sure that you arrange your business affairs so that the

reduced unscheduled time can be made a reality.

Priority Conflicts.  There are only two ways to remove a priority

conflict.  First, rearrange the tasks so that higher priority

tasks (lower numbers) precede lower priority tasks (higher

numbers) in the outline.  The other is to change the priority

numbers so that there is no conflict.

Age Conflict.  Age conflicts only occur on Active tasks (tasks

whose Status fields are marked Active).  You can remove the age

warning for an individual task by marking the Status field as

Inactive (in effect, saying "this is on hold, I don't care how

old it is).  Alternatively, you could raise the Age Warning Level

in the Configure-General Defaults screen to a very high number

like 999.  However, this action would turn off the age warning

feature globally (for all tasks).

- 12 -

EDITING TASKS

Tasks can be edited at any time.  All task fields except

calculated fields, Date Entered, and Est. Working Hours may be

modified.  To edit a task, you must first highlight it with the

outline pointer and either (1) press Enter, or (2) press 'ET'

(Edit-task).

EDITING RESOURCES

Resources can be edited at any time.  All resource fields except

calculated fields may be modified.  There are 3 ways to trigger

resource editing.  First, if the outline pointer is positioned on

a task, press 'ER' (Edit-resource) to start data entry for the

resource to which the task is assigned. Next, if the outline

pointer is positioned on a resource, either press Enter or press

'ER' (Edit-resource).

ADDING AND USING PROJECTS

Project records are used to summarize the data from several

tasks.  You must first add the project, and then link tasks to

the project.  A project record is added by typing 'AP' (Add-

project).  You must add a Description and a Label.  The label, as

with resources, is used as an index to the project record.  It

must be present and it must be unique among all project labels.

The Number and Commit Date fields are optional.  However, if a

Commit Date is entered for a project, that Commit Date is also

imposed on any tasks linked to the project in addition to the

task's own Commit Date.

You'll notice at first that the project record doesn't appear in

the outline.  You can only see projects if the outline is placed

into project mode.  Do this by entered 'RP' (Rearrange-Project).

The project will now appear as the top level item in the outline.

Since no tasks will be linked, they (and all their resources) are

included under the project heading "all other not linked".  The

^T outline may be switched back and forth from resource to

project outline modes by typing 'RR' and 'RP'.

To link tasks to the project, simply edit each task, Tab to the

Project field (which will no longer be skipped over since a

project exists), and select the project from the pop-up table.

Not only will the tasks appear in the project mode outline under

that project, but it's data will appear in the project summary.

To view the project summary,  edit the project record and look at

the calculated fields.  The project Start Date is the earliest

Start Date for any task linked to the project.  The End Date is

the latest End Date for any task linked to the project.  The

- 13 -

costs are all sums of the costs for all the tasks linked to the

project.

OUTLINE MAINTENANCE

It is expected that, at routine intervals, the data in the

outline will be updated.  This would occur, for example, as a

result of a weekly status meeting.  This maintenance is performed

in the following steps.

1. Update each task to reflect current Act. and O.T. hours worked

on the task.  These would be cumulative numbers.  Also, update

Percent Complete.

2. Add new tasks that have been assigned since the last update.

3. Delete old tasks that are now 100% complete.

4. For each resource for which you have updated task information,

update the Start Date.

When these 4 steps are completed, you will see an automatically

recalculated, date-adjusted, new schedule of the remaining work.

You are also gradually accumulating incurred time and cost

information.

Each week (or other adjustment interval) new conflicts may arise.

You'll have to deal with them by rearranging positions, changing

Commit Dates or Priorities, etc.

DELETING TASKS

A task is deleted by pressing 'DT' (Delete-task).  You will be

asked if you want to Archive or Discard the task.  Archiving mean

that the record is written into an archive file and deleted from

the outline.  See the ^T Reference for details on the archive

file.  Discarding means to simply throw the task away, deleting

it from the outline file.  NOTE: In this version, ^T provides no

means to access the Archive file.  The record layouts for this

file are documented in the ^T Reference for those who which to

design their own access facility.

When deleting a task, you may be given a warning that the task is

linked to a project.  You are warned because, if the task is

deleted, its data will no longer be included in the project

summary.  When tasks are linked to projects, it is recommended

that they be marked 100% complete and left in the outline.  That

way their data will be included until all tasks are finished and

the project record is complete.

DELETING PROJECTS

- 14 -

A project is deleted by pressing 'DP' (Delete-project).  You will

be asked if you want to Archive or Discard the project.

When deleting a project, you may be given a warning that there

are still tasks linked.  If it is indeed your intent to delete

the project, the tasks will be automatically unlinked but will

otherwise be intact.

SAVING THE FILE

Your file can be saved at any time by typing 'FS' (File-Save).

CUSTOMIZING THE OUTLINE DISPLAY

The outline may be displayed in either resource mode or project

mode.  In addition, each of the three record types (resources,

tasks, and projects) may be customized as to the fields that are

displayed in the outline.  This is done by entering the Configure

menu, and selecting either Task Fields, Resource Fields, or

Project Fields.  Then enter 'Y' for each field you want to

display and 'N' for fields you want to hide.

PRINTING REPORTS

In this version, ^T prints 3 basic reports.

For all reports, the fields that are printed are the fields

marked with a 'Y' on the configuration screens and currently

visible on the screen.  This gives you a lot of variation as to

what appears in the report.

The Outline report is simply a continuous listing of the outline

currently displayed.

The Resource Assignments report prints each resource on a

separate page with only the tasks assigned to that resource.  You

can choose the resource to print or print all of them at once.

The intent of this report is to provide hand-out assignment

sheets to individual workers.

The Project Assignments report prints each project on a separate

page with only the resources and tasks for that project.  You can

choose the project to print or print all of them at once.

You can also print data into a print file or into an ASCII data

file.  A print file is simply a text image of how the report

would have printed, minus the printer control codes.  This file

can be loaded into a word processor, text editor, or even a

spreadsheet to be modified by the user.  The ASCII data format is

designed for access by other programs.  See the ^T reference for

details.

- 15 -

QUESTIONS AND ANSWERS

Here is a list of actual users' questions with the answers

provided.

Q. How do I handle employees' vacation time?

A. There are a couple of approaches.  First, if your

establishment has regular planning periods, you might want to

average the vacation into the unscheduled tasks for each

resource during the planning stage, and then remove it after

the schedule is set.  When vacation is actually scheduled,

enter it as a task, with a Commit Date set to the last

scheduled vacation day, and Adj Working Hours set to 'NO'.

Q. What items should be included in the resource Unscheduled

Tasks area?

A. The rule of thumb is to include any activity that is not

likely to be added to the outline as a task.  Also, be honest.

Many people are slightly shocked when they first realize just

how much unscheduled time there really is.  A "working

supervisor" (a supervisor who is also expected to do 'work',

and a common denizen of the modern business office), may

actually have only 10% to 20% of his or her schedule available

for scheduled tasks.

Q. How do I use the Adj Working Hours field?

A. Much of the inaccuracy in date scheduling arises from

confusing the hours spent actually working on a task with the

hours that pass on the clock.  For example, a person who is

frequently interrupted may require 8 hours on the clock to

perform 2 hours of actual work on a task.  ^T attempts to

alleviate the confusion by automatically adjusting the working

hours to clock hours in the schedule.  However, there are

activities which do take place in an uninterrupted manner,

such as Travel, Classes, Vacation, etc.  To have ^T do the

adjustment from working hours to clock hours, set Adj Working

Hours to YES.  For activities that are uninterrupted, set it

to 'NO'.

Q. What is happening when I have a Commit Date conflict on a task

that does not have a Commit Date and/or is obviously not in

conflict with it's End Date.?

- 16 -

A. The task is probably linked to a project that does have a

Commit Date, and the task End Date is in conflict with that

date.

Q. I keep getting Commit Date conflicts on tasks that are marked

100% complete.?

A. If the task is complete and you want to leave it in the

outline, delete the Commit Date.

Q. Is there a way to assign multiple resources to the same task?

A. No.  If two or more resources are working on the same task,

break the task down into two or more task records with a piece

assigned to each resource.

Q. Can I force a task to start on a specific date?

A. No.  For now, we recommend the following procedure.  Enter a

dummy task before the subject task to push the back task to

the desired Start Date.  Then enter the calculated End Date

into the Commit Date field.  Finally, delete the dummy task.

Now, if the task slides past that Commit Date, you'll be

warned.

- 17 -

FUTURE VERSIONS OF ^T

The following changes are under consideration for future versions

of ^T.

- The ability to make temporary configuration changes.

- Search capability

- Zoom feature (e.g. treat a resource as though it is the

entire outline).

- True 4-directional field-to-field cursor movement during

data entry.

- Have a calendar for each resource (to facilitate part time

employees, etc.).

- Ability to move resources and projects.

- Print to structured outline file.

- Add a field to each record to indicate when last updated.

- Provided a facility for accessing Archive files.

- Performance improvements

We would appreciate any feedback on these or any other

recommendations for improvement.

- 18 -

^T REGISTRATION FORM

Please complete this form and send it with the $35.00

registration fee to the address below.

Name____________________________________________________________

Company_________________________________________________________

Shipping Address________________________________________________

Mailing Address_________________________________________________

City______________________________State_____Zip_________________

^T Version Number_______________________________________________

Computer Make/Model_____________________RAM Installed___________

Diskette Size:  3 1/2_______     5 1/4_______

Where did you acquire ^T?_______________________________________

Comments/Suggestions

________________________________________________________________

________________________________________________________________

________________________________________________________________

________________________________________________________________

________________________________________________________________

________________________________________________________________

Send to

Steve Starsinic

7 Dorchester Road

Hummelstown, PA 17036

- 19 -

----------------end-of-author's-documentation---------------

Software Library Information:

This disk copy provided as a service of

The Public (Software) Library

We are not the authors of this program, nor are we associated

with the author in any way other than as a distributor of the

program in accordance with the author's terms of distribution.

Please direct shareware payments and specific questions about

this program to the author of the program, whose name appears

elsewhere in  this documentation. If you have trouble getting

in touch with the author,  we will do whatever we can to help

you with your questions. All programs have been tested and do

run.  To report problems,  please use the form that is in the

file PROBLEM.DOC on many of our disks or in other written for-

mat with screen printouts, if possible.  The P(s)L cannot de-

bug programs over the telephone.

Disks in the P(s)L are updated monthly, so if you did not get

this disk  directly from the P(s)L,  you should be aware that

the files in this set may no  longer be the current versions.

For a copy of the latest monthly software library newsletter

and a list of the 2,000+ disks in the library, call or write

The Public (Software) Library

P.O.Box 35705

Houston, TX 77235-5705

(713) 524-6394