�������������������������������������������

���������

�       �             �              �    �

�       �                            �  ���

�       �   �    �    �    ������    ����

�     � �   �    �    �    �         � ���

���������   ������    �    ������    �   ��

�

���������

�                               �       �

�                             �����   �����

�      ��   ������   ������     �       �

�       �   �    �   �    �     �       �

���������   ������   �    �     �       �

�������������������������������������������

A  Project  Scheduling  Tool

By  L. Varga

Copyright(c) 1987,88

Release  2.0

Release 2.0

Table of Contents

Section

Introduction .  .  .  .  .  .  .  .  .  .  1

System Requirements   .  .  .  .  .  .  .  2

Overview of Quick Gantt  .  .  .  .  .  .  3

Screen Fields   .  .  .  .  .  .  .  .  .  4

Menu Commands.  .  .  .  .  .  .  .  .  .  5

Key Commands .  .  .  .  .  .  .  .  .  .  6

Messages  .  .  .  .  .  .  .  .  .  .  .  7

Quick Gantt Tips.  .  .  .  .  .  .  .  .  8

page 1-1

Introduction

------------

���������������������������������������������������������ͻ

�                                                         �

� Quick Gantt is a project scheduling tool that makes it  �

� easy to create and maintain Gantt charts. It is         �

� available in two sizes and two prices. The small version�

� which handles up to 50 tasks is available for FREE where�

� you find it ( BBS, a friend and Shareware outlets have  �

� it). The large version which handles up to 500 tasks is �

� available for $20 from me along with support.           �

�                                                         �

� L. J. Varga                                             �

� 18725 S. E. 43rd St.                                    �

� Issaquah, WA. 98027                                     �

���������������������������������������������������������ͼ

Just a Quick Note from the Author

The reason I created QG was probably for the reason you are looking at

it.  I didn't need a $400 project manager. All I wanted to do was

determine the end date of a project allowing for weekends, holidays,

etc. I also wanted to add, delete and change tasks and get a quick

answer.  I am working to improve Quick Gantt and the copy you purchase

will no doubt be improved. I am trying to include your suggestions as

they come.

I have discovered that I can improve the appearance of the printed

chart by simply altering a few character fonts on the printer. The

result is a is solid black bar for completed tasks and a white bar for

the incomplete portions.  I intend to proved my font set for the HP

Laser Jet Series II and plan to have a set for the Epson (or

compatable) too.

OK now to Quick Gantt ............

The Gantt chart is a popular way of displaying schedules.  It is

constructed with a calendar on the horizontal axis and a list of

events or tasks on the vertical axis. The duration of the task is

shown as the horizontal line.  The Gantt chart tends to have a

stepped or 'waterfall' appearance as the tasks go down the side and

the duration line moves further to the right.

Calendar(time) ---->

Tasks

1         ----------

2                   ---------

3                            ----

4                                -----

page 1-2

Another tendency is for many of the tasks to be dependent upon one

another.  The second task often must wait for the first task to be

completed before it can start.  This dependency can be useful in

constructing the chart.  For example, if one knows when Task 1 is to

begin and its flow time (duration) and that Task 2 begins with the

end of Task One and that Task 3 begins with the end of Task 2, etc.,

all that is required to build dependencies in the chart is to know

when Task One starts, the flow time of each task and the order of

task execution.  If Task One is delayed then the second is also

delayed. As a result the chart can be thought of as a series of

dependencies.

Gantt charts are popular for project control because they are easy to

construct and graphically show the tasks, their dependencies and

their durations.  As a task is worked or completed it is often

'colored' in to more easily display project status at any point in

time.

Some scheduling programs account for resources, cost and other

items.  But in most projects the schedule is the overriding concern.

The need then is for a simple tool that can depict tasks, their flow

time and their relationships, thereby providing an overall view of

when each task of a project is predicted to occur.

The objective of Quick Gantt is to rapidly create, maintain and print

a project schedule in the form of a Gantt chart.

page 2-1

System Requirements for Quick Gantt

-----------------------------------

-  IBM (tm) PC or compatible

-  DOS 2.0+

-  Minimum of 140k of memory for the Small Version

and 300k for the large version. You can open

a shell to DOS but more memory will be necessary

to run programs or execute DOS commands.

-  Monochrome or color monitor

-  Printer with IBM (tm) extended character set

(for better visual appeal only)

This program has been designed to use the font

found on standard printers and requires no

graphics capabilities.

-  One disk drive but a fixed hard drive is better.

page 3-1

An Overview of Quick Gantt

--------------------------

Quick Gantt treats tasks in a schedule very much as a spreadsheet

treats cells.  Tasks can be set up as dependent on one another such

that if one changes, all dependent tasks are changed to agree.

Up to 500 tasks can be scheduled over any time span.  Weekends can be

included or excluded along with specific user defined holidays.  The

minimum increment of scale is one (1) day.  Tasks of less then one day

will appear as a one day flow on the Gantt chart.  The printed copy

can be up to 255 characters wide. Most of the Fields on the report are

optional, so only necessary data need be presented.

Quick Gantt creates and maintains a Gantt chart on the PC screen.

Each task requires only three pieces of data to create a useful

chart:

1.  A task number or name.

2.  The task duration or flow time in days.

3.  The identity of an absolute start date or the

preceding task upon which the task is dependent.

As a task is created or changed, the task duration will be displayed

as a bar in the chart portion of the screen along with other tasks and

their durations. In this way you can see the position of the task with

respect to both calendar dates and the other tasks.

Once the data has been entered the chart can be printed or sent to a

file where it can be edited for a report.

Once a report has been created the report titles and specifications

are saved with the file.

page 3-2

Input  Screen

The input screen is used to edit one task at a time. The top two rows

contain all the data about the task which has been selected for

editing.  The rest of the screen is a condensed Gantt chart which

displays this task and eleven adjacent tasks.  As you scroll or page

through the chart, the tasks and related information will appear for

editing in the top two rows of the screen.

�TASK�����������TITLE��������������������������������������RESPONSIBILITY��W�H�

�3             �Select a contractor                       �ME             �1�1�

�ESD��������FLOW�ECD��������%CM�FORMULA����������������������������������DEV�͹

�10/17/1988�30  �11/25/1988�33 �Begin with End of     2                 �-6   �

�����������������������������������������������������������������������������͹

�           YR �  1988                     1989                               �

�           MO �  Aug Sep  Oct   Nov  Dec  Jan  Feb  Mar  Apr  May  Jun  Jul  �

�           DA �  08 26 13 01 19 06 24 12 30 17 04 22 12 30 17 05 23 10 28 16 �

�����������������������������������������������������������������������������͹

�1             �  ====           .                                            �

�2             �      ======     .                                            �

�3             �             ==----                                           �

�4             �             =======------                                    �

�5             �                 .         ---------------------------        �

�5.1           �                 .         --                                 �

�5.1.1         �                 .         -                                  �

�5.1.2         �                 .          -                                 �

�5.1.3         �                 .          -                                 �

�5.1.4         �                 .           -                                �

�              �                                                              �

�              �                                                              �

�����������������������������������������������������������������������������ͼ

Line #  1 of   1

File: WORK.QG

page 3-3

Printed Report

The report is initiated from the menu.  The width of all the columns

is variable and optional. The report can be up to 255 columns wide and

can be formatted to fit all common sizes of printer paper.

As of 10/10/1988

�������������������������������������������������������������������������������

�                                                      My Project

�

�������������������������������������������������������������������������������

�      �                     �       �    �     1988                        198

�TASK  �TITLE                �RESPONS�FLOW�     Aug Sep   Oct   Nov   Dec   Jan

�������������������������������������������������������������������������������

�1     �Select the site      �ME     �20  �08/08     09/02 .

�      �                     �       �    �     =====      .

�      �                     �       �    �                .

�2     �Prepare plans        �Archati�30  �     09/05      . 10/14

�      �                     �       �    �          ======+-

�      �                     �       �    �                .

�3     �Select a contractor  �ME     �30  �              10/17        11/25

�      �                     �       �    �                .  --------

�      �                     �       �    �                .

�4     �Get financing        �ME     �60  �              10/17               01

�      �                     �       �    �                .  ---------------

�      �                     �       �    �                .

�      �                     �       �    �                .

�5     �Construction         �A&B Con�120 �                .             01/09

�      �                     �       �    �                .                  -

�      �                     �       �    �                .

�5.1   �Prepare the site     �       �12  �                .             01/09

�      �                     �       �    �                .                  -

�      �                     �       �    �                .

�5.1.1 �Notify the Utilities �A&B Con�2   �                .             01/09

�      �                     �       �    �                .                  -

�      �                     �       �    �                .

�5.1.2 �Clear the site       �A&B Con�3   �                .              01/11

�      �                     �       �    �                .                  -

�      �                     �       �    �                .

�������������������������������������������������������������������������������

This example is wider than shown and has been truncated on the right side.

page 3-4

Preparing for Quick Gantt

When planning a project, forethought must be given to the structure

and organization of tasks so that the project will become more

manageable.

The Gantt chart should be constructed to reflect the project and how

it will develop remembering that most projects are made up of many

small projects.

People generally find it natural to think in a structured "top down"

order.  They visualize the completed project in total then disassemble

it into its major components. Each major component is subdivided into

its components until the work is broken down into meaningful and

manageable tasks.  Quick Gantt is designed to utilize this work

breakdown structure (WBS).

It is not necessary to retain the higher level tasks to use Quick

Gantt but the intermediate tasks will provide more reporting

possibilities.

The Natural order is to start with the first task assign it a number

or identifier then get the next task(s) which immediately follows and

number it. In this way the Gantt chart will have a full left to right

and descending appearance. This is clean, neat and orderly and clearly

shows the dependencies of the tasks.  It is fine for small projects.

The Tiered WBS order is to assign each major task a number (or letter)

such as 2, 4A or B, then take each task and decompose it numbering

each as a subset of the parent.

Ex:  2.2 and 2.3 are under task 2.

Repeat this process until each task has a clearly defined action and

deliverable product.  Retain the intermediate tasks.

The WBS allows assignment of responsibility at a detailed level and

"rolling" the tasks up to be managed at a higher level.  The use of

this structure is not necessary when using Quick Gantt but doing so

allows reporting at various levels of detail depending upon the

management level to be addressed.  This structure creates extra tasks

but they can be self maintained by Quick Gantt (refer to "Formulas" in

the Screen Fields section). This structure also permits large charts

to be broken down into small ones for more effective tracking.  The

WBS method permits flexibility in the level of reporting detail.

Quick Gantt reports can be printed in either Natural or Work

Breakdown order.

page 3-5

Below is a graphical example of a task, 3, being sub defined like a

product structure. The lower level or 'Tier' is identified by a

decimal system  where the task takes the numerical name of its parent,

then identifies itself by adding a decimal (.) and a character.

Example

If 3 is a task then 3.1 and 3.2 are a subset of 3.  3.1.1 and

3.1.2 are a third level tier of 3. In this way a schedule and

responsibility can be assigned with a separate schedule, yet the

schedule supports the total project.

Quick Gantt identifies tiers in the schedule by a decimal point.

The Natural Gantt chart can become too large with too many tasks

to efficiently track progress and can become cluttered with

irrelevant tasks when there are many responsible participants.

Natural Order

������������������������������������������ͻ

�       �3/3   4/6                         �

� 1     �   ---                            �

�       �  4/7        6/16                 �

� 2     �      -------                     �

�       �         6/17       8/10          �

� 3     �             -------              � <--

�       �         6/17   7/1               �

� 3.1   �             ---                  � <--

�       �         6/17 6/20                �

� 3.1.1 �             -                    �

�       �          6/21  7/1               �

� 3.1.2 �              --                  �

�       �             7/2    8/10          �

� 3.2   �                ----              �

�       �                                  �

������������������������������������������ͼ

Tasks 3 and 3.1 are not necessary since they are simply higher levels

of task 3.2, 3.1.1 and 3.1.2.

page 3-6

Tiered - Work Breakdown Structure

������������������������������������������ͻ

�       �3/3   4/6                         �

� 1     �   ---                            �

�       �  4/7        6/16                 �

� 2     �      -------                     �

�       �         6/17       8/10          �

� 3     �             -------              �

����������������   /           \ ���������ͼ

/                  \

/                         \

/                                \

/                                       \

������������������������������������������ͻ

�       �         6/17       8/10          �ͻ

� 3                   -------           <-------- 3 is a summary

�       �         6/17   7/1               � � �  rollup of any

� 3.1              /  ---                  � � �  3.**** task.

�       �       /         \                � � �

� 3.2   �    /              \              � � �

������    /                   \�����������ͼ � �

���  /                        \�����������ͼ �

/                              \����������ͼ

/                                    \

������������������������������������������ͻ

�       �         6/17   7/1               �ͻ

� 3.1   �             ---         <------------- 3.1 is a summary

�       �         6/17 6/20                � �   rollup of any

� 3.1.1 �             -                    � �   3.1.**** task

�       �          6/21  7/1               � �

� 3.1.2 �              --                  � �

������������������������������������������ͼ �

������������������������������������������ͼ

page 4-1

SCREEN  FIELDS

----------------

This section will describe the use and purpose of the fields on the

screen. To move between screen fields, use the tab key to advance

right or (shift + tab) to move left.

Field Name:    TASK

Purpose:       To provide a unique alphanumeric identity for an

event.

Restrictions:  This is a required field. Any character is valid. One

to 14 characters may be used. Although there is no

restrictions to task identifiers Quick Gantt has

features that use a decimal work breakdown structure.

This means the major task is identified by a character

(Ex: 32 ) and as the task is broken down is components

take the parents Id. (Ex: 32.5)

How to use:

2       Major Task

�TASK�����������TITLE�����     2.1     Sub Task of 2

�2.1           �                 2.1.1    Sub Task of 2.1

�ESD��������FLOW����ECD���       2.2.2    Sub Task of 2.1

2.2      Sub Task of 2

Enter any character or number. The task can be a number or

name.

Ex :  1

Start

1-st

Tasks must always be referenced using exactly the format

that was initially used.  Task dependencies are based on

correct labeling.

Ex:

'First-Task'is not the same as 'first-task'.

Although there are no restrictions on the task name, it is

worth giving thought to the level of detail that will

ultimately be incorporated into the schedule.  For example

if you plan to build a new house you might set tasks such

as:

1   select site

2   have plans drawn

3   select contractor

4   get bank loan

5   start construction

page 4-2

These tasks are quite broad and their duration may be too

lengthy for good control.  It is then necessary to break

down these tasks to a lower level:

5 Construction

5.1   prepare the site

5.2   frame

5.3   finish exterior

5.4   finish interior

Even at this level many important tasks are not identified

so further breakdown may be necessary:

5.1   prepare the site

5.1.A   notify the utility companies

5.1.B   clear the site

5.1.C   dig to foundation level

5.1.D   provide utility access

Field Name:   TITLE

Purpose:      To provide a description of the event.

Restrictions: This field is not required.  Any alphanumeric character

is valid.  1 to 42 characters may be entered.

How to use:

�������TITLE���������������������������������������RESP

�Grade building site  to foundation level   �

���FLOW����ECD��������FORMULA��������������������������

Enter the title of the task, splitting the title at the

hash mark, if desired.  When the TITLE column of the

chart is printed, up to 21 characters of the title will

appear on the first line with up to the remaining 21

characters appearing on the second line.  The hash mark

indicates the start of the second line.

page 4-3

Field Name:   RESPONSIBILITY

Purpose:      To identify the person or group responsible for

completing the task.

Restrictions: This field is not required.  Any alphanumeric character

is valid.  1 to 18 characters may be entered.

How to use:   Enter the name, title or description that is to assume

responsibility for the task. This might also be used to

identify resources.

����������RESPONSIBILITY��W�H�

�A&B Constructio�1�1�

������������������������DEV�͹

ESD, FLOW and ECD

Many factors influence the timing of tasks but there are two basic

approaches. The first is to establish a starting date for the first

task, specify the sequence in which all tasks will occur and provide

the flow time or duration of each.  Then it is a simple process to

'draw' the chart.  When the flow time of any task changes all

dependent tasks are changed to agree.

The second approach is to establish absolute fixed start and

completion dates. The flow time is calculated to be the number of work

days between these two dates.

Both approaches can be accommodated when using the next three fields:

ESD,FLOW and ECD.  The user must choose to establish the flow time and

let the estimated start and completion dates 'float' or to input

firmly 'fixed' the start and completion dates. Depending upon this

choice either the FLOW time field or the ESD/ECD fields will be used

but not both.

page 4-4

Field Name:   W (Workday Schedule)

Purpose:      To define which of five (5) possible workday schedules.

is used to calculate the beginning or end dates of a task.

The default is schedule 1.

Restrictions: Must be a number between 1 and 5.

����������RESPONSIBILITY��W�H�

�               �1� �

������������������������DEV�͹

Field Name:   H (Holiday Schedule)

Purpose:      To define which of three (3) possible holiday schedules.

is used to calculate the end dated of a task.

Restrictions: Must be a number between 1 and 3.

����������RESPONSIBILITY��W�H�

�               � �1�

������������������������DEV�͹

Field Name:   ESD (Expected Start Date)

Purpose:      To define the date a specific task is expected to begin.

Restrictions: Must be a valid date.

�ESD��������FLOW�ECD��������%CM�FORMULA��

�09/16/1986�    �          �   �

�����������������������������������������

This field can  only be reached if 'Fixed Esc/Ecd'

appears in row 24 of the screen.  It is used when

flow is not as important as firm ESD's and ECD's.

See page 26 on key F6.

In all other instances in which it is dependent upon

another task's schedule before this task's schedule can

be established this date is calculated by formula.  It

is calculated from the beginning or end of a parent or

driving task.

As with all fields in which a date is entered, if the

year is excluded then it is assumed to be the current

year.

page 4-5

Field Name:   FLOW

Purpose:      To define the duration of a task.

Restrictions: This field is required unless using the fixed ESD/ECD

option.  6 numeric characters may be entered.

How to use:

�ESD��������FLOW�ECD��������%CM�FORMULA��

�          �23  �          �   �

�����������������������������������������

FLOW is the expected duration of the task in days.  Only

whole days can be entered, not fractions.  It is not

necessary and in fact not desirable to include weekends

and holidays in the flow time. These non-workdays will be

dealt with in the CALENDAR section . The

flow time should be thought of as net work days to

perform the task.

Field Name:   ECD (Expected Completion Date)

Purpose:      To define the date a task is expected to complete.

Restrictions: Valid date

How to use:

�ESD��������FLOW�ECD��������%CM�FORMULA��

�          �    �10/04/1986�   �

�����������������������������������������

This field is the date the task will end and is calculated

from the start date plus flow.  Normally this field is not

used  and the cursor will jump over it.  However, when the

fixed ESD/ECD mode is used this field must be completed.

page 4-6

Field Name:   %CM (Percent Complete )

Purpose:      To define the amount of the task that has been

completed.

Restrictions: A numerical value between 0 and 100.

How to use:   Determine the actual portion of the task that has

been completed. This should be a percentage of the

effort required.  Zero (0) if the task has not been

started and 100 if the task is complete. An internal

progress date is calculated.

�ESD��������FLOW�ECD��������%CM�FORMULA����

�          �    �          �22 �

�������������������������������������������

page 4-7

Field Name:   FORMULA

Purpose:      To establish the start or end dates of a task. To

create dependencies between tasks. To enter an

informational note.

Restrictions: Required. See complete instructions below.

How to use:

The formula performs one of four functions for any given

task:

1.  To set an absolute start or end date to a task.

2.  To set up the dependencies between tasks

3.  To summarize or 'rolls up' a group of tasks.

4.  To create a note or information line.

In addition the formula field is made up of four

sub-fields.  It is necessary to enter data into one or more

of these sub-fields to perform each of the functions.

1.  Set an absolute start or end date to a task.

If the task is to begin or end on a specific date, then in

the first position  of the formula field enter a 'B' when

meaning the task beginning or a 'E' when meaning a task

ending.  The first sub-field will be filled with 'Begin

with' or 'End with' then the cursor will move to the second

sub-field.  In this field enter the date that the task is to

begin or end.  The date is entered as month / day /year.  A

slash (/) or dash (-) is required between numbers.

�����%CM�FORMULA�����������������������������������DEV�͹

�   �Begin with 7/14/86                       �     �

�������������������������������������������������������͹

Press the return key and if no errors appear, the task,

title and its' associated scale line will be displayed in

the chart section of the screen.

The formula will read :

(This task will)   END WITH   (the date)   7/4/86

or (This task will)   BEGIN WITH   (the date)  7/4/86

page 4-8

2.  Set up the dependencies between tasks

As with setting an absolute date (above), in the first

sub-field enter a 'B' meaning 'begin with' or an 'E' meaning

'end with'.  When the cursor moves to the second sub-field

again choose "B" if the task is dependent upon the beginning

of another task or "E" if it is dependent upon the end of a

task. The sub-field will be filled with "Begin of" or "End

of". The cursor will move to the third sub-field where the

parent task is entered.

end of the

independent task >|

A.1             ------------

B.1                          ----------

| > beginning of the

dependent task

Formula for task B.1

�����%CM�FORMULA�����������������������������������DEV�͹

�   �Begin with End of     A.1                �     �

�������������������������������������������������������͹

The cursor can then be tabbed to the fourth field where an

adjustment in days can be entered. The purpose of the

adjustment is to shift the beginning or ending of the

dependent task.  For example this task may begin 5 days

before its parent task ends.

end of the

independent task >|

A.1             ------------

|     |

adjustment of  |     |

5 days    |     |

B.1                   |----------

| < beginning of the

dependent task

Formula for task B.1

�����%CM�FORMULA�����������������������������������DEV�͹

�   �Begin with End of     A.1           -5   �     �

�������������������������������������������������������͹

page 4-9

With these choices a number of task relationships can be

created so that a formula now reads something like:

(This task will)   BEGIN WITH  (the)   END OF  (task)  1.a

start when the first ends

or (This task will)   BEGIN WITH  (the)  BEGIN(ning) OF  (task)  1.a

start when the first starts

or (This task will)   END WITH  (the)   END OF  (task)  1.a

end when the first ends

or (This task will)   END WITH  (the)  BEGIN(ning) OF  (task)  1.a

end when the first starts

Using the adjustment field :

(This task will) BEGIN WITH (the) END OF  (task)  1.a  (plus) 5 (days)

start 5 days after the first task ends

3.  Summarize or 'roll up' a group of tasks.

The formula field can also be used to display a 'summary'

bar. Often it is useful to include in a Gantt chart a higher

level summary bar which represents the total time required

to complete a group of related lower level tasks.

Since the summary task is made up of all the detailed tasks,

when one of the detail tasks changes, the summary task

changes accordingly.  Quick Gantt allows the creation of tasks

which are not individually scheduled but picks up the

schedule for a group of tasks.  In this way the summary

level schedule is maintained.

Entering 'S' in the first position of the first sub-field

will fill the sub-fields one and two with 'Summary   Level

of  ' and then move the cursor to sub-field 3 for a task

mask.  The mask must end with '.*'.   The character string

before the .* is used as a constant so that any task with

this string is included in the 'roll up'.

�����%CM�FORMULA�����������������������������������DEV�͹

�   �Summary    Level   of 1.a.*              �     �

�������������������������������������������������������͹

page 4-10

In the above example any task with '1.a.' in the first 4

positions will be "rolled up" into this task so the flow

days for the summary task will be calculated for the range

of all these detail tasks.

��������������������������������������������������������

�1.a           � -----------------

�1.a.1         � ------

�1.a.b         �               ---

�1.a.2         �       ---------

�1.b.1         �                ---------

��������������������������������������������������������

Note that 1.b.1 was not included in the roll up.  As the

duration of any task with a '1.a.' in the first 4 positions

is changed, the roll up bar '1.a' will change. A

recalculation is usually necessary.

4.  Create a note.

Occasionally a task is known to be required but the flow,

time start date or dependency is not known at the time the

Gantt chart is created. In this case it may be desirable to

enter a note of explanation or status on the chart so the

task is not forgotten and can be completed when all the

information is available.  The formula field permits this by

starting the formula with a double quotation mark (") then

using the next 43 characters in the formula field to enter

an explanatory note into the chart.

This field can also be used without a task label to provide

descriptive breaks in the chart.

�����%CM�FORMULA�����������������������������������DEV�͹

�   �"Awaiting estimate from engineering      �     �

�������������������������������������������������������͹

������������������������������������������������������������

�1.a           � -----------------

�2.            � Awaiting estimate from engineering

������������������������������������������������������������

page 4-11

Summary of Formula constructs:

field 1   | field 2  |  field 3    | field 4

|          |             |

�����%CM�FORMULA����������������������������������������͹

�   �Begin with End of     4.3.1         5     �     �

��������������������������������������������������������͹

Begin with Begin of  task #         +- adjustment

days

End with   End of

MM/DD/YY

Summary    Level  of task #.*

" text ----------------------------------->

Field Name:   DEV (Deviation from schedule)

Purpose:      To define the number of work days the task is

ahead (+) or behind (-) schedule.

Restrictions: This field is calculated no entry is permitted.

How to use: This field is calculated from the percentage complete

(%CM) field. The current date is then subtracted from

the progress date.

�%CM�FORMULA�����������������������������������DEV�͹

�   �                                         �-7   �

���������������������������������������������������͹

page 4-12

Field Name:   Scale

Purpose:      To display the dates of the tasks.

Restrictions: The Quick Gantt chart is always shown in a 60 character

field on the screen with the minimum increment being one

day.

How to use:

��������������������������������������������������������������

�           YR �  1987                    1988

�           MO �  Nov     Dec             Jan            Feb

�           DA �  15 21 27 03 09 15 21 27 02 08 14 20 26 01 07

��������������������������������������������������������������

The scale is made up of three lines. The first shows the

year, the second the month (abbreviated) and the last

displays the day. The scale is calculated with the first

date entry.  As tasks are added the scale will change to

show the duration of all tasks currently entered into the

Gantt chart. If a task is deleted or shortened the scale

line will not change until the entire chart is

recalculated.  The scale will never be less the one day per

scale column but it can be can compressed so a column can

represent several days. As seen in the above example each

column represents 2 days.

page 4-13

Field Name:   Chart

Purpose:      To provide a visual display of task durations

Restrictions:  The chart cannot be directly accessed but is

the graphic result of the formulas and input in the

first two lines of the screen.

How to use:

�����������������������������������������������������������

1      �1.2           � -----------------

2      �1.2.A         � --------

3      �1.2.B         �         ---------

4      �              �

5      �1.3           � ERROR in parent

6      �1.3.A         � ERROR in task

7      �1.4           �  To Be Determined

�����������������������������������������������������������

There are twelve Gantt lines displayed on the screen. On

each line, the left side displays the task identity; the

right side displays the graphical duration of a task. The

length of a line is the task duration from the expected

start date (ESD) to the expected completion date (ECD) when

measured on the scale line.  As the formula for the task is

changed, the length and position of this line will change.

If this task is dependent upon another task then it may

change due to that task.

Seven samples of line display are shown above:

1)  Could be a summary level (the rollup of lines 2 & 3)

2&3)  These are tasks with dates and dependencies established

by their formula field.

4)  A blank line in which the task was left blank.

5)  This message 'ERROR in task' indicating

that a task cannot be calculated because at least one

of the three required data items is wrong or missing

data is missing in the task.

6)  This a message 'ERROR in parent' indicates

that a task cannot be calculated because some required

data is missing in the parent task. This task cannot

be calculated until the parent is correct.

7)  Example of a note where no start or finish time has

been determined.

page 5-1

Menu Commands

---------------

The menu can be reached by pressing the F1 key. A list of

commands will appear below the chart. By pressing the first

letter of each command that command will be executed. Some

commands will lead to additional commands.  The menu

structure is represented as follows:

keys            description

---------     ------------------------------

Esc           MENU

Esc,F             Files

Esc,F,L              Load

Esc,F,S              Save

Esc,F,A              Append

Esc,F,C              Clear

Esc,T             Tasks

Esc,T,I              Insert

Esc,T,C              Copy

Esc,T,I              Move

Esc,T,F              Formulas

Esc,T,F,R               Recalculate

Esc,T,F,E               Errors

Esc,T,F,F               Fixed Esd/Ecd

Esc,T,F,L               Link

Esc,T,D              Delete

Esc,T,S              Sort

Esc,T,L              Locate

Esc,T,N              Next

Esc,C             Calendar

Esc,C,W              Weekends

Esc,C,H              Holidays

Esc,R             Report

Esc,H                Header

Esc,C                Columns

Esc,D                Data

Esc,P                Print

Esc,A             Appearance

Esc,A,R              Refresh

Esc,A,C              Color

Esc,A,G              Gantt Line

Esc,A,Q              Quick Keys

Esc,D             DOS

Esc,Q             Quit

page 5-2

Menu Name:    Esc  (Escape Key)

Purpose:      To present the menu and terminate screen changes.

Restrictions: None.

How to use:   Press Escape (Esc) key and the F-key menu will be

replaced by a command line menu. The escape (Esc) can

be used to exit this menu. No chart updates can occur

while in this menu.

Menu Name:    Files,Load

Purpose:      To load a previously saved Gantt chart.

Restrictions: File must have been created by QUICK GANTT.

How to use:   Press Esc,F,L keys. Type the name of a valid file and

press enter.  Include the full path if not in the

current directory.

Menu Name:    Files,Save

Purpose:      To save a Gantt chart

Restrictions: File must have been created by QUICK GANTT.

How to use:   Press Esc,F,S keys. Type the name of a valid file

and press enter. If no file is entered the current

file is saved.  The startup file id "WORK.QG".

Menu Name:    Tasks,Insert

Purpose:      To insert one or more blank lines.

Restrictions: Lines are inserted ahead or the current position.

How to use:   Press Esc,T,I keys. Enter the number of lines to be

inserted then press the ENTER key.

page 5-3

Menu Name:    Tasks,Delete

Purpose:      To delete lines no longer required or to remove

blank lines.

Restrictions: One or more lines may be removed at a time.

How to use:   Press Esc,T,D. On the last line of the screen there will

appear a counter of the lines be be deleted. This wilo the

start with the current line.

Example:

If the cursor is at task line 5 then on the last

line of the screen will appear

Delete Lines 5..5

As the cursor is scrolled up or down the range will

change. When the ENTER key is pressed all lines

within this range will be deleted.

Menu Name:    Tasks,Copy

Purpose:      To copy lines to another area of the chart.

Restrictions: One or more lines may be copied. The new location

must be outside of the range.

How to use:   Press Esc,T,C. On the last line of the screen there will

appear a counter of the lines be be copied. This will the

start with the current line. The end of the range wil

change as the cursor is moved up and down. At the

end of the range press the ENTER key. This will

cause the "to" line to appear. Scroll up or down

to the desired location then press the ENTER key.

The Group of lines will be inserted ahead of this line.

Example:

If the cursor is at task line 5 then on the last

line of the screen will appear

Copy Lines 5..5

As the cursor is scrolled up or down the range will

change. When the ENTER key is pressed the copy

range will be defined and the "to" location will

appear.

Copy Lines 5..8 to 8

Scroll up or down to the desired input line then

press the ENTER key. The destination MUST be

out side the copy block. It will then be inserted

ahead of this line.

page 5-4

Menu Name:    Tasks,Move

Purpose:      To copy lines to another area of the chart.

Restrictions: One or more lines may be moved. The new location

must be outside of the range.

How to use:   Press Esc,T,M. On the last line of the screen there will

appear a counter of the lines be be moved. This will the

start with the current line. The end of the range wil

change as the cursor is moved up and down. At the

end of the range press the ENTER key. This will

cause the "to" line to appear. Scroll up or down

to the desired location then press the ENTER key.

The Group of lines will be inserted ahead of this line.

and deleted from their current location. Move is

identical to the Copy action except that the original

lines are deleted.

Menu Name:    Tasks,Sort

Purpose:      To re-arrange the order of the tasks in Gantt chart.

Restrictions: All tasks lines including blank lines can be sorted in

ascending or descending order for following fields:

1    Task

2    Responsibility

3    ESD (Expected Start Date)

4    ECD (Expected Completion Date)

How to use:   Press Esc,T,S. A numerical selection is made for one of the

four fields. If the selection is a positive number then

the sort is ascending, if the selection is a negative

number then the sort is descending

Ex:   1  sorts tasks in ascending order.

-1  sorts tasks in descending order.

Menu Name:    Tasks,Locate

Purpose:      To locate a literal string of characters in the Gantt

chart.

Restrictions: The search is in the Task, Description, Responsible

ESD, ECD and Formula fields.

How to use:   Press Esc,T,R. The enter the string to be searched for.

and press the ENTER key. The search will start from

first task. When a match is found the task will appear

as the first task in the screen.

page 5-5

Menu Name:    Tasks,Next

Purpose:      To locate the next occurrence of literal string

of characters in the Gantt chart.

Restrictions: The search is in the Task, Description, Responsible

ESD, ECD and Formula fields. It must follow the

Locate action.

How to use:   Press Esc,T,N.  The search will start from

last occurrence. When a match is found

the task will appear as the first task

in the screen.

Menu Name:    Tasks,Formulas,Recalc

Purpose:      To recalculate the date for all tasks on the Gantt

chart.

Restrictions: All tasks that have an entry in Task field are

recalculated.

How to use:   Press Esc,T,R. A recalculating message will appear at the

bottom of the screen along with the line number being

recalculated. There are no provisions to test for circular

dependencies and summary tasks proceeding the tasks being

summarized may require more then one recalculation.

Menu Name:    Tasks,Formulas,Errors

Purpose:      To locate tasks which have an error in the required

fields which will prevent calculation of task

schedules.

Restrictions: The search will begin with the first task.

How to use:   Press Esc,T,E.

page 5-6

Menu Name:    Tasks,Formulas,Fixed Dts

Purpose:      To establish absolute beginning and end dates for a task.

Restrictions: Both ESD and ECD dates must be entered.

How to use:   Press Esc,T,F. "Fixed ESD ECD" message will appear on

the bottom of the screen. Access to ESD and ECD fields

now occurs. When these dates are enterd the flow time

and a formula will be created. You may modify of change

or change the task dependencies at any time.

Menu Name:    Tasks,Formulas,Link

Purpose:      To simplify the effort when creating tasks of linking

tasks in the formula.

Restrictions: This will change or create the task dependency

How to use:   Enter the formula up to the parent or preceding task.

The task preceding this one may be several pages back

and you don't remember it's number. Press Esc,T, F, and

L. Then scroll to the dependent task. You will notice

a stationary cursor bar marking the original task. When

you get to the parent task press the enter key. This will

copy the parent task number into the formula and return

you to the original position on the chart.

page 5-7

Menu Name:    Calendar,Weekends

Purpose:      To include or exclude weekends (Saturday & Sunday)

from the available time period.

Restrictions: Weekends are either on or off for the entire Gantt chart.

How to use:   Press Esc,C,W. Schedule #1 will the appear with the

cursor on Sunday. Press 'N' if it is a non-workday or

'Y' if it is. The cursor will then move to the next

day. There must be at least one work day in the week.

When complete press the escape key (Esc) and schedule

#2, 3, 4, and 5 will appear. When complete with

schedule #5 you will return to the main screen.

��������������������ͻ

�    Schedule  #1    �

�     Work  Days     �

��������������������Ķ

�   Sunday    :No    �

�   Monday    :Yes   �

�   Tuesday   :Yes   �

�   Wednesday :Yes   �

�   Thursday  :Yes   �

�   Friday    :Yes   �

�   Saturday  :No    �

�                    �

� Total Workdays  5  �

��������������������ͼ

Total workdays must be greater then 0

Esc  to end

page 5-8

Menu Name:    Calendar,Holidays

Purpose:      To load dates that are to be excluded from the available

workdays for the entire Gantt chart.

Restrictions: A maximum of 120 dates can be loaded.

How to use:   Press Esc,C,H. The first of three holiday schedules

will appear.  A new screen will appear with the cursor

in a block in the upper left-hand corner. In this box

enter a date which will be a Non-work date in the

format of MM/DD/YYYY. Years between 00 and 99 are

assumed to be in the 1900's. Then press one of the

cursor movement keys (8,2,4 or 6) on the number pad.

Do not use the enter keys. The cursor and box will move

to the next position for another entry.  When all

entries have been made, press the escape key.  There

will be a pause as the dates are sorted and checked for

duplicates.  When complete press the escape (Esc) key

and the second and third holiday schedules will appear.

After the third one you will return to the main

screen.

�����������������������������������������������������������������ͻ

�              Holiday schedule #1                                �

�  Enter Specific Non-Work Dates [mo/da/yr] -- ### Esc. to end    �

�����������������������������������������������������������������Ķ

� 12/25/87  12/24/87  1/1/87                                      �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�                                                                 �

�����������������������������������������������������������������ͼ

page 5-8

Menu Name:    Report,Header

Purpose:      To identify the print character which will be used to

draw the chart and to create the report title.

Restrictions: Printer with IBM (tm) graphic fonts is preferred,

not necessary. Up to 4 title lines may be used.

How to use:   Press keys Esc,H. The screen shown below will

be presented.

���������������������������������������������������������������������ͻ

�                                 Report  Header                      �

�                                                                     �

�   Use graphic characters ..........(Y/N): Y                         �

�   Boxed or Open header ............(B/O): B                         �

�   Lines per page................(Min 15): 60                        �

�                                                                     �

�                                                                     �

�                                                                     �

�                                                                     �

�   Number of Title Lines ..........(0..4): 2                         �

�   Enter Title Line      2                                           �

�This is the second Title line                                        �

�   Corrections ...(Y/N):                                             �

���������������������������������������������������������������������ͼ

���������������������������������������������������������������������������

�                                Title line 1

�                        This is the second Title line

���������������������������������������������������������������������������

The above title block will be created on the Header screen as it is

defined. It is an example of a boxed graphics  header with two

title lines. The one below is an open header in non-graphics with

three title line.

Title line 1

This is the second Title line

This is a 3rd Title Line

+--------------------------------------------------------------------------

page 5-9

Menu Name:    Report,Columns

Purpose:      To define the columns and their size that will appear

on the report.

Restrictions: All columns except the Gantt chart are optional. Most

permit variable sizes.

How to use:   Press keys Esc,R,H. The screen shown below will

be presented.

�����������������������������������������������������������������������ͻ

�                            Report  Columns                            �

�                                                                       �

�   Enter Task width . . . . . (0..14): 4                               �

�   Enter Title width. . . . . (0..21): 21                              �

�   Enter Responsible width. . (0..15): 0                               �

�   Enter Flow width . . . . . . (0,4): 4                               �

�   Enter % Complete width.  . . (0,3): 3                               �

�   Enter Deviation width. .   . (0,5): 5                               �

�   Enter Print width  . . .(min..255): 80                              �

�   Gantt width ......................: 36                              �

�   Corrections....(Y/N):                                               �

�����������������������������������������������������������������������ͼ

�������������������������������������������������������������������������

�                                Title line 1

�                        This is the second Title line

�������������������������������������������������������������������������

�    �                     �    �   �     �

�Task�Title                �Flow�%Cm�d Sch�

�������������������������������������������������������������������������

The full header including column titles will be created on this

screen as they are defined.

page 5-11

Menu Name:    Report,Data

Purpose:      To define which tasks are to be printed on the report

by data content.

Restrictions:

How to use:   Press keys Esc,R,D. The screen shown below will

be presented.

�����������������������������������������������������������������������ͻ

�                            REPORT  DATA                               �

�                                                                       �

�                 From                          To                      �

�   Task . . . .:                 Task . . . :                          �

�   ESD  . . .  :                 ESD. . . . :                          �

�   ECD  . . . .:                 ECD. . . . :                          �

�   %Complete. .:   0             %Complete. : 100                      �

�   Deviation. .: -9999           Deviation. :  9999                    �

�   Flow . . . .:    0            Flow . . . : 9999                     �

�   Responsible :                                                       �

�   Sort by :                                                           �

�      1-Task 2-Responsible 3-ESD 4-ECD 5-Flow 6-%Cmpl 7-Dev            �

�   Corrections ......(Y/N):                                            �

�                                                                       �

�����������������������������������������������������������������������ͼ

page 5-12

Menu Name:    Report,Print

Purpose:      To initiate the actual printing of the report

and to determine the report output destination.

Restrictions: Output is to the printer unless a file is stated.

How to use:   Press keys Esc,R,P. The screen shown below will

be presented.

�������������������������������������������������ͻ

� Report by Tier or Natural order..(T/N): T       �

�   From Tier: 1    To Tier: 1                    �

� Output to Printer or Disk........(P/D): d       �

�   File Name: c:\qg\myfile.qg                    �

�                                                 �

� Quit, Change, Print:                            �

�������������������������������������������������ͼ

page 5-13

Menu Name:    Appearance,Refresh

Purpose:      To restore the screen if shifted or altered by system

error messages.

Restrictions: None.

How to use:   Press Esc,A,R.  The entire screen will be cleared and

replaced with a new copy of the chart.

Menu Name:    Appearance,Colors

Purpose:      To change the colors of the screen.

Restrictions: This feature should only be used on color monitors but

can be used on monochrome to reverse the white on black

standard.

How to use:   Press Esc,A,C. The first request will be for a foreground

color or the character color. Select a number between 0

and 15. Then a request will be made for a background

color or the field behind the character.  Select a number

between 0 and 7. Do not use the same color for both or

there will be no visible characters on the screen.

Number   Color            Number  Color

0     Black               8    Gray

1     Blue                9    Light Blue

2     Green              10    Light Green

3     Cyan               11    Light Cyan

4     Red                12    Light Red

5     Magenta            13    light Magenta

6     Brown              14    Yellow

7     white              15    Hi Intensity White

page 5-14

Menu Name:    Appearance,Gantt line

Purpose:      To change the image of the Gantt line on both the screen

and the printed chart.

Restrictions: Any character.

How to use:   Press Esc,A,G. There are 3 characters displayed on the

screen and the report, they are for the task line

character for the portion of the task completed, the

character for the portion of the task in work or not

yet complete and a character to mark the current date.

Each will be requested.  if no character change is

wanted press the ENTER key.  after the final character

request the the chart will be redrawn. These characters

are save in the definition file and loaded with the

program.

page 5-15

Menu Name:    Appearance,Quick keys

Purpose:      To replace multiple menu key strokes with a single

key by use of the 40 (F) function keys.

Restrictions: The first character of each menu item is used just

as if the keys were pressed.

How to use:   Press Esc,A,Q. There are 40 function keys which can

be defined to replicate menu key strokes. Each of

the 10 function keys can be used in normal condition,

in the shifted position by holding the 'Shift' key then

pressing the 'F' key, with the 'Ctrl' key and

with the 'Alt' key.

Key strokes and data are put in the action field just

as it would be typed using the menu; with two

exceptions, the 'Enter' key is replaced with '<'

and do not start with the 'Esc' key as you would on

the menu.

Once defined they are saved in the QG.DEF file which

is loaded with the program.

��������������������������������������������������ͻ

�         Norm      Quick Key Definitions          �

��������������������������������������������������Ķ

�       Action                           �  Menu   �

��������������������������������������������������Ķ

� F1 = AQ                                �1-QKeys  �

� F2 = FS<                               �2-Save   �

� F3 =                                   �         �

� F4 =                                   �         �

� F5 =                                   �         �

� F6 =                                   �         �

� F7 =                                   �         �

� F8 =                                   �         �

� F9 = RHCD{Esc}                         �9-Rpt    �

� F0 = RP{Esc}                           �10-Prnt  �

��������������������������������������������������Ķ

� Select-Keys, Key Group, [Ecs]:                   �

� Keys 1..0,                                       �

� Key Group N Normal, S Shifted, A Alt, C Cntl     �

��������������������������������������������������ͼ

page 5-16

Select the group you want to define and press the key for that

group. 'N' for the normal group, S for shifted, 'A' for the

alt group and 'C' for the control gorup. When this is done

the top line in window will identify the group.

Then press a number for the F-key; Ex. 2 is F2. The cursor

will then go to this line in the window. Type the key strokes

then press enter. The cursor will then move to the Menu column.

Enter the prompt you want to appear on the main screen menu.

Up to 8 characters can be used for each key. Four menu lines

will be created. One each for Norm, Shift, Ctrl and Alt.

When the Shift, Alt or Ctrl key is pressed, the function key

menu will appear under the chart.

Example above

Normal F1 is Appearance,Quickkeys

this will go to the Quick Key window.

F2 is Files,Save and ENTER

this will cause immediate saving of the

current file.

The F-key menu will appear as:

�5.1.4         �        ==========----

�������������������������������������������������������

1-QKeys 2-Save 9-Rpt 10-Prnt

Line #  1 of   1

File: WORK.QG

NOTE: If running from a floppy be sure to put your program

diskette back in the drive before Quiting. The key

definitions are save at this time and are reloaded when

the program is started.

page 5-16

Menu Name:    DOS

Purpose:      To execute DOS commands.

Restrictions: If you run this program from a hard disk then Command.com

should be in the root directory. If run from a floppy then

copy command.com to the floppy disk.

How to use:   Press F1,D.  You can then enter the DOS command. If doing a

directory listing be sure to include asterisks (*).

Ex; dir a:*.dat

Menu Name:    Quit

Purpose:      To terminate this program.

Restrictions: None.

How to use:   Press Esc,Q. If no changes have been made to the chart

since the last save (see F2 key), the program will halt. If

a change has occurred, Quick Gantt prompts "File not saved-

Quit without saving [Y/N]".  A "Y" response will halt the

program.  Any other character will cause Quick Gantt to

continue.

page 6-1

Key  Commands

---------------

Esc  - accesses the menu or exits the menu.

Home - moves the window to the first task.

End  - moves the window to the last task.

PgUp - moves the Gantt Chart window up 12 lines.

PgDn - moves the Gantt Chart window down 12 lines.

Cursor Up - moves up one task

Cursor Down - moves down one task

Tab Right - moves the cursor to the next screen field.

(Shift) Tab Right - moves the cursor to the previous screen field.

Shift, Ctrl, Alt - will also cause the Function key menus to appear

if they have been defined.

See the Menu section on Quick Keys for defining and use of the

Function (F) keys.

page 8-1

Messages

--------

Two types of messages exist - those that inform you about

current processing and those that identify an error or warning.

All of these appear at the bottom of the screen.

Informational messages:

"Line # xxx of xxx " is always present on line 24 and identifies

the current line being edited along with the total number of

lines in the chart.

"Fixed ESD ECD" appears in line 24 and is toggled on/off through

use of the menu or defined Quick keys.  When this appears

the ESD and ECD fields are accessible but the flow field is

not.

"Recalculating xxx" appears in line 24 when the chart is being

recalculated. The xxx is the current line being

recalculated.

"INSERT" appears in line 24 and is toggled on/off by the insert

key on the number pad.

"File :xxxxxxxx.xxx" appears on line 25 and is the name of the

current Gantt file being edited.

page 8-2

Error messages:

"ERROR in task" appears in the chart instead of a flow line when

one or more of the three required items is missing.

"ERROR in parent" appears in the chart instead of a flow line

when the task on which the current task depends upon has an

error.

"Invalid file name" appears in line 25 when the entered file

cannot be found.

"Value must be 0 to 9" appears when the key pressed is not within

the range.

"Exceeds maximum number of tasks" appears when attempting to add

another task and that task would exceed the total number

of tasks permitted in the Quick Gantt program.

"Invalid date  Re-enter" appears when attempting to begin or end a

task on a specific invalid date.

"Task does not exist" appears when making a task dependent upon

another which does not exist.

"ECD must equal or be greater then ESD" appears when in the fixed

ESD/ECD mode, the dates are in the wrong order.

"Input file is not for this program" appears when attempting to

load a file not created by Quick Gantt.

"Must be 'B','E' or 'S'" appears when entering the first field of

the formula.

"Must be 'B' or 'E' or valid date" appears when pressing the

wrong key in the second field of the formula.

page 9-1

Quick Gantt Tips

----------------

1.  Save your file regularly and ALWAYS save before printing,

sorting or working with blocks of tasks. No software or

system is without its bugs.

2.  For Floppy Use Only: Before quitting Quick Gantt return the

program disk to the active drive so that the current QG.DEF

file can be saved.  This file contains any changes made to

F-Key assignment, etc.

3.  If you want to preview your report before printing, you can

print it to a file. Using the DOS shell of the menu, you can

view the file of your report. If it is not what you want, simply

make the corrections and reprint.

4   The use of a text editor will allow additions, footnotes,

etc, that Quick Gantt may not provide.

5.  Printing can be a lengthy process, depending upon the size of

the chart.  You can print to a file, then QUIT Quick Gantt,

exiting to DOS. You can print the report in background,

using the DOS PRINT program thereby enabling the use of you

computer for other tasks.

6.  A report up to 255 characters can be built. This is often too

wide for many printers. By first printing to a file, then

using a simple program, "slices" can be printed and "glued"

side by side to create a full width Gantt chart. This works

well when using double wide font. You can create a wall size

chart that allows several people to view at one time. Be sure

you do not use a proportional print font.

7.  Some companies have standards for the symbols that appear on

a Gantt chart and most printers permit "user defined

characters" (see your user guide). You can define the

characters used for the Gantt line or others you may have

"edited" into the file so that when printed the chart meets

your standards. There are utilities for designing these fonts.

They look very good when done on a laser jet.

----------------end-of-author's-documentation---------------

Software Library Information:

This disk copy provided as a service of

The Public (Software) Library

We are not the authors of this program, nor are we associated

with the author in any way other than as a distributor of the

program in accordance with the author's terms of distribution.

Please direct shareware payments and specific questions about

this program to the author of the program, whose name appears

elsewhere in  this documentation. If you have trouble getting

in touch with the author,  we will do whatever we can to help

you with your questions. All programs have been tested and do

run.  To report problems,  please use the form that is in the

file PROBLEM.DOC on many of our disks or in other written for-

mat with screen printouts, if possible.  The P(s)L cannot de-

bug programs over the telephone.

Disks in the P(s)L are updated monthly, so if you did not get

this disk  directly from the P(s)L,  you should be aware that

the files in this set may no  longer be the current versions.

For a copy of the latest monthly software library newsletter

and a list of the 1,000+ disks in the library, call or write

The Public (Software) Library

P.O.Box 35705 - F

Houston, TX 77235-5705

(713) 665-7017