## Slide 1
SOFTWARE PROJECT MANAGEMENT
Overview ● Software Project Estimation
Software Project Metrics ● Software Project Planning
Notes: Objectives of Module 2
Present and discuss the basic concepts of Software Project Management:
  Software Metrics
  Software Cost and Timing Estimation
  Software Project Planning

## Slide 2
TOPICS
Overview
Metrics
Estimation
Planning

## Slide 3
Overview
To successfully manage software development, the project leader must determine:
1. Scope of work to be done
2. Risks to be incurred
3. Resources that will be required
4. Tasks to be accomplished
5. Effort (cost) that will be expended
6. Schedule to be followed
Software project management begins before the technical work starts.
Software project management ends when the software is retired.
Notes: Many factors, such as risks, resources, effort (cost), and schedule are difficult to determine in advance without information from previous projects.
In this vein, there is an emphasis on collecting software metrics and then using those metrics to make estimates which are reasonably close.
Industry has traditionally not been good at collecting software metrics on its projects because:
  Collecting metrics costs money and takes time, both of which have a direct impact on a project, particularly if they were not planned for in advance
  Collecting metrics can be tedious work -- something that many software practitioners tend to avoid

## Slide 4
Overview, Continued
Set Objectives and
Scope
Identify Metrics and
Measurement
Estimate Time, Man-
power, Materials
Perform Risk
Analysis
Conduct, Track, and
Control the Process
The Planning Process
Notes: Software in industry is usually developed under the following situations:
  As part of a product
  In support of a product
  As an activity of research and development
In the first two cases, budgets are allocated based on the cost estimates. If software is developed for a customer, the award of a contract may be on a firm, fixed-price basis or on a cost-plus or cost-reimbursable basis.

## Slide 5
SOFTWARE METRICS
Measuring Software
Why Measure Software?
Two Types of Measurements
Categories of Metrics
Size-Oriented Metrics
Function Points
Feature Points
Function-Oriented Metrics
Measuring Software Quality
Relationship of LOC to FP
Use of Productivity Data
Integrating Metrics into the Software Engineering Process
Collecting Software Metrics

## Slide 6
Measuring Software
Objectively measuring software is difficult.
  Most projects use only "lines of code" (LOC) for metrics.
  Much disagreement exists on what and how much to measure.
but
Accurately measuring software is vitally important to tracking and controlling software development.
LOC
Statements
Same Project
Different Metrics

## Slide 7
Why Measure Software?
To --
1. identify quality of the software product
2. assess productivity of the software developers
3. assess benefits of using development processes and tools
4. form a baseline for estimation
5. justify requests for tools and training

## Slide 8
Two Types of Measurements
Direct
-- cost
-- LOC
-- execution speed
-- binary code size
-- memory used
💧 easy to make
Indirect
-- functionality
-- quality
-- "-ilities"
💧 not easy to make

## Slide 9
Categories of Metrics
Size-Oriented
Function-Oriented
Human-Oriented
Productivity
Quality
Technical

## Slide 10
Size-Oriented Metrics
Let KLOC = "thousand lines of code"
Then we can define
  productivity = KLOC / person-months
  quality = defects in code / KLOC
  cost = dollars / KLOC
  documentation = pages of documents / KLOC
Efforts and costs include all elements of software development (analysis, design, code, test, etc.).

## Slide 11
Size-Oriented Metrics - Examples
Project Person- Cost KLOC Pages of Errors
Months Doc
A 24 $168,000 12.1 365 29
B 62 $440,000 27.2 1224 86
C 43 $314,000 20.2 1050 64
Project Productivity Quality Cost Documents
(KLOC/p-months) (errors/KLOC) ($/LOC) (pages/KLOC)
A 0.504 2.40 $13.88 30.17
B 0.439 3.55 $16.18 45.00
C 0.470 3.67 $15.54 51.98

## Slide 12
Problems with Size-Oriented Metrics
Definition of "lines of code"
  Programming language dependent
  Penalize well-designed shorter programs
  Cannot easily accommodate non-procedural languages
  Difficult to assess LOC before a program is written
Only known errors can be counted
Types, skill levels, and productivity of personnel varies

## Slide 13
Function Points - Fi Values
0
1
2
3
4
No
Influence
Incidental
Moderate
Average
Significant
1. Does the system require reliable backup? 8. Are the master files updated on-line?
2. Are data communications required? 9. Are the inputs, outputs, files, or inquiries complex?
3. Are there distributed processing functions? 10. Is the internal processing complex?
4. Is performance critical? 11. Is the code designed to be reusable?
5. Will the system run in an existing environment? 12. Are conversion and installation included in design?
6. Does the system require on-line data entry? 13. Is the system designed for multiple installations in
7. Does the on-line data entry require the input different organizations?
transaction to be built over multiple screens 14. Is the application designed to facilitate change and
or operations? ease of use?

## Slide 14
Function Points - Computation
Weighting Factor
Measurement Parameter Count Simple Average Complex Product
Number of user inputs x 3 4 6 =
Number of user outputs x 4 5 7 =
Number of user inquiries x 3 4 6 =
Number of files x 7 10 15 =
Number of external interfaces x 5 7 10 =
Count - Total

## Slide 15
Feature Points
Function Point Extensions
for Technical Software
Function points were originally designed for business information systems applications.
Extensions called feature points apply to technical software applications.
Algorithms are a bounded computational problem that is included within a specific computer program.

## Slide 16
Feature Points - Computation
Measurement Parameter Count Weight Product
Number of user inputs x 4 =
Number of user outputs x 5 =
Number of user inquiries x 4 =
Number of files x 7 =
Number of external interfaces x 7 =
Algorithms x 3 =
Count - Total

## Slide 17
Problems with Function Points and Feature Points
1. These metrics are based on subjective data.
2. Parameters can be difficult to obtain after-the-fact.
3. Function and Feature Points have no direct physical meaning.

## Slide 18
Function-Oriented Metrics
Focus is on "functionality" or "utility"
Both Function Points and Feature Points support the derivation of potentially useful data for the comparison of one project to another:
  Productivity = FP / person-month
  Quality = defects / FP
  Cost = $ / FP
  Documentation = pages / FP

## Slide 19
Measuring Software Quality
Before Delivery
  Program complexity
  Effective modularity
  Program size
After Delivery (most widely used)
  Number of defects uncovered in the field
  Maintainability of the system

## Slide 20
“After Delivery” Quality Metrics
Correctness - defects/KLOC or defects/FP over a one-year period
Maintainability - mean-time-to-change (MTTC), which is the time required to:
  analyze the change request,
  design a modification to the software,
  implement the change,
  test the changed software and the system as a whole, and
  distribute the changed system to the users

## Slide 21
“After Delivery” Quality Metrics, Continued
Integrity - based on threats and security
  Threat - probability that a specific attack will take place within a given period of time
  Security - probability that the attack of a specific type will be repelled
Useability - based on several perceptions of the users:
  skill required to use the program
  time required to learn the use of the program
  the increase in productivity from using the program
  the user's attitude towards the program

## Slide 22
Relationship of LOC to FP
The relationship of lines of code to feature points is a function of the programming language used and the quality of the design.
Rough estimates of the number of lines of code to create on feature point are:
Language LOC/FP
Assembly 300
COBOL 100
FORTRAN 100
Pascal 90
Ada 70
Object-Oriented Languages 30
Fourth Generation Languages 20
Automatic Code Generators 15

## Slide 23
Use of Software Productivity Data
Do not use LOC/person-month or FP/person-month to:
  Compare one group of developers to another
  Rate the performance of an individual
Many factors affect productivity:
Approximate % Variation
Factor in Productivity
People (number, experience) 90%
Problem (complexity, number of changes) 40%
Process (language, CASE) 50%
Product (reliability, environment) 140%
Resources (CASE, hardware, software) 40%

## Slide 24
Integrating Metrics into the Software Engineering Process
A historical baseline of metrics data is needed:
  Company, department, or unit should be identified in the scope of this data.
  Resistance to data collection should be expected in many corporate cultures.
At least three years of accurate, standardized metric data collection is needed to produce accurate planning estimates.

## Slide 25
Collecting Software Metrics
The process of collecting and using software metrics includes the following steps:
1. data collection
2. metrics computation
3. data evaluation
The following slides show a spreadsheet model for the collection and computation of historical software baseline data.
Software
Engineering
Process
Software
Managers
Practitioners
Data
Collection
Metrics
Computation
Data
Evaluation

## Slide 26
Spreadsheet Data Collection Model
Description Units Sample Data
Cost Data Input
Labor cost $/person-month $7,744
Labor year hours/year 1560
Data for Metrics Computation
Release type alphanumeric maintenance
Number of staff members people 3
Effort person-hours 4800
Elapsed time to complete hours 2000
Source code KLOC
Newly developed 11.5
Modified 0.4
Reused 0.8
Delivered 33.4

## Slide 27
Spreadsheet Data Collection Model
Description Units Sample Data
Data for Metrics Computation, Continued
Documentation pages
Technical 265
User 122
Number of errors to date numeric
Critical errors 0
Level 1 errors 12
Level 2 errors 14
Documentation errors 40
Maintenance to date person-hours
Modifications 3550
Error correction 1970

## Slide 28
Spreadsheet Data Collection Model
Description Units Sample Data
Project Data % of total
Analysis and specification 18%
Design 20%
Coding 23%
Testing 25%
Other - Describe 14%

## Slide 29
Spreadsheet Data Collection Model
Description Units Sample Data
Function-Oriented Data
Information Domain
1. No. of user inputs inputs 24
2. No. of user outputs outputs 46
3. No. of user inquiries inquiries 8
4. No. of files files 4
5. No. of ext. interfaces interfaces 2
Weights
1. No. of user inputs 3, 4, 6 4
2. No. of user outputs 4, 5, 7 4
3. No. of user inquiries 3, 4, 6 6
4. No. of files 7, 10, 15 10
5. No. of ext. interfaces 5, 7, 10 5

## Slide 30
Spreadsheet Data Collection Model
Description Units Sample Data
Function-Oriented Data, Continued
Processing Complexity Factors 0-5
1. backup and recovery required 4
2. data communication required 1
3. distributed processing function 0
4. performance critical 3
5. heavily utilized operating environment 3
6. online data entry 5
7. input transaction with multiple screens 4
8. master files updated online 4
9. input, output, files, queries complex 3
10. internal processing complex 3
11. code designed to be reusable 2
12. conversion/installation included in design 2
13. system design for multiple installation 4
14. maintainability/ease of use 5

## Slide 31
Spreadsheet Data Collection Model
Description Units Sample Data
Size-Oriented Metrics
Productivity and Cost
Output KLOC/p-month 0.905
Cost - all code $/KLOC $22,514
Cost - exclude reuse $/KLOC $24,028
Elapsed time months/KLOC 1.0
Documentation pages/KLOC 30
Documentation pages/p-month 10
Documentation $/page $739
Quality
Defects errors/KLOC 2.0
Cost of errors $/error $376

## Slide 32
Spreadsheet Data Collection Model
Description Units Sample Data
Function-Oriented Metrics
Productivity and Cost
Output FP/p-month 378
Cost - all code $/FP $700
Elapsed time FP/month 31.4
Documentation pages/FP 0.9
Quality
Defects errors/FP 0.064

## Slide 33
SOFTWARE PROJECT ESTIMATION
Overview
Resources
Decomposition Techniques
Using LOC or FP to Estimate Effort
Effort Estimation by Function
Effort Estimation by Task
Empirical Estimation Models
COCOMO
Putman Estimation Model

## Slide 34
Overview
Estimation of:
● resources
● costs
● schedules
Requires:
● experience
● historical information
● quantitative measures of qualitative data

## Slide 35
Overview, Continued
Degree of structure,
definition, variability
Size of effort
Complexity
based on
past efforts
Low-risk domain
Estimation
can be Risky

## Slide 36
Resources
1. Statement of software scope must be bounded
2. Software scope describes:
  function
  performance
  constraints
  interfaces
  reliability
evaluated together
Planning Task 1:
Software Scope

## Slide 37
Resources, Continued
Planning Task 2:
Estimation of
Needed
Resources
People
Hardware/software
tools
Specify:
  Required skills
  Availability
  Duration of tasks
  Start date
Specify:
  Description
  Availability
  Duration of use
  Delivery date

## Slide 38
Resources, Continued
CASE
Database
Maintenance Tools
Prototyping and
Simulation Tools
Integration and
Testing Tools
Programming Tools
Analysis and
Design Tools
Support Tools
Project Management
Framework Tools
Business Systems
Planning
CASE - Computer-Aided Software Engineering

## Slide 39
Resources, Continued
Two rules:
1. If existing software meets requirements, then
acquire and use it!
2. If existing software can meet requirements with some modification, then
be careful!
The cost of modification can exceed the cost of new development!
Reuse - A Resource

## Slide 40
Decomposition Techniques
LOC and FP Estimation
Effort Estimation

## Slide 41
Decomposition Techniques, Continued
The idea is that the person planning the software project:
  creates a bounded statement of the scope of the software
  decomposes the scope into smaller subfunctions
  estimates LOC or FP for each subfunction
  applies baseline productivity metrics (e.g., LOC/person-month) to LOC or FP estimates to produce a cost or effort estimate for each subfunction
  combines estimates for each subfunction to derive estimates for the entire project
LOC and FP Estimation

## Slide 42
Decomposition Techniques, Continued
FP estimation techniques require less detail than LOC
LOC is estimate directly while FP is estimated indirectly
Differences Between LOC and FP

## Slide 43
Using LOC or FP to Estimate Effort
1. Estimate LOC or FP values for each subfunction
  Use historical data (or intuition, if necessary)
  Three estimates: optimistic (o), most likely (m), and pessimistic (b)
2. Calculate expected value for each subfunction
3. Apply productivity data to get effort to be expended; two ways:
1. Total expected LOC or FP for all subfunctions and divide this by the expected LOC or FP completed per person-month (estimated from past projects); example:
Effort = 310 expected FP for project/5.5 expected FP per person-month
= 56 person-months
2. Multiply each subfunction LOC or FP by the adjusted productivity value (based on the estimated complexity of the function) and sum the results for all subfunctions in the project

## Slide 44
Effort Estimation by Function
Function Optimistic Most Likely Pessimistic Expected $/Line Line/Month Cost Months
User interface control 1800 2400 2650 2,340 $14 315 $ 32,760 7.4
2-D geometric analysis 4100 5200 7400 5,380 $20 220 $107,600 24.4
3-D geometric analysis 4600 6900 8600 6,800 $20 220 $136,000 30.9
Data structure mgmt 2950 3400 3600 3,350 $18 240 $ 60,300 13.9
Graphics display 4050 4900 6200 4,950 $22 200 $108,900 24.7
Peripheral control 2000 2100 2450 2,140 $28 140 $ 59,920 15.2
Design analysis 6600 8500 9800 8,400 $18 300 $151,200 28.0
Estimated Effort 33,360 $656,680 144.5
CAD Program Example
Estimated Cost: $ 656,680
Estimated Effort: 144.5 person-months

## Slide 45
Effort Estimation by Task
CAD Program Example
Function RA Design Code Test Total
User interface control 1.0 2.0 0.5 3.5 7.0
2-D geometric analysis 2.0 10.0 4.5 9.5 26.0
3-D geometric analysis 2.5 12.0 6.0 11.0 31.5
Data structure mgmt 2.0 6.0 3.0 4.0 15.0
Graphics display 1.5 11.0 4.0 10.5 27.0
Peripheral control 1.5 6.0 3.5 5.0 16.0
Design analysis 4.0 14.0 5.0 7.0 30.0
Total 14.5 61.0 26.5 50.5 152.5
Rate ($) 5200 4800 4250 4500
Cost ($) 75,400 292,800 112,625 227,250 708,075
Estimated Cost: $ 708,075
Estimated Effort: 152.5 person-months

## Slide 46
Empirical Estimation Models
Static single-variable model (example: COCOMO)
where
x is the estimated characteristic (LOC, FP, effort, etc.)
c and d are constants derived from data collected from past projects
Static multivariable model
where
x, y, ... and c, d, ... are as above
Dynamic multivariable model
Project resource requirements are determined over a series of time steps
Theoretical (example: Putman Estimation Model)
Uses equations derived from hypothesized expenditure curves

## Slide 47
COCOMO
Involves basic, intermediate, and advanced models
Basic model:
a(b), b(b), c(b), and d(b) are determined from the table:
Software Project a(b) b(b) c(b) d(b)
Organic 2.4 1.05 2.5 0.38
Semidetached 3.0 1.12 2.5 0.35
Embedded 3.6 1.20 2.5 0.32

## Slide 48
COCOMO, Continued
Example of COCOMO basic model on the CAD program:
Effort = 3.0 (LOC) ^ 1.12
= 3.0 (33.3) ^ 1.12
= 152 person-months
Development Time = 2.5 (Effort) ^ 0.35
= 2.5 (152) ^ 0.35
= 14.5 months
Thus, estimated number of people N is:
N = Effort / Development Time
= 152 / 14.5
= 11 people

## Slide 49
Putman Estimation Model
Data is derived from large projects
Model is applicable to smaller projects as well
The distribution of effort is described by the Rayleigh-Norden curve
System
Definition
Functional
Spec, design
Design
and coding
Test and
validation
Installation
Man-
power
Time

## Slide 50
SOFTWARE PROJECT PLANNING
What Software Project Planning Involves
Risk Analysis
Risk Management
Risk Monitoring - Project Tracking
Software Project Scheduling
Typical Task Network
Approaches to Project Tracking
Software Acquisition
Software Acquisition Decision Tree
Software Re-Engineering
Organizational Planning
Enhancements to a Good Organization
The Software Project Plan (SPP)

## Slide 51
What Software Project Planning Involves
1. Estimation
2. Risk Analysis
3. Scheduling
4. Acquisition Decision Making
5. Re-Engineering
6. Organizational Planning
Notes: Before starting a development project, we must:
1. Assess the risks involved
2. Develop a strategy for attacking the problem
3. Establish a mechanism for assessing the program
4. Organize people who will be building the project

## Slide 52
Risk Analysis
Project
Schedule
Overrun
Project Cost Overrun
Referent Point (Cost/Time Value)
Project Termination Will Occur

## Slide 53
Risk Management
Create risk management and monitoring plan
For each risk triplet, define the risk management steps
Risk management incurs additional project cost
For larger projects, there may be 30-40 risks identified
Example
Assume:
Risk = High staff turnover
Likelihood of occurrence = 70%
Impact = Increase project time by 15%, project cost by 12%
Risk Management steps may be:
1. Identify high turnover causes
2. Reduce causes before project starts
3. Develop techniques to assure work continuity in light of turnover

## Slide 54
Risk Monitoring - Project Tracking
1. Determine if predicted risk occurs
2. Properly apply risk aversion steps
3. Collect info for future risk analysis

## Slide 55
Software Project Scheduling
People-work relationships
Task definition and parallelism
Effort distribution
Scheduling methods
An example

## Slide 56
Software Project Scheduling
People-Work Relationships
Adding people to a project when behind schedule is counterproductive (adding people to a late project makes it later)
Using fewer people over a longer period of time is more beneficial than lots of people for a shorter period of time
Use of small, tightly-knit teams is productive
Inspire creativity and self-motivation within the structure of the project

## Slide 57
Software Project Scheduling
Task Definition and Parallelism
analysis
R
R
W
W
T
C
D
IT
VT
A
D
TP
TPr
R
●
●
●
Notes: Legend:
A: Analysis and specification
R: Review
D: Design
W: Walkthrough
C: Coding
T: Test
TP: Test planning
TPr: Test procedure
IT: Integration test
VT: Validation test

## Slide 58
Software Project Scheduling
Task Definition and Parallelism
Initial Sequential Events
Milestone 1 Occurs After --
  System analysis and specification
  System requirements review
Milestone 2 Occurs After --
  System architecture and data design
  System preliminary design review

## Slide 59
Software Project Scheduling
Task Definition and Parallelism
Parallel Events for Each Subfunction
Milestone P1 Occurs After --
  Procedural design
  Design walkthrough
Milestone P2 Occurs After --
  Coding
  Code walkthrough
Milestone P3 Occurs After --
  Unit testing

## Slide 60
Software Project Scheduling
Task Definition and Parallelism
System Testing Activities Can Be Performed In Parallel
Testing Milestone (After Unit Testing) --
  System test planning
  System test procedure
  System test review

## Slide 61
Software Project Scheduling
Task Definition and Parallelism
Integration Test Milestone - completed after system is assembled
Validation Test Milestone - completed last

## Slide 62
Software Project Scheduling
Effort Distribution
Analysis
and
Design
(40-50%)
Testing
and
Debugging
(30-40%)
Coding
(15-20%)

## Slide 63
Software Project Scheduling
Scheduling Methods
PERT - Program Evaluation and Review Technique
CPM - Critical Path Method
PERT and CPM are:
  Usually presented pictorially
  Quantitative tools for the planner to determine:
    Critical path
    Most likely time estimates
    Boundary times (earliest task start time, latest task start time, earliest task finish time, latest task finish time, total float time)

## Slide 64
Typical Task Network
Analysis
activities
complete
Perform
Data
Design
Begin
arch.
design
Design
interface
Integrate
program
arch.
Review
program
structure
Develop
test plan
and sched
Review
test
plan
Design
test
procedures
0
5
3
4
2
3
3
1
10
4/24/90
4/25/90
5/2/90
5/2/90
5/8/90
5/15/90
4/25/90
4/30/90
5/1/90

## Slide 65
Approaches to Project Tracking
Conducting periodic project status meetings in which each team member reports progress and problems
Evaluating the results of all reviews conducted throughout the engineering process
Determining whether formal project milestones have been accomplished by the scheduled date
Comparing the actual start date to the planned start date for each task
Meeting informally with software engineers to obtain their subjective assessments of the progress to date and problems on the horizon

## Slide 66
Software Acquisition
Make or buy?
  Who will use?
  Buy and modify?
  Contact outside contractor to build?
Decision based on:
  Reduced cost
  Earlier delivery date
  Not enough or properly skilled people to develop
  Better support outside

## Slide 67
Software Acqusition Decision Tree
Approach Cost
Build Simple $380,000
Difficult $450,000
Reuse Minor changes $275,000
Major changes Simple $310,000
Complex $490,000
Buy Minor changes $210,000
Major changes $400,000
Contract Without changes $350,000
With changes $500,000

## Slide 68
Software Re-Engineering
For often-used programs, build a controlled database of components for all to use.
Include documents, source code, user's guide, maintenance guide, test procedures and data, and a history of use with the components.
Software re-engineering may be enhanced by object-oriented design and implementation.

## Slide 69
Organizational Planning
There are lots of human organizational structures for software development
Possibilities - consider N people working for K years on M different functional tasks
Level of
Approach Interaction Coordination
1 Assign N people to M tasks Individual Project Mgr
( M > N )
2 Assign N people to M tasks Teams Project Mgr,
( M < N ) Team Leader
3 Assign N people to T teams, Formal Project Mgr,
each team resp. for 1 or Teams Team Leader
more tasks

## Slide 70
Enhancements to a Good Organization
The Chief Programmer Team
The Software Librarian
Egoless programming with a team environment

## Slide 71
The Software Project Plan (SPP)
A brief document which describes --
  The scope of the project
  The resources to be used
  Risks and risk avoidance techniques
  Cost and schedule
  Overall approach to software development
Management, technical staff, and customer are the primary reads of the SPP.
The SPP provides a starting point for the rest of the project.