## Slide 1
TOPICS
Overview
Metrics
Estimation
Planning

## Slide 2
SOFTWARE PROJECT ESTIMATION
Overview
Resources
Decomposition Techniques
Using LOC or FP to Estimate Effort
Effort Estimation by Function
Effort Estimation by Task
Empirical Estimation Models
COCOMO
Putman Estimation Model

## Slide 3
Overview
Estimation of:
● resources
● costs
● schedules
Requires:
● experience
● historical information
● quantitative measures of qualitative data

## Slide 4
Overview, Continued
Degree of structure,
definition, variability
Size of effort
Complexity
based on
past efforts
Low-risk domain
Estimation
can be Risky

## Slide 5
Resources
1. Statement of software scope must be bounded
2. Software scope describes:
  function
  performance
  constraints
  interfaces
  reliability
evaluated together
Planning Task 1:
Software Scope

## Slide 6
Resources, Continued
Planning Task 2:
Estimation of
Needed
Resources
People
Hardware/software
tools
Specify:
  Required skills
  Availability
  Duration of tasks
  Start date
Specify:
  Description
  Availability
  Duration of use
  Delivery date

## Slide 7
Resources, Continued
CASE
Database
Maintenance Tools
Prototyping and
Simulation Tools
Integration and
Testing Tools
Programming Tools
Analysis and
Design Tools
Support Tools
Project Management
Framework Tools
Business Systems
Planning
CASE - Computer-Aided Software Engineering

## Slide 8
Resources, Continued
Two rules:
1. If existing software meets requirements, then
acquire and use it!
2. If existing software can meet requirements with some modification, then
be careful!
The cost of modification can exceed the cost of new development!
Reuse - A Resource

## Slide 9
Decomposition Techniques
LOC and FP Estimation
Effort Estimation

## Slide 10
Decomposition Techniques, Continued
The idea is that the person planning the software project:
  creates a bounded statement of the scope of the software
  decomposes the scope into smaller subfunctions
  estimates LOC or FP for each subfunction
  applies baseline productivity metrics (e.g., LOC/person-month) to LOC or FP estimates to produce a cost or effort estimate for each subfunction
  combines estimates for each subfunction to derive estimates for the entire project
LOC and FP Estimation

## Slide 11
Decomposition Techniques, Continued
FP estimation techniques require less detail than LOC
LOC is estimate directly while FP is estimated indirectly
Differences Between LOC and FP

## Slide 12
Using LOC or FP to Estimate Effort
1. Estimate LOC or FP values for each subfunction
  Use historical data (or intuition, if necessary)
  Three estimates: optimistic (o), most likely (m), and pessimistic (b)
2. Calculate expected value for each subfunction
3. Apply productivity data to get effort to be expended; two ways:
1. Total expected LOC or FP for all subfunctions and divide this by the expected LOC or FP completed per person-month (estimated from past projects); example:
Effort = 310 expected FP for project/5.5 expected FP per person-month
= 56 person-months
2. Multiply each subfunction LOC or FP by the adjusted productivity value (based on the estimated complexity of the function) and sum the results for all subfunctions in the project

## Slide 13
Effort Estimation by Function
Function Optimistic Most Likely Pessimistic Expected $/Line Line/Month Cost Months
User interface control 1800 2400 2650 2,340 $14 315 $ 32,760 7.4
2-D geometric analysis 4100 5200 7400 5,380 $20 220 $107,600 24.4
3-D geometric analysis 4600 6900 8600 6,800 $20 220 $136,000 30.9
Data structure mgmt 2950 3400 3600 3,350 $18 240 $ 60,300 13.9
Graphics display 4050 4900 6200 4,950 $22 200 $108,900 24.7
Peripheral control 2000 2100 2450 2,140 $28 140 $ 59,920 15.2
Design analysis 6600 8500 9800 8,400 $18 300 $151,200 28.0
Estimated Effort 33,360 $656,680 144.5
CAD Program Example
Estimated Cost: $ 656,680
Estimated Effort: 144.5 person-months

## Slide 14
Effort Estimation by Task
CAD Program Example
Function RA Design Code Test Total
User interface control 1.0 2.0 0.5 3.5 7.0
2-D geometric analysis 2.0 10.0 4.5 9.5 26.0
3-D geometric analysis 2.5 12.0 6.0 11.0 31.5
Data structure mgmt 2.0 6.0 3.0 4.0 15.0
Graphics display 1.5 11.0 4.0 10.5 27.0
Peripheral control 1.5 6.0 3.5 5.0 16.0
Design analysis 4.0 14.0 5.0 7.0 30.0
Total 14.5 61.0 26.5 50.5 152.5
Rate ($) 5200 4800 4250 4500
Cost ($) 75,400 292,800 112,625 227,250 708,075
Estimated Cost: $ 708,075
Estimated Effort: 152.5 person-months

## Slide 15
Empirical Estimation Models
Static single-variable model (example: COCOMO)
where
x is the estimated characteristic (LOC, FP, effort, etc.)
c and d are constants derived from data collected from past projects
Static multivariable model
where
x, y, ... and c, d, ... are as above
Dynamic multivariable model
Project resource requirements are determined over a series of time steps
Theoretical (example: Putman Estimation Model)
Uses equations derived from hypothesized expenditure curves

## Slide 16
COCOMO
Involves basic, intermediate, and advanced models
Basic model:
a(b), b(b), c(b), and d(b) are determined from the table:
Software Project a(b) b(b) c(b) d(b)
Organic 2.4 1.05 2.5 0.38
Semidetached 3.0 1.12 2.5 0.35
Embedded 3.6 1.20 2.5 0.32

## Slide 17
COCOMO, Continued
Example of COCOMO basic model on the CAD program:
Effort = 3.0 (LOC) ^ 1.12
= 3.0 (33.3) ^ 1.12
= 152 person-months
Development Time = 2.5 (Effort) ^ 0.35
= 2.5 (152) ^ 0.35
= 14.5 months
Thus, estimated number of people N is:
N = Effort / Development Time
= 152 / 14.5
= 11 people

## Slide 18
Putman Estimation Model
Data is derived from large projects
Model is applicable to smaller projects as well
The distribution of effort is described by the Rayleigh-Norden curve
System
Definition
Functional
Spec, design
Design
and coding
Test and
validation
Installation
Man-
power
Time