## Slide 1
TOPICS
Overview
Metrics
Estimation
Planning

## Slide 2
SOFTWARE PROJECT PLANNING
What Software Project Planning Involves
Risk Analysis
Risk Management
Risk Monitoring - Project Tracking
Software Project Scheduling
Typical Task Network
Approaches to Project Tracking
Software Acquisition
Software Acquisition Decision Tree
Software Re-Engineering
Organizational Planning
Enhancements to a Good Organization
The Software Project Plan (SPP)

## Slide 3
What Software Project Planning Involves
1. Estimation
2. Risk Analysis
3. Scheduling
4. Acquisition Decision Making
5. Re-Engineering
6. Organizational Planning
Notes: Before starting a development project, we must:
1. Assess the risks involved
2. Develop a strategy for attacking the problem
3. Establish a mechanism for assessing the program
4. Organize people who will be building the project

## Slide 4
Risk Analysis
Project
Schedule
Overrun
Project Cost Overrun
Referent Point (Cost/Time Value)
Project Termination Will Occur

## Slide 5
Risk Management
Create risk management and monitoring plan
For each risk triplet, define the risk management steps
Risk management incurs additional project cost
For larger projects, there may be 30-40 risks identified
Example
Assume:
Risk = High staff turnover
Likelihood of occurrence = 70%
Impact = Increase project time by 15%, project cost by 12%
Risk Management steps may be:
1. Identify high turnover causes
2. Reduce causes before project starts
3. Develop techniques to assure work continuity in light of turnover

## Slide 6
Risk Monitoring - Project Tracking
1. Determine if predicted risk occurs
2. Properly apply risk aversion steps
3. Collect info for future risk analysis

## Slide 7
Software Project Scheduling
People-work relationships
Task definition and parallelism
Effort distribution
Scheduling methods
An example

## Slide 8
Software Project Scheduling
People-Work Relationships
Adding people to a project when behind schedule is counterproductive (adding people to a late project makes it later)
Using fewer people over a longer period of time is more beneficial than lots of people for a shorter period of time
Use of small, tightly-knit teams is productive
Inspire creativity and self-motivation within the structure of the project

## Slide 9
Software Project Scheduling
Task Definition and Parallelism
analysis
R
R
W
W
T
C
D
IT
VT
A
D
TP
TPr
R
●
●
●
Notes: Legend:
A: Analysis and specification
R: Review
D: Design
W: Walkthrough
C: Coding
T: Test
TP: Test planning
TPr: Test procedure
IT: Integration test
VT: Validation test

## Slide 10
Software Project Scheduling
Task Definition and Parallelism
Initial Sequential Events
Milestone 1 Occurs After --
  System analysis and specification
  System requirements review
Milestone 2 Occurs After --
  System architecture and data design
  System preliminary design review

## Slide 11
Software Project Scheduling
Task Definition and Parallelism
Parallel Events for Each Subfunction
Milestone P1 Occurs After --
  Procedural design
  Design walkthrough
Milestone P2 Occurs After --
  Coding
  Code walkthrough
Milestone P3 Occurs After --
  Unit testing

## Slide 12
Software Project Scheduling
Task Definition and Parallelism
System Testing Activities Can Be Performed In Parallel
Testing Milestone (After Unit Testing) --
  System test planning
  System test procedure
  System test review

## Slide 13
Software Project Scheduling
Task Definition and Parallelism
Integration Test Milestone - completed after system is assembled
Validation Test Milestone - completed last

## Slide 14
Software Project Scheduling
Effort Distribution
Analysis
and
Design
(40-50%)
Testing
and
Debugging
(30-40%)
Coding
(15-20%)

## Slide 15
Software Project Scheduling
Scheduling Methods
PERT - Program Evaluation and Review Technique
CPM - Critical Path Method
PERT and CPM are:
  Usually presented pictorially
  Quantitative tools for the planner to determine:
    Critical path
    Most likely time estimates
    Boundary times (earliest task start time, latest task start time, earliest task finish time, latest task finish time, total float time)

## Slide 16
Typical Task Network
Analysis
activities
complete
Perform
Data
Design
Begin
arch.
design
Design
interface
Integrate
program
arch.
Review
program
structure
Develop
test plan
and sched
Review
test
plan
Design
test
procedures
0
5
3
4
2
3
3
1
10
4/24/90
4/25/90
5/2/90
5/2/90
5/8/90
5/15/90
4/25/90
4/30/90
5/1/90

## Slide 17
Approaches to Project Tracking
Conducting periodic project status meetings in which each team member reports progress and problems
Evaluating the results of all reviews conducted throughout the engineering process
Determining whether formal project milestones have been accomplished by the scheduled date
Comparing the actual start date to the planned start date for each task
Meeting informally with software engineers to obtain their subjective assessments of the progress to date and problems on the horizon

## Slide 18
Software Acquisition
Make or buy?
  Who will use?
  Buy and modify?
  Contact outside contractor to build?
Decision based on:
  Reduced cost
  Earlier delivery date
  Not enough or properly skilled people to develop
  Better support outside

## Slide 19
Software Acqusition Decision Tree
Approach Cost
Build Simple $380,000
Difficult $450,000
Reuse Minor changes $275,000
Major changes Simple $310,000
Complex $490,000
Buy Minor changes $210,000
Major changes $400,000
Contract Without changes $350,000
With changes $500,000

## Slide 20
Software Re-Engineering
For often-used programs, build a controlled database of components for all to use.
Include documents, source code, user's guide, maintenance guide, test procedures and data, and a history of use with the components.
Software re-engineering may be enhanced by object-oriented design and implementation.

## Slide 21
Organizational Planning
There are lots of human organizational structures for software development
Possibilities - consider N people working for K years on M different functional tasks
Level of
Approach Interaction Coordination
1 Assign N people to M tasks Individual Project Mgr
( M > N )
2 Assign N people to M tasks Teams Project Mgr,
( M < N ) Team Leader
3 Assign N people to T teams, Formal Project Mgr,
each team resp. for 1 or Teams Team Leader
more tasks

## Slide 22
Enhancements to a Good Organization
The Chief Programmer Team
The Software Librarian
Egoless programming with a team environment

## Slide 23
The Software Project Plan (SPP)
A brief document which describes --
  The scope of the project
  The resources to be used
  Risks and risk avoidance techniques
  Cost and schedule
  Overall approach to software development
Management, technical staff, and customer are the primary reads of the SPP.
The SPP provides a starting point for the rest of the project.