## Slide 1
TOPICS
Overview
Metrics
Estimation
Planning

## Slide 2
SOFTWARE METRICS
Measuring Software
Why Measure Software?
Two Types of Measurements
Categories of Metrics
Size-Oriented Metrics
Function Points
Feature Points
Function-Oriented Metrics
Measuring Software Quality
Relationship of LOC to FP
Use of Productivity Data
Integrating Metrics into the Software Engineering Process
Collecting Software Metrics

## Slide 3
Measuring Software
Objectively measuring software is difficult.
  Most projects use only "lines of code" (LOC) for metrics.
  Much disagreement exists on what and how much to measure.
but
Accurately measuring software is vitally important to tracking and controlling software development.
LOC
Statements
Same Project
Different Metrics

## Slide 4
Why Measure Software?
To --
1. identify quality of the software product
2. assess productivity of the software developers
3. assess benefits of using development processes and tools
4. form a baseline for estimation
5. justify requests for tools and training

## Slide 5
Two Types of Measurements
Direct
-- cost
-- LOC
-- execution speed
-- binary code size
-- memory used
💧 easy to make
Indirect
-- functionality
-- quality
-- "-ilities"
💧 not easy to make

## Slide 6
Categories of Metrics
Size-Oriented
Function-Oriented
Human-Oriented
Productivity
Quality
Technical

## Slide 7
Size-Oriented Metrics
Let KLOC = "thousand lines of code"
Then we can define
  productivity = KLOC / person-months
  quality = defects in code / KLOC
  cost = dollars / KLOC
  documentation = pages of documents / KLOC
Efforts and costs include all elements of software development (analysis, design, code, test, etc.).

## Slide 8
Size-Oriented Metrics - Examples
Project Person- Cost KLOC Pages of Errors
Months Doc
A 24 $168,000 12.1 365 29
B 62 $440,000 27.2 1224 86
C 43 $314,000 20.2 1050 64
Project Productivity Quality Cost Documents
(KLOC/p-months) (errors/KLOC) ($/LOC) (pages/KLOC)
A 0.504 2.40 $13.88 30.17
B 0.439 3.55 $16.18 45.00
C 0.470 3.67 $15.54 51.98

## Slide 9
Problems with Size-Oriented Metrics
Definition of "lines of code"
  Programming language dependent
  Penalize well-designed shorter programs
  Cannot easily accommodate non-procedural languages
  Difficult to assess LOC before a program is written
Only known errors can be counted
Types, skill levels, and productivity of personnel varies

## Slide 10
Function Points - Fi Values
0
1
2
3
4
No
Influence
Incidental
Moderate
Average
Significant
1. Does the system require reliable backup? 8. Are the master files updated on-line?
2. Are data communications required? 9. Are the inputs, outputs, files, or inquiries complex?
3. Are there distributed processing functions? 10. Is the internal processing complex?
4. Is performance critical? 11. Is the code designed to be reusable?
5. Will the system run in an existing environment? 12. Are conversion and installation included in design?
6. Does the system require on-line data entry? 13. Is the system designed for multiple installations in
7. Does the on-line data entry require the input different organizations?
transaction to be built over multiple screens 14. Is the application designed to facilitate change and
or operations? ease of use?

## Slide 11
Function Points - Computation
Weighting Factor
Measurement Parameter Count Simple Average Complex Product
Number of user inputs x 3 4 6 =
Number of user outputs x 4 5 7 =
Number of user inquiries x 3 4 6 =
Number of files x 7 10 15 =
Number of external interfaces x 5 7 10 =
Count - Total

## Slide 12
Feature Points
Function Point Extensions
for Technical Software
Function points were originally designed for business information systems applications.
Extensions called feature points apply to technical software applications.
Algorithms are a bounded computational problem that is included within a specific computer program.

## Slide 13
Feature Points - Computation
Measurement Parameter Count Weight Product
Number of user inputs x 4 =
Number of user outputs x 5 =
Number of user inquiries x 4 =
Number of files x 7 =
Number of external interfaces x 7 =
Algorithms x 3 =
Count - Total

## Slide 14
Problems with Function Points and Feature Points
1. These metrics are based on subjective data.
2. Parameters can be difficult to obtain after-the-fact.
3. Function and Feature Points have no direct physical meaning.

## Slide 15
Function-Oriented Metrics
Focus is on "functionality" or "utility"
Both Function Points and Feature Points support the derivation of potentially useful data for the comparison of one project to another:
  Productivity = FP / person-month
  Quality = defects / FP
  Cost = $ / FP
  Documentation = pages / FP

## Slide 16
Measuring Software Quality
Before Delivery
  Program complexity
  Effective modularity
  Program size
After Delivery (most widely used)
  Number of defects uncovered in the field
  Maintainability of the system

## Slide 17
“After Delivery” Quality Metrics
Correctness - defects/KLOC or defects/FP over a one-year period
Maintainability - mean-time-to-change (MTTC), which is the time required to:
  analyze the change request,
  design a modification to the software,
  implement the change,
  test the changed software and the system as a whole, and
  distribute the changed system to the users

## Slide 18
“After Delivery” Quality Metrics, Continued
Integrity - based on threats and security
  Threat - probability that a specific attack will take place within a given period of time
  Security - probability that the attack of a specific type will be repelled
Useability - based on several perceptions of the users:
  skill required to use the program
  time required to learn the use of the program
  the increase in productivity from using the program
  the user's attitude towards the program

## Slide 19
Relationship of LOC to FP
The relationship of lines of code to feature points is a function of the programming language used and the quality of the design.
Rough estimates of the number of lines of code to create on feature point are:
Language LOC/FP
Assembly 300
COBOL 100
FORTRAN 100
Pascal 90
Ada 70
Object-Oriented Languages 30
Fourth Generation Languages 20
Automatic Code Generators 15

## Slide 20
Use of Software Productivity Data
Do not use LOC/person-month or FP/person-month to:
  Compare one group of developers to another
  Rate the performance of an individual
Many factors affect productivity:
Approximate % Variation
Factor in Productivity
People (number, experience) 90%
Problem (complexity, number of changes) 40%
Process (language, CASE) 50%
Product (reliability, environment) 140%
Resources (CASE, hardware, software) 40%

## Slide 21
Integrating Metrics into the Software Engineering Process
A historical baseline of metrics data is needed:
  Company, department, or unit should be identified in the scope of this data.
  Resistance to data collection should be expected in many corporate cultures.
At least three years of accurate, standardized metric data collection is needed to produce accurate planning estimates.

## Slide 22
Collecting Software Metrics
The process of collecting and using software metrics includes the following steps:
1. data collection
2. metrics computation
3. data evaluation
The following slides show a spreadsheet model for the collection and computation of historical software baseline data.
Software
Engineering
Process
Software
Managers
Practitioners
Data
Collection
Metrics
Computation
Data
Evaluation

## Slide 23
Spreadsheet Data Collection Model
Description Units Sample Data
Cost Data Input
Labor cost $/person-month $7,744
Labor year hours/year 1560
Data for Metrics Computation
Release type alphanumeric maintenance
Number of staff members people 3
Effort person-hours 4800
Elapsed time to complete hours 2000
Source code KLOC
Newly developed 11.5
Modified 0.4
Reused 0.8
Delivered 33.4

## Slide 24
Spreadsheet Data Collection Model
Description Units Sample Data
Data for Metrics Computation, Continued
Documentation pages
Technical 265
User 122
Number of errors to date numeric
Critical errors 0
Level 1 errors 12
Level 2 errors 14
Documentation errors 40
Maintenance to date person-hours
Modifications 3550
Error correction 1970

## Slide 25
Spreadsheet Data Collection Model
Description Units Sample Data
Project Data % of total
Analysis and specification 18%
Design 20%
Coding 23%
Testing 25%
Other - Describe 14%

## Slide 26
Spreadsheet Data Collection Model
Description Units Sample Data
Function-Oriented Data
Information Domain
1. No. of user inputs inputs 24
2. No. of user outputs outputs 46
3. No. of user inquiries inquiries 8
4. No. of files files 4
5. No. of ext. interfaces interfaces 2
Weights
1. No. of user inputs 3, 4, 6 4
2. No. of user outputs 4, 5, 7 4
3. No. of user inquiries 3, 4, 6 6
4. No. of files 7, 10, 15 10
5. No. of ext. interfaces 5, 7, 10 5

## Slide 27
Spreadsheet Data Collection Model
Description Units Sample Data
Function-Oriented Data, Continued
Processing Complexity Factors 0-5
1. backup and recovery required 4
2. data communication required 1
3. distributed processing function 0
4. performance critical 3
5. heavily utilized operating environment 3
6. online data entry 5
7. input transaction with multiple screens 4
8. master files updated online 4
9. input, output, files, queries complex 3
10. internal processing complex 3
11. code designed to be reusable 2
12. conversion/installation included in design 2
13. system design for multiple installation 4
14. maintainability/ease of use 5

## Slide 28
Spreadsheet Data Collection Model
Description Units Sample Data
Size-Oriented Metrics
Productivity and Cost
Output KLOC/p-month 0.905
Cost - all code $/KLOC $22,514
Cost - exclude reuse $/KLOC $24,028
Elapsed time months/KLOC 1.0
Documentation pages/KLOC 30
Documentation pages/p-month 10
Documentation $/page $739
Quality
Defects errors/KLOC 2.0
Cost of errors $/error $376

## Slide 29
Spreadsheet Data Collection Model
Description Units Sample Data
Function-Oriented Metrics
Productivity and Cost
Output FP/p-month 378
Cost - all code $/FP $700
Elapsed time FP/month 31.4
Documentation pages/FP 0.9
Quality
Defects errors/FP 0.064